## Workplan
Work plan
Outcome 1 |  |  |  | Improved design and monitoring of SP programs and increased use of evidence on SP impact system contributes to increased coverage of social protection
Output | Annual targets |  |  | List of activities | [11 empty] | Total Cost (EUR) - excluding OXFAM | Agencies involved | Implementing partner/s involved
| 2020 | 2021 | 2022 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 1.1. Evidence-based frameworks and tools to guide, monitor and evaluate the implementation of the National Social Protection Policy Framework are developed and implemented | - 1 research on role of SP on economic development finalized -M&E framework for CT programme (women and children) drafted | M&E framework for CT programme (women and children) drafted | - Actuarial Valuation for 3 branches of NSSF finalized - At least a policy revision initiated based on the actuarial revision recommendations | 1.1.1 Technical assistance to selected budget entities in implementing NSPC M&E Framework and linking programme M&E frameworks with RB budgeting. | [11 empty] | 163818 | UNICEF, (ILO) | GS-NSPC | bar: Q2 to Q2
|  |  |  | 1.1.2 - Provide technical assistance and financial support to implement a gender-sensitive analysis of the financial situation (actuarial review) of the NSSF Schemes (actuarial review) | [12 empty] | ILO (OXFAM) | NSSF, GS-NSPC | bar: Q3 to Q4
|  |  |  | 1.1.3 - Develop research on the potential role of expanded Social Protection for Cambodia Socio-economic development | [12 empty] | ILO (OXFAM) | GS-NSPC | bar: Q2 to Q4
Output 1.2 –Feasibility studies and tools for expansion of the social protection schemes are developed | Family Package options paper and costed programme document developed and validated 50 districts with PwD identification system | 57 districts with PwD identification system | 50 Districts with PwD163,181 identification system All provinces have trained staff to support identification of PwD Revised Disability Allowance Sub-decree Costed Disability Allowance Programme | 1.2.1 Technical assistance to design and development of gender- and -child -sensitive integrated / family package of social assistance programmes (cash transfer for pregnant women and children, cash scholarships, disability allowance, and social pension for elderly) and administrative models /institutional arrangements for their delivery | [11 empty] | 254417 | UNICEF, (ILO, OXFAM) | GS-NSPC, MOSVY | bar: Q2 to Q4
|  |  |  | 1.2.2 Technical assistance and financial support to strengthen the delivery of the disability allowance programme (identification, data collection and costing) | [12 empty] | UNICEF | MOSVY | bar: Q2 to Q4
Output 1.3. The CSO-Trade Union Network can engage effectively with decision makers for improvement of the design and monitoring of selected SP programs | 1 Common recommendation produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 1 recommendation produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF | 2 Common recommendations produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 2 recommendations produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF x gender sensitive policy improvements proposed | 5 Common recommendations produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 recommendations produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF | 1.3.1 Capacity strengthening of the CSO-TU Network on gender-sensitive and results-based budgeting, design and monitoring of selected SP programmes. | [12 empty] | OXFAM | CSO-TU Network | bar: Q2 to Q1
|  |  |  | 1.3.2 Impact and needs analysis at the level of constituents of the CSO-TU Network regarding selected SP programs, including development of recommendations for improvement of budgeting, design and monitoring. | [12 empty] | OXFAM | CSO-TU Network | bar: Q3 to Q2
|  |  |  | 1.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for improvement of budgeting, design and monitoring of selected SP programs. | [12 empty] | OXFAM (ILO) | CSO-TU Network | bar: Q4 to Q4
|  |  |  | 1.3.4 Extract learning from the CSO-TU engagement on selected SP programs and share with relevant stakeholders, including GCSPF . | [12 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2
Outcome 2 |  |  |  | Social Protection institutions enhance their planning, budgeting and M&E capacities in alignment with the Public Finance Management Reform Programme
Output | Annual targets |  |  | List of activities | [11 empty] | Total Cost (EUR) - excluding OXFAM | Agencies involved | Implementing partner/s involved
| 2020 | 2021 | 2020 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 2.1 -Tools and Knowledge in place for improved planning, budgeting and tracking of social protection expenditures including a consistent mechanism for compilation of revenues and expenditures | - 1 report integrating a list of social protection programs, coverage and costs, including a note on information gaps and respective briefing - 1 assessment on links among the SP M&E framework and the results structure/KPIs and budgets of SP agencies/budget entities - Assessment of existing budget formulation, execution and reporting documents and their alignment with RB and PB for 9 budget owners implementing social assistance (including at SNA level) | - 1 report integrating a list of social protection programs, coverage and costs, including a note on information gaps and respective briefing - Expenditure data base developed and the possibilities for extension into SP database explored (link to activity 2.1.2) - implemenation of functional classification of social protection schemes improved by at least 1 line Ministry '- 120 officials from MoSVY and DoSVYs, MoP and MoI trained on RB Budget formulation - Guidelines on improved budget process and hands-on training implemented | - financial review of the SP in Cambodia finalized including a list of social protection programs, coverage and costs - recommendations produced under the SP Financial Review incorporated into the revised SP Policy Framework revised Action Plan | 2.1.1 – Technical assistance to review implementation of the functional classification of social protection schemes by selected ministries implementing SP programmes | [11 empty] | 264500 | ILO (UNICEF) | GS-NSPC; MEF | bar: Q3 to Q2; Q1 to Q2
|  |  |  | 2.1.2 – Technical assistance to develop social protection tracking expenditure database for MoSVY-supported social assistance programmes | [12 empty] | UNICEF | GS-NSPC, MOSVY | bar: Q1 to Q4
|  |  |  | 2.1.3 Provide technical assistance and support to building the capacities of the selected line ministries and institutions responsible for social assistance to develop adequate/high-quality results-based frameworks in support of programme-based budget formulation, execution and reporting | [12 empty] | UNICEF (ILO = OXFAM) | GS-NSPC, MEF, MOSVY | bar: Q2 to Q4
|  |  |  | 2.1.4 – Technical assistance to implement a comprehensive gender-sensitive Financial Review of Social Protection in Cambodia as input to MTR of SPPF | [12 empty] | ILO (UNICEF) (OXFAM) | GS-NSPC | bar: Q2 to Q2
Output 2.2 – Social budget forecasting system established |  | - a social budgeting model developed and operational - social budgeting model results used to inform the MTR of SPPF | - social budgeting model incorporated within MEF planning tools | 2.2.1 - Provide capacity building (training and coaching) on social budgeting forecasting model to MEF departments | [11 empty] | 120000 | ILO | GS-NSPC; MEF | bar: Q3 to Q4
|  |  |  | 2.2.2 Provide technical assistance and jointly develop tools to develop gender-sensitive social budgeting forecasting model for Cambodia | [12 empty] | ILO | GS-NSPC; MEF | bar: Q1 to Q4
Output 2.3 – The CSO-TU Network can engage effec-tively with decision makers for more fiscal space to increase the coverage of the informal economy workers under the NSPPF, especially women workers | 1 of common recommendation for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 1 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | 2 of common recommendations for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 2 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | 5 of common recommendations for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | 2.3.1 Capacity strengthening of the CSO-TU Network on overall PFM and financing of SP systems, including GRB | [12 empty] | OXFAM (ILO) | CSO-TU Network | bar: Q2 to Q1
|  |  |  | 2.3.2 Needs and contributory capacity assessment of constituents of the CSO-TU Network, in particular of female informal economy workers, including development of recommendations for increased coverage | [12 empty] | OXFAM | CSO-TU Network | bar: Q3 to Q2
|  |  |  | 2.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased fiscal space for better coverage of informal economy workers, women in particular. | [12 empty] | OXFAM, (ILO) | CSO-TU Network | bar: Q4 to Q4
|  |  |  | 2.3.4 Extract learning and lessons from the CSO-TU engagement on increasing the coverage for informal economy workers and share with relevant stakeholders, including GCSPF | [12 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2
Outcome 3 |  |  |  | Service providers at sub-national level (SNAs) are better able to implement social protection services
Output | Annual targets |  |  | List of activities | [11 empty] | Total Cost (EUR) - excluding OXFAM | Agencies involved | Implementing partner/s involved
| 2020 | 2021 | 2022 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 3.1- Service providers have improved skills to deliver social protection services | Training curriculum | 140 key government officials and 140 sub-national officials trained Study on knowledge-sharing implemented Study on roles and existing mechanisms for SA at SNA level implemented |  | 3.1.1 Technical assistance to develop training curriculum for sub-national administrations (SNAs) on social protection, with focus on disability allowance | [11 empty] | 168182 | UNICEF (OXFAM) | MOSVY | bar: Q3 to Q1
|  |  |  | 3.1.2 Provide financial support for implementation of a child and gender-sensitive training program on social assistance for national and subnational government officials (Focus on Provincial/Capital levels) | [12 empty] | UNICEF, (ILO, OXFAM) | MOSVY | bar: Q4 to Q4
|  |  |  | 3.1.3 Technical assistance to assess existing knowledge sharing and information dissemination channels and develop strategies for capacity building of SNAs | [12 empty] | UNICEF, (ILO, OXFAM) | MOSVY,MOI | bar: Q4 to Q1
|  |  |  | 3.1.4 Research (Assessment) of roles and existing mechanism at SNA level in implementing SA programmes | [12 empty] | UNICEF (OXFAM) | MOSVY
Output 3.2 - Increased capacity and engagement of the CSO-TU Network to engage in social accountability mechanisms related to SP delivery at subnational level | 1 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 1 of common recommendations on gender sensitive social accountability mechanisms accepted. | 2 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 2 of common recommendations on gender sensitive social accountability mechanisms accepted. | 3 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 3 of common recommendations on gender sensitive social accountability mechanisms accepted. | 3.2.1 Capacity strengthening of of the CSO-TU Network on the social accountability framework and how this applies to SP delivery at subnational level. | [11 empty] | - | OXFAM | CSO-TU Network | bar: Q2 to Q1
|  |  |  | 3.2.2 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased social accountability in SP delivery at subnational level | [13 empty] | CSO-TU Network | bar: Q1 to Q2
|  |  |  | 3.2.3 Awareness building amongst constituents regarding social accountability mechanisms they can make use of. | [12 empty] | OXFAM | CSO-TU Network | bar: Q2 to Q4
|  |  |  | 3.2.4 Extract learning from the CSO-TU engagement on the use of social accountability mechanisms within SP delivery. | [12 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2