## Workplan
Work plan
Outcome 1: A framework created of a strengthened National Social Registration (NSR) system with improved mechanisms for interoperability with humanitarian relief as well as rapid relief to vulnerable groups impacted by shocks, including economic shocks.
Output | Annual target/s |  | List of activities | [6 empty] | Implementing partners involved
| 2020 | 2021 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Total Cost
Result 1.1: The National Social Registry is adjusted to include sub-sets of data for rapid response (including humanitarian) and linked to the social health insurance schemes. |  | Updated NSR system (database) approved, with interoperability with the RRR, URB, SHIA’s. All RRR and URB HH included as subsets of NSR. | Activity 1.1.1: Establish a Rapid Response Register, in collaboration with the WB, under the purview of the Federal Ministry of Humanitarian Affairs, Disaster Management and Social Development (FMHDS), developing criteria that can capture vulnerabilities caused by the COVID-19 measures and the economic slowdown. This includes identifying potential complementary registries/ databases held by other ministries/ trade unions/ grass-root organisations. | x | x | x |  |  | 80000 | FMHDS, NASSCO
|  |  | Activity 1.1.2 – Harmonize and consolidate existing database of Internally Displaced Persons (IDPs) and vulnerable groups across all the humanitarian, early recovery and development programs in Yobe and Adamawa State into the existing Unified Registry of Beneficiaries (URB). | x | x | x |  |  |  | NASSCO
|  |  | Activity 1.1.3: Create linkages between both the URB and RRR database to the NSR, as a sub-set, developing harmonized checklists and synthesize the databases to establish interoperability and integration. |  |  | x | x |  |  | NASSCO
|  |  | Activity 1.1.4: Step-by step manual created and tested to validate of households in the RRR and URB and bring them onto the social register. |  |  | x | x |  |  | NASSCO, SOCU
Result 1.2: Coordination structures and ownership of NSR among key stakeholders at federal and state level are improved. |  | Guidelines on use of State Social Registry agreed by all government and non-government social protection, humanitarian and health insurance partners active in Yobe and Adamawa. At least 3 MoU’s signed with State Health Insurance Schemes, including in Yobe and Adamawa. | Activity 1.2.1: Establishment of and/or support to technical working groups between NASSCO, NHIS, social partners and State Health Insurance Schemes and local government representatives and humanitarian actors at Yobe and Adamawa state level to lead holistic responses in social protection and emergencies/crises going forward, with SOCU acting as the secretariat for the committee. | x | x | x | x |  | 20000 | NASSCO, NHIS, SOCU, SHIS, EU, Action Against Hunger, Save the Children, Humanitarian partners, social partners
|  |  | Activity 1.2.2: Support MoU development for mining of the NSR (including RRR and URB) by social Health insurance schemes at state level; prioritising the two target states as well as states with operational health insurance schemes for the informal sector: e.g. Lagos, Abuja (FCT), Katsina and Kebbi. MoU’s include guidelines created for “pilot” projects coupling cash transfer with health insurance. |  |  | x | x |  |  | NASSCO, SOCU, State Health Insurance Schemes of Yobe and Adamawa, NHIS
Result 1.3: Strategy created for NASSCO in the context of emergencies, natural disasters, forced displacements, protracted fragility and economic crises to establish contingency plans and multi-year funding strategies to run adaptive social protection mechanisms. |  | Emergency strategy in place, including agreements, MoU’s, SoPs, and Manuals and approved by relevant authorities. | Activity 1.3.1: Creation of a framework that guides rapid development of a beneficiary register as a first response in times of crisis, including emergency protocols, roles and responsibilities across all relevant actors via agreements including standby agreements, MOUs, Standard Operating Procedures, manuals of operations, etc. |  | x | x | x | x | 50000 | ILO, NASSCO, SOCU
|  |  | Activity 1.3.2: Development of flexible (geographical and categorical) targeting and registration protocols and procedures under RRR and NSR as a whole, meeting special needs of vulnerable groups, including IDP’s, refugees, women, persons with disability, informal workers and migrant workers. |  |  | x | x | x
Outcome 2: Capacity building programme put in place of the FMHDS, NASSCO and partners to implement and monitor effectively shock-sensitive gender-sensitive and disability-inclusive social protection systems and programmes, including COVID-19 response measures for all residents of Nigeria. | [8 empty] | 50000 | ILO, NASSCO, SOCU
Result 2.1: FMHDS, NASSCO staff and SOCUs in target states know how to use and implement new NSR modalities in humanitarian and non-humanitarian scenarios. |  | At least 60 staff members trained | Activity 2.1.1: Development of training materials of NSR guidelines and modalities for key FMHDS and NASSCO staff. |  | x | x
|  |  | Activity 2.1.2: Development of training materials and procedures for the State Operations Coordinating Units (SOCU) of NASSCO in building and delivery of shock-responsive social safety nets. |  |  |  | x | x
|  |  | Activity 2.1.3: organization of series of trainings at federal and state level for managers and implementers (users). |  |  |  | x | x