Possible areas for future investigation

|  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- |
| 1/ Standardization |  |  |  |
| 2/ Services per category of dependency |  |  |  |
| 3/ Human Resources policy |  |  |  |
| 4/ Organization and coordination |  |  |  |
| 5/ Legal reform for the establishment of the LTCare system |  |  |  |
| 6/ Costing model |  |  |  |
| 7/ Stakeholders analysis |  |  |  |
| 8/ Finalization of the recommendations |  |  |  |

>> based on international standards, methodologies (GIP experts)

>> based on practice in Thailand (documentation, surveys,…)

>> who does what? (taskforces)

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 1/ Standardization |  |  |  |  |
| 1 | To develop national standards for LTC classification, ADL assessment tools - Agreed categories of dependency (“dependency clusters”) - Rules for the classification of beneficiaries according to the categories Costing task No1 | GIP experts can provide benchmarks | Analysis of the ADL assessment tools and results | Taskforce No1 (to be nominated) |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 2/ Services per category of dependency |  |  |  |  |
| 1 | To further design the required services per category of dependency and the required personnel for each service Level of care and needs for each level of dependency | GIP experts can provide examples | Document Thailand’s pilot projects Assess cost structure of institutions Conduct additional surveys | Taskforce No1 (to be nominated) |
| 2 | To estimate the cost for each service - Number of hours required per service and category of dependency, at home and in institutions Costing task No1 - Additional costs for equipment, infrastructure, accommodation, transportation, etc. Costing task No3 | GIP experts (benchmarks - example a nurse should be paid 1.1 * average wage) |  |  |
| 3 | To estimate the number and percentage of potential beneficiaries for each category of dependency and per age group (will be used for the costing as well) |  | ADL results |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 3/ Human Resources policy |  |  |  |  |
| 1 | To develop the HR requirements (list of occupations, job descriptions) | GIP experts (international practice) | Document practice: surveys, pilots | Taskforce No2 (to be nominated) |
| 2 | To assess the requirements for each type of personnel (# of nurses needed, # of care managers, etc.) |  |  |  |
| 3 | To compare the requirements with the situation and assess the gaps (mis-match) |  |  |  |
| 4 | To develop an HR investment plan (new curricula, number of persons in need of training for each type of training) | GIP experts (methodology) |  |  |
| 5 | To estimate the cost of the HR investment plan Costing task No2/5 |  |  |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 4/ Organization and coordination |  |  |  |  |
| 1 | To further elaborate on the organization and role of the different actors at national and sub-national levels | GIP experts (methodology) | Document practice: pilots | Taskforce No3 (to be nominated) |
| 2 | To reinforce the coordination (cross-ministerial, national/sub-national level, at delivery level…) for a shared view of the LTC policy and for an efficient delivery of LTC services | Single Window Service approach |  |  |
| 3 | To develop coordination with other policies (such as child care policy) |  |  |  |
| 4 | To prepare the description of the main processes for the design of the IT system (general and detailed specifications of the IT system) NB the IT system could be a strong factor of integration at national level (coordination of policies, monitoring) and delivery level (Single Window) | GIP experts (methodology) | IT experts in Thailand (description of the processes) |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 5/ Legal reform for the establishment of the LTCare system |  |  |  |  |
| 1 | To analyse existing laws and regulations and identify loopholes |  | Legal review | Legal expert |
| 2 | To provide recommendations based on benchmarks and international experience | GIP experts ILO conventions |  |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 6/ Costing model |  |  |  |  |
| 1 | To finalize the costing model based on the detailed choice of parameters | GIP experts | ILO RAP model (adapted to LTC) | Taskforce No4 (to be nominated) |
| 2 | To complete the costing with a fiscal space analysis, and financing strategy |  |  |  |
| 3 | To develop a Rate of Return model (assumption that LT care will contribute to the economic growth through the development of a new sector of the economy) |  |  |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 7/ Stakeholders analysis |  |  |  |  |
| 1 | To conduct a stakeholders analysis to understand the views of all stakeholders and prepare an advocacy campaign |  | Based on methodology used for UCS | Stakeholders analyst (HISRO) |
| 2 | To identify additional research subjects needed in order to fill the knowledge/advocacy gaps |  |  |  |
| 3 | To conduct the required research |  |  | ?? |
| 4 | To develop a communication and advocacy strategy and tools |  | Social marketing and communication campaigns, parliament …. |  |

|  |  | >> based on international standards | >> based on practice in Thailand | >> who does what? |
| --- | --- | --- | --- | --- |
| 8/ Finalization of the recommendations |  |  |  |  |
| 1 | To write the LTC system’s design and report | GIP experts |  | ILO, writing team, translation team |
| 2 | To present it to individual policy makers (ministers of MSDHS, MOL, MOH, MOI, PM Office, MOE, NESDB, MOF/Bureau of Budget) |  |  | UN SPF/RTG team on social protection under the UNPAF |
| 3 | To launch the report in a national launching event |  |  |  |
| 4 | To develop a roadmap for the implementation of the LTC system | GIP experts |  |  |

Recommendations:

- A same person can provide inputs into different task forces

- And also provide support to the whole project manager

- Dr Ladda was the project manager of the previous LTcare project

- We had a big team of researchers including academics and so on

- Khun Viennarat could be a good coordinator

- We could also have focal points on specific issues

- Would also be good to have in our task forces experts coming from Japan

- Formal invitation would need to be sent to JICA -> joint project (ILO-JICA-RTG)

- This project does not duplicate with other efforts but it is a CO-PROJECT where we try to compile what we have done and join forces for the design of the LTC system for Thailand

- The project manager of the JICA project is from MOPH/MSDHS

- Ask to the Ministry of Health, Labour and SW in Japan