WORKPLAN 2012 – SPF Coalition

| Activity | Deliverables | Objective | Agencies | Date |
| --- | --- | --- | --- | --- |
| 1. Country operations | Matrix of SPF country activities which includes information on: - Description of the activity; - Country; - Involved agency(ies); - Focal person. | Update mapping exercise of SPF activities: - What is going on where? - Who is doing what? - Tools needed? - Who can take a lead where? - Who to contact? | ILO will send a matrix to all the coalition members who are asked to update and complete it. | 1. The matrix will be send by the ILO to the initiative members before 29 February 2012. 2. All members have to complete the matrix before 31 May 2012. |
| Country operations in selected countries | Selecting number of countries based on the criteria discussed during the meeting | Joint work plan to implement SPF in selected countries | Coalition members | End 2012 and ongoing |
|  | Report on joint activities to support national decision makers to implement (elements of a) a SPF |  | ILO, UNICEF, UNDP | End 2012 |
| 2. Response to Global requests (Rio+20, recommendations G20, post-MDGs) | Note on a list of different ongoing and planned processes and intervention points to get the SPF into the post-MDG agenda | Mapping exercise: - What processes are going on? - What is planned, when and where? - Where can we add inputs? | - WHO (Peter Mertens) - UNHabitat (Yamina Djacta) - FES (Sara Burke) - Helpage | 31 May 2012 |
|  | Data and indicators | Mapping exercise: - What tools are available? - What data is available where? - Definitions? - How to connect? | - ILO - UNICEF - UNDP - UNWomen | 31 May 2012 |
| 3. Coordination – mobilization | Material and other tools for reaching out to the civil society at the country level |  | - UNFPA (Azza Karam) -ESN (Thierry Weishaupt) - Helpage | 31 May 2012 |
| 4. Funding strategy | 5 page funding strategy paper (think piece) | Analysis of possible funding strategies for the SPF-Initiative | - Timo Voipio - Ministry for Foreign Affairs, Finland - Marie Christine Coënt - Ministry for Labor, Employment and Public Health, France - ILO, WHO, UNICEF | 31 May 2012 |
| 5. Planned coordination activities |  | Follow up ILC, G20, Rio 20+ |  | July 2012 |