## Approach 1 2022-23
GLO/19/53/EUR - SC 190731 | Improving synergies between social protection and public finance management
Work plan cross-country component of Approach 1
Outcome 1 |  | To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10.
Output | List of activities | Annual target/s |  |  |  | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
|  | 2020 | 2021 | 2022 | 2023 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Output 1.1 (Result 1.2 of the logframe): Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations. | Activity 1.1: Research on multiplier effects and coordination of other research activities | Annual target/s 2021: backstopping of 7 action research; Annual target/s 2022: backstopping of 8 action research exploring new research on positive impact of investing in SP; Annual target/s 2023: 1 research study with external validity | 338250 | ILO | UNICEF, GCSPF
| Activity 1.2: Backstopping analytical work and tool applications, in particular on fiscal space | Annual target/s 2021: backstopping of 4 tool applications or analytical work; Annual target/s 2022: backstopping of 24 countries and 4 tool applications or analytical work; Annual target/s 2023: backstopping of 16 countries and 4 tool applications or analytical work |  | ILO | UNICEF, GCSPF, country teams, EU Delegations
| Activity 1.3: Further development of the EU SPaN Guidance Package | Annual target/s 2022: Update of SPaN guidance package or other nexus tools; Annual target/s 2023: Update of SPaN guidance package or other nexus tools |  | UNICEF | ILO
| Activity 1.4: Refining of ISPA tools, TRANSFORM and ILO good practice guides | Annual target/s 2022: development of new ISPA tool on SP financing; Annual target/s 2023: Min. 3 tools refined |  | ILO | UNICEF, GCSPF
| Activity 1.5: Support to regional and global meetings/workshops/conferences | Annual target/s 2021: Min. 5 events; Annual target/s 2022: Mini. 2 events; Annual target/s 2023: Mini. 1 event |  | ILO | UNICEF, GCSPF
| Activity 1.7: Communication and visibility | Annual target/s 2020: See communication plan indicators and targets |  | ILO | UNICEF, GCSPF, Steering committee
| Activity 1.8: Overall management of the Action, including monitoring and final evaluation | Annual target/s 2020: 1 inception report; Annual target/s 2021: 1 financial and narrative progress report 1 evaluatbility report; Annual target/s 2022: 1 financial and narrative progress report; Annual target/s 2023: 1 final financial and narrative report 1 final evaluation |  | ILO | UNICEF, GCSPF
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | 2.1 Training and capacity building | Annual target/s 2021: Min. 3 webinars or trainings; Annual target/s 2022: Min. 3 webinars or trainings supported by cross-country; Annual target/s 2023: Min. 1 webinars or trainings supported by cross-country | 45000 | ILO | UNICEF, GCSPF, country teams, EU Delegations

## Approach 2 2022-23
GLO/19/53/EUR | Improving synergies between social protection and public finance management
Work plan Approach 2
Outcome 1 |  | A minimum of 10 countries receive on-demand high quality, gender-responsive, disability-inclusive technical advisory services that are relevant and produce technically, financially and politically feasible recommendations on how to improve the national social protection system, programmes or delivery mechanisms
Output | List of activities | Annual target/s |  |  |  | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
|  | 2020 | 2021 | 2022 | 2023 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Outputs 1.1 Selection of 10 countries through a minimum of two call for proposals, based on criteria of relevance and sound operations | 1.1.1 Launch and disseminate the calls for proposals, receive the proposals | Annual target/s 2020: min. 15 requests received; Annual target/s 2021: min. 15 requests received |  | ILO | EU Delegation, Government
| 1.1.2 Organise the selection of requests through the operational steering committee | Annual target/s 2020: min. 5 requests approved; Annual target/s 2021: min. 5 requests approved |  | ILO | Operational Committee
| 1.1.3 Support services to develop the proposals | Annual target/s 2020: min. 5 of requests supported; Annual target/s 2021: min. 10 of requests supported |  | ILO | Government, social partners, CSO
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | 1.2.1. Set up a multidisciplinary technical team to deliver the services in line with the request | Annual target/s 2020: Composition of the team; Annual target/s 2021: min. 3 of countries receiving services and backstopping missions; Annual target/s 2022: min. 3 of countries receiving services and backstopping missions; Annual target/s 2023: min. 3 of countries receiving services and backstopping missions |  | ILO | Experts and academias
| 1.2.2. Establish a process for participatory implementation of the advisory services , to the extent possible drawing on existing consultation or dialogue structures | Annual target/s 2020: TDR of the participatory process; Annual target/s 2021: min. 7 countries with a process for participatory implementation |  | ILO | EU Delegation, Governments, UN agencies
| 1.2.3. Create evidence base to address the request, including information and data on gender, disability, shock-responsiveness, costs, financing and digitalization | Annual target/s 2021: min. 3 countries with social protection data and information; Annual target/s 2022: min. 5 countries with social protection data and information |  | ILO | Goverrnments, including National Statistical agencies, UN agencies
| 1.2.4. Identify different scenarios to improve the social protection system, programme or delivery mechanisms (in line with the request) - scenarios are designed ensuring coherence and coordination within the social protection system across sectors and administrative levels and beyond social protection sector and with related policy areas such as employment policies. | Annual target/s 2021: min. 3 of countries with identified scenarios; Annual target/s 2022: min. 5 of countries with identified scenarios |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.5. Analyse the identified scenarios regarding their cost, financing sources, political economy implications, institutional capacity, technical feasibility and taking into consideration implications regarding their effects on gender, disability, shock-responsiveness and potential of using new technologies in their implementation | Annual target/s 2021: min. 3 scenarios that are costed per country; Annual target/s 2022: min. 3 scenarios that are costed per country |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.6. Disseminate findings so that national stakeholders, including social partners are well-informed about social protection needs and possible actions to address them | Annual target/s 2021: min. 1 dissemination and advocacy events (per country); Annual target/s 2022: mini. 1 dissemination and advocacy event (per country); Annual target/s 2023: mini. 1 dissemination and advocacy event (per country) |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.7. Summarize delivered technical advisory services in an outcome document (country report, strategy, roadmap, draft policy, etc.) | Annual target/s 2022: min. 1 outcome document at country level; Annual target/s 2023: min. 1 outcome document at country level |  | ILO | Operational Committee, Governments
| 1.2.8. Establish a framework and tools for monitoring progress in implementing the project outcomes (country report, strategy, roadmap, draft policy, etc.) and in extending social protection | Annual target/s 2020: min. 3 countries with a monitoring framework; Annual target/s 2021: min.8 of countries with a monitoring framework; Annual target/s 2023: min.8 of countries with a monitoring framework completed |  | ILO | Operational Committee, National statistical agencies

## Angola 2022-23
| GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Angola
Work Plan of the Programme "Improving Synergies between Social Protection and Public Finance Management |  | Agency and implementation modalities | Implementation partners | 2022 | [11 empty] | 2023
|  |  |  | Q1 | Q2 | Q4 | Q2 | Q3 | Q4 | Q3 | Q2 | Q4 | Q4 | Q2 | Q4 | Q1 | Q2
PRODUCT 1. A Social Action Policy is implemented and costed |  | ILO
1.1 | Definition of the Action Plan of the Strategy for the Implementation of the National Social Action Policy | ILO
1.1.1 | Carry out a diagnosis of the Angolan Social Protection system, using the CODI-ISPA tool to assess the existing schemes and programmes, the legal framework, the population covered, the content and level of benefits, gaps, coordination mechanisms, among others. | Use of the ILO's National Evaluation-based Dialogue methodology, international consultancy, synergies with the ACTION PORTUGAL project in the Contributory Social Protection component | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF HEALTH MINISTRY OF EDUCATION MINISTRY OF FINANCE ILO COMMISSION INSS OCS IMF WB
1.1.2 | Identify the different strategic actions within the scope of the implementation of the Operationalisation Strategy of the Social Action Policy towards a universal coverage and improve the efficiency and effectiveness of social protection expenditure
1.1.3 | Identify the different scenarios for the different strategic actions and the different approaches for their implementation. (phases / timing / regional coverage etc.)
1.2 | Costing of strategic actions | ILO
1.2.1 | Formulate the methodological approach and assumptions of the strategic options of the costing model | ILO internal technical work | MASFAMU MINISTRY OF PLANNING MINISTRY OF FINANCE ILO COMMISSION OCS IMF WB
1.2.2 | Collect relevant macroeconomic, financial, expenditure and socio-economic data and estimate key parameters
1.2.3 | Draw up the costing document for the different strategic options
1.2.4 | Estimate financing gaps in social protection to achieve the SDG target
1.2.5 | Identify and assess funding options for strategic actions based on the country's economic, fiscal, social and political viability
1.3 | Social Dialogue and Advocacy | ILO
1.3.1 | Organise national consultations for concertation, validation, monitoring of defined strategic actions, implementation and financing options | Social dialogue and ILO in-house technical work, national advocacy consultancy | MASFAMU MINISTRY OF PLANNING MINISTRY OF FINANCE ILO COMMISSION OCS IMF WB
1.3.2 | Prepare a document: Action Plan of the Implementation Strategy of the National Social Action Policy with the strategic actions, their costing and financing modalities resulting from the validation process at the level of social dialogue for validation and approval
1.3.3 | Prepare an advocacy strategy for the Strategy Action Plan document of Implementation of the National Social Action Policy resulting from the validation at the level of social dialogue for validation and approval
PRODUCT 2. A performance-based budgeting model in social protection institutions is implemented |  | UNICEF
2.1 | Creation and operationalisation of an inter-ministerial working group | UNICEF
2.1.1 | Creation of an inter-ministerial working group for the pilot of Performance Based Budgeting, including technicians from the Ministry of Finance, Ministry of Economy and Planning and the institutions that regulate the Social Protection system in Angola |  | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF FINANCE INSS
2.1.2 | Draw up a training programme based on the Working Group's objectives
2.2 | Performance-based budgeting model | UNICEF
2.2.1 | Systematise the evaluation of the budgeting cycle in accordance with international standards, using the ongoing PEFA process and the four main phases into which the cycle is divided |  | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF FINANCE INSS
2.2.2 | Develop a methodological and conceptual note on the theoretical foundations of performance-based budgeting, including its components
2.2.3 | Prepare a manual on how to implement performance-based budgeting in the social protection sector
2.2.4 | Formulate an Action Plan with pilot test included to launch a performance-based budget in a sample of social institutions
PRODUCT 3: The coordination of the social protection system is strengthened |  | UNICEF & ILO
3.1 | Operationalisation of the National Social Protection Committees | UNICEF
3.1.1 | Map the coordination mechanisms in social protection and evaluate them through a SWOT analysis or similar methodology | UNICEF technical work supported by a consultancy | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF HEALTH MINISTRY OF EDUCATION MINISTRY OF FINANCE ILO COMMISSION INSS OCS IMF WB
3.1.2 | Propose an architecture to strengthen coordination between the different Councils, including mechanisms for articulation between institutions and social protection programmes, including the programme for ex-combatants | UNICEF technical work
3.1.3 | Developing the tools and operational procedures for liaison between the councils | UNICEF technical work
ILO
3.1.4 | Prepare a communication and advocacy plan that strengthens coordination mechanisms | Social dialogue and internal ILO technical work
3.1.5 | Technical support for the functioning of the National Social Protection Committees, such as support to promote and facilitate social dialogue, inter-ministerial dialogue, training, exchange of experiences, facilitation of specialised technical sessions, among others. | Social dialogue and internal ILO technical work
PRODUCT 4. Public institutions with improved capacities to improve the budgeting and delivery of Social Protection services |  | UNICEF & ILO
4.1 | Capacity building in the areas of planning, budgeting and expenditure control | ILO
4.1.1 | Carry out a diagnosis of the institutions and their human resources to assess institutional capacity in the areas of planning, budgeting and expenditure control | Internal ILO technical work | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF FINANCE ILO COMMISSION INSS OCS
4.1.2 | Prepare an institutional capacity building plan that responds to the needs identified in the diagnosis (4.1.1)
4.2 | Institutional capacity-building in the management of social protection programmes | UNICEF & ILO
4.2.1 | Technical support and training in the implementation of programmes aimed at extending contributory social security to informal economy workers and low-income and rural workers | Technical and training work by the ILO and in partnership with ACTION Portugal | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF FINANCE ILO COMMISSION INSS OCS
4.2.2 | Technical support and training in the implementation of social programmes and services within the scope of Basic Social Protection | UNICEF technical and training work
4.2.3 | Training for the ILO Commission on issues related to the extension of social protection coverage in Angola and the establishment of a Social Protection Floor in Angola | ILO technical and training work in partnership with ACTION
4.3 | Evaluate the effects of the project's institutional capacity building | UNICEF & ILO
| Carry out a final evaluation at the end of project implementation to assess the effects of institutional capacity building on the management, planning and financing of Social Protection programmes | Independent consultancy | MASFAMU MAPTSS MINISTRY OF PLANNING MINISTRY OF FINANCE ILO COMMISSION INSS OCS

## Burkina Faso 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Burkina Faso
Outcome 1 | Enhanced conception, coordination, tracking and financing of gender-sensitive and inclusive schemes and programmes, of the social protection system of Burkina Faso towards SDGs 1 and 10
Output | List of activities |  | 2022 | [11 empty] | 2023 |  |  |  |  | Annual target/s
|  | Responsible | Janv | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Year 1 (Oct 2019-Dec 2020) | Year 2 (Jan 2021-Dec 2021) | Year 3 (Jan 2022-May 2023)
Outputs 1.1 An overall review of the national social protection system using ISPA tools allows stakeholders adopting consensual recommendations for improving the social protection system in Burkina Faso and provide evidences for the adoption of the new PNPS | 1.1.1 Provide technical support the SP-CNPS and develop tools to reinforce the multisector coordination and facilitate a national dialogue through technical committees and working groups for the formulation of the social protection floor guaranties. | ILO UNICEF SP-CNPS MFPTPS | [17 empty] | - Study on unemployment insurance - Simulation cash transfer study | 1 workshop | bar: 2022 May
1.1.2 Implement capacity-building activities in order to secure the active participation of all actors of the social protection sector in the national dialogue for the overall review and adoption of recommendations for strengthening the system.
| 1.1.3 Conduct in consultation with the stakeholders, and referring to ISPA tools, an inventory (coverage, financing and architecture), an analysis of the performance and gaps of contributory and non-contributory social protection programmes and measures and assess the adequacy of internal or external financing to meet the social protection. | ILO UNICEF SP-CNPS | bar: 2022 Apr to 2022 Jul
| 1.1.4 Provide technical support to the SP-CNPS for the development of recommendations and reforms to support the coordinated and effective implementation of the PNPS, within the framework of a participatory and inclusive national dialogue. | ILO UNICEF | [18 empty] | 4 national dialogue sessions | bar: 2022 Jul; 2022 Sep; 2022 Nov
1.1.5 Support the SP-CNPS for the integration of reforms in updating PNPS and the drafting of a progressive implementation strategy
Output 1.2 : Burkina Faso has a sustainable and adequate financing strategy of its national system of social protection | 1.2.1 Conduct a social protection expenditures review, including external financing. This review will take in consideration aspects related to gender, children, young people, people with disabilities as well as the impact of shocks on vulnerable populations | [18 empty] | Social protection expenditure review (UNICEF)
| 1.2.2 Assess the costs of the guaranties of a national social protection floor and recommendations for strengthening the social protection system emanating from the review of the system | [19 empty] | 1 costing (RAP) of recommendations
| 1.2.3 Identify opportunities for mobilising sustainable resources within the available budgetary space | [18 empty] | Financing strategy (UNICEF) | 1 document analysing medium- and long-term funding sources
| 1.2.4 Provide technical and methodological support to the SP-CNPS and the Ministry of Finance in adopting options for sustainable financing in the national social protection system | [20 empty] | A medium-term financing framework document for the social protection sectore
| 1.2.5 Implement training activities to reinforce capacities of government institutions and technical ministries, social partners and other actors on social protection (ILO and UNICEF guides and methodologies) in order to take informed decisions regarding the social protection budget | [19 empty] | 1 capacity building workshop
| 1.2.6 Prepare the argument and to undertake advocacy actions for increased social protection public financing | [20 empty] | 1 capitalisation document
Outcome 2 | To support institutional and technical actors in the implementation of universal health coverage and strengthening of local mechanisms for the extension of social protection schemes and programmes at the municipal level, adapted in particular to the needs of persons in situations of temporary and lasting vulnerability and fragility, including displaced persons
Output | List of activities |  | 2022 Janv: 2022; 2023 Jan: 2023 | Annual target/s
|  | Responsible | Janv | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Year 1 (Oct 2019-Dec 2020) | Year 2 (Jan 2021-Dec 2021) | Year 3 (Jan 2022-May 2023)
Output 2.1 Renforcement des capacités des acteurs institutionnels et techniques et des outils de suivi du système national de protection sociale | 2.1.1 Carry out a mapping of the social protection statistical system (sources of production, collection and analysis of information) | [18 empty] | Study indicator SMART PNPS UNICEF SP/CNPS | 1 mapping of data sources
| 2.1.2 Provide technical support to the development of a framework for monitoring and evaluating progress in the social protection sector (ILO SSI, social insurance performance indicators, and SDG indicators) | ILO | [18 empty] | ILO SSI (Social Security Inquiry) | bar: 2022 May to 2022 Jun
| 2.1.3 Strengthen stakeholders' capacities to monitor and evaluate social protection programmes, taking into account gender aspects and non-discrimination of people living with disabilities | ILO | [18 empty] | 1 capacity building workshop | bar: 2022 Jul
Output 2.2 Strengthened technical capacities of the schemes to ensure the quality and sustainability of minimum guarantees of social protection | 2.2.1 Provide technical assistance to the CNAMU, the mutualist movement and social partners for the effective implementation of the RAMU and its extension to the formal and informal sectors and to the rural sector | ILO | [19 empty] | 1 strategy for the implementation and expansion of the RAMU | bar: 2022 Janv to 2022 Nov
| (New proposed activity) Provide support to Government and social partners for extending social protection to the informal economy workers. | ILO | bar: 2022 Jun to 2023 May
| 2.2.2 In pilot communes, design and test mechanisms for counselling beneficiaries, channelling central programmes to the local level, collecting data, targeting and registering vulnerable populations in the communal social services | UNICEF | [19 empty] | 15 pilot municipalities have targeting mechanisms | bar: 2022 Apr to 2023 Mar
| 2.2.3 Provide technical support to the harmonization and strengthening of targeting mechanisms for poor and vulnerable households | UNICEF | [19 empty] | 15 pilot municipalities have targeting mechanisms | bar: 2022 Apr to 2023 Mar
| 2.2.4 Capitalize on these pilot experiences in order to integrate and scale up good practices in the revision of the PNPS in 2022 | [20 empty] | 1 capitalisation document
Outcome 3 | Shock-responsive programmes, tailored to the needs of people in situations of vulnerability, fragility and insecurity, including displaced persons, are integrated into the national social protection system, in coherence and synergy with social insurance schemes, and social assistance and social safety net programmes
Output | List of activities |  | 2022 Janv: 2022; 2023 Jan: 2022 | Annual target/s
|  | Responsible | Janv | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Year 1 (Oct 2019-Dec 2020) | Year 2 (Jan 2021-Dec 2021) | Year 3 (Jan 2022-May 2023)
Output 3.1 Strengthened capacities of mechanisms and programmes to ensure the construction of a social protection system that can also meet social protection needs in the context of crisis and fragility in Burkina Faso | 3.1.1 Support consultation between social protection actors and those of the humanitarian country team and humanitarian clusters to strengthen the coherence of humanitarian responses with social protection programmes, and propose steps for their integration into the social protection system | ILO UNICEF | [19 empty] | A national approach nexus humanitarian development | bar: 2022 Mar to 2022 Dec
| 3.1.2 Provide technical support, where possible, to the identification, registration and integration of beneficiaries of humanitarian responses and displaced people in the single social registry, the communal social services and the universal health scheme | [20 empty] | 1 system for registering and caring for shock victims | bar: 2022 Apr to 2022 Apr
| 3.1.3 Provide technical support to the integration of data (on coverage, benefits, financing, etc.) of humanitarian responses into the national social protection information system | [20 empty] | Integration of humanitarian responses into the data compilation tool | bar: 2022 Ago to 2022 Apr
| 3.1.4 Document good practices in linking social protection and humanitarian responsesDocumenter les bonnes pratiques du lien entre protection sociale et réponses humanitaires | ILO | [19 empty] | 1 document capitalizing on good practices | bar: 2022 Jan to 2022 Mar

## Cambodia 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Cambodia
Outcome 1 | Improved design and monitoring of SP programs and increased use of evidence on SP impact system contributes to increased coverage of social protection
Output | List of activities | 2022 |  |  |  | 2023 |  | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | 2022
Output 1.1. Evidence-based frameworks and tools to guide, monitor and evaluate the implementation of the National Social Protection Policy Framework are developed and implemented | 1.1.1 Technical assistance to selected budget entities in implementing NSPC M&E Framework and linking programme M&E frameworks with RB budgeting. | [6 empty] | UNICEF, (ILO) | GS-NSPC; MEF | - Actuarial Valuation for 3 branches of NSSF finalized - At least a policy revision initiated based on the actuarial revision recommendations
| 1.1.2 - Provide technical assistance and financial support to implement a gender-sensitive analysis of the financial situation (actuarial review) of the NSSF Schemes (actuarial review) | X | X | X | X | X | X | ILO (OXFAM) | NSSF, GS-NSPC
| 1.1.3 - Develop research on the potential role of expanded Social Protection for Cambodia Socio-economic development | X | [5 empty] | ILO (OXFAM) | GS-NSPC
Output 1.2 –Feasibility studies and tools for expansion of the social protection schemes are developed | 1.2.1 Technical assistance to design and development of gender- and -child -sensitive integrated / family package of social assistance programmes (cash transfer for pregnant women and children, cash scholarships, disability allowance, and social pension for elderly) and administrative models /institutional arrangements for their delivery | X | X | X | X | X | X | UNICEF, (ILO, OXFAM) | GS-NSPC, MOSVY | 50 Districts with PwD163,181 identification system All provinces have trained staff to support identification of PwD Revised Disability Allowance Sub-decree Costed Disability Allowance Programme
| 1.2.2 Technical assistance and financial support to strengthen the delivery of the disability allowance programme (identification, data collection and costing) | X | X | X | X | X | X | UNICEF | MOSVY
Output 1.3. The CSO-Trade Union Network can engage effectively with decision makers for improvement of the design and monitoring of selected SP programs | 1.3.1 Capacity strengthening of the CSO-TU Network on gender-sensitive and results-based budgeting, design and monitoring of selected SP programmes. | x | [5 empty] | OXFAM | CSO-TU Network | 5 Common recommendations produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 recommendations produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF
| 1.3.2 Impact and needs analysis at the level of constituents of the CSO-TU Network regarding selected SP programs, including development of recommendations for improvement of budgeting, design and monitoring. | x | x |  |  |  |  | OXFAM | CSO-TU Network
| 1.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for improvement of budgeting, design and monitoring of selected SP programs. | x | x | x | x | x | x | OXFAM (ILO) | CSO-TU Network
| 1.3.4 Extract learning from the CSO-TU engagement on selected SP programs and share with relevant stakeholders, including GCSPF . | x | x |  |  |  |  | OXFAM | CSO-TU Network, GCSPF
Outcome 2 | Social Protection institutions enhance their planning, budgeting and M&E capacities in alignment with the Public Finance Management Reform Programme
Output | List of activities | 2022 |  |  |  | 2023 |  | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | 2022
Output 2.1 -Tools and Knowledge in place for improved planning, budgeting and tracking of social protection expenditures including a consistent mechanism for compilation of revenues and expenditures | 2.1.1 – Technical assistance to review implementation of the functional classification of social protection schemes by selected ministries implementing SP programmes | X | X |  |  |  |  | ILO (UNICEF) | GS-NSPC; MEF | - financial review of the SP in Cambodia finalized including a list of social protection programs, coverage and costs - recommendations produced under the SP Financial Review incorporated into the revised SP Policy Framework revised Action Plan
| 2.1.2 – Technical assistance to develop social protection tracking expenditure database for MoSVY-supported social assistance programmes | X | X | X | X | X | X | UNICEF | GS-NSPC, MOSVY
| 2.1.3 Provide technical assistance and support to building the capacities of the selected line ministries and institutions responsible for social assistance to develop adequate/high-quality results-based frameworks in support of programme-based budget formulation, execution and reporting | X | X | X | X | X | X | UNICEF (ILO, OXFAM) | GS-NSPC, MEF, MOSVY
| 2.1.4 – Technical assistance to implement a comprehensive gender-sensitive Financial Review of Social Protection in Cambodia as input to MTR of SPPF | X | X |  |  |  |  | ILO (UNICEF) (OXFAM) | GS-NSPC
Output 2.2 – Social budget forecasting system established | 2.2.1 - Provide capacity building (training and coaching) on social budgeting forecasting model to MEF departments | [6 empty] | ILO | GS-NSPC; MEF | - social budgeting model incorporated within MEF planning tools
| 2.2.2 Provide technical assistance and jointly develop tools to develop gender-sensitive social budgeting forecasting model for Cambodia | X | X |  |  |  |  | ILO | GS-NSPC; MEF
Output 2.3 – The CSO-TU Network can engage effec-tively with decision makers for more fiscal space to increase the coverage of the informal economy workers under the NSPPF, especially women workers | 2.3.1 Capacity strengthening of the CSO-TU Network on overall PFM and financing of SP systems, including GRB | x | [5 empty] | OXFAM (ILO) | CSO-TU Network | 5 of common recommendations for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF
| 2.3.2 Needs and contributory capacity assessment of constituents of the CSO-TU Network, in particular of female informal economy workers, including development of recommendations for increased coverage | x | x |  |  |  |  | OXFAM | CSO-TU Network
| 2.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased fiscal space for better coverage of informal economy workers, women in particular. | x | x | x | x | x | x | OXFAM, (ILO) | CSO-TU Network
| 2.3.4 Extract learning and lessons from the CSO-TU engagement on increasing the coverage for informal economy workers and share with relevant stakeholders, including GCSPF |  | x |  |  |  |  | OXFAM | CSO-TU Network, GCSPF
Outcome 3 | Service providers at sub-national level (SNAs) are better able to implement social protection services
Output | List of activities | 2022 |  |  |  | 2023 |  | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | 2022
Output 3.1- Service providers have improved skills to deliver social protection services | 3.1.1 Technical assistance to develop training curriculum for sub-national administrations (SNAs) on social protection, with focus on disability allowance | [6 empty] | UNICEF (OXFAM) | MOSVY
| 3.1.2 Provide financial support for implementation of a child and gender-sensitive training program on social assistance for national and subnational government officials (Focus on Provincial/Capital levels) | [6 empty] | UNICEF, (ILO, OXFAM) | MOSVY
| 3.1.3 Technical assistance to assess existing knowledge sharing and information dissemination channels and develop strategies for capacity building of SNAs | X | [5 empty] | UNICEF, (ILO, OXFAM) | MOSVY,MOI
| 3.1.4 Research (Assessment) of roles and existing mechanism at SNA level in implementing SA programmes | X | [5 empty] | UNICEF (OXFAM) | MOSVY
Output 3.2 - Increased capacity and engagement of the CSO-TU Network to engage in social accountability mechanisms related to SP delivery at subnational level | 3.2.1 Capacity strengthening of of the CSO-TU Network on the social accountability framework and how this applies to SP delivery at subnational level. | x | [5 empty] | OXFAM | CSO-TU Network | 3 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 3 of common recommendations on gender sensitive social accountability mechanisms accepted.
| 3.2.2 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased social accountability in SP delivery at subnational level | x | x |  |  |  |  | Oxfam | CSO-TU Network
| 3.2.3 Awareness building amongst constituents regarding social accountability mechanisms they can make use of. | x | x | x | x | x | x | OXFAM | CSO-TU Network
| 3.2.4 Extract learning from the CSO-TU engagement on the use of social accountability mechanisms within SP delivery. |  | x |  |  |  |  | OXFAM | CSO-TU Network, GCSPF

## Ethiopia 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Ethiopia
ILO/UNICEF Joint Work Plan: 2020-2023
Outcome 1 | Improving the social protection system for Ethiopia through a sustainable financing strategy
Output | List of activities | 2022 |  |  |  | 2023 |  | PUNO/s involved | Implementing partner/s involved
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | Year 3 (Jan 2022-May 2023)
Output 1 Financing Strategy for Social Protection in Ethiopia | 1.1. Building an evidence base for financing non-contributory social protection programmes (such as vulnerability analysis on COVID-19, an investment case for social protection and fiscal space analysis) | X | X | X | X | X |  | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | - Final fiscal space analysis and investment case documents are completed
| 1.2. Technical/Expertise contribution to actuarial valuation (contributory) | X | X | X | X |  |  | ILO (lead), UNICEF | POESSA, PSSA | - final Actuarial evaluation document submitted to PSSA and POESSA
| 1.3. Financing strategy (including the research component, policy paper, consultations and validation) | X | X | X | X | X | X | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | - Final financing strategy produced
| 1.4. Awareness raising, workshops, and policy advocacy related to financing social protection | X | X | X | X | X | X | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | - 1 knowledge exchange forum - - 1 national conference on PFM &SP conducted
Output 2 Extending social security to informal economy workers and supporting labour legislation related to social protection | 2.1 Technical assessment to extend social security to informal sector workers including COVID-19 social protection responses | X | X | X | X | X | X | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA | - Final version of the analytical study on extending SP to informal economy workers submitted
| 2. 2. Awareness raising through media and/or workshops (Federal/Regional) for consensus building on the extension of social security to informal economy workers including COVID-19 social protection responsive programmes |  | X |  | X | X |  | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA | - 1 awareness raising training/workshops organised at Federal and Regional levels on extension of SP to informal economy workers.
| 2.3 Tripartite consultation among government, workers’ and employers’ representatives on minimum wage and related social protection schemes | X | X |  | X | X | X | ILO (lead), UNICEF | MoLSA, CETU, EEC | - 3rd and 4th round of tripartite consultations done with tripartite partners and the wage board aiming at drafting the minimum wage legislation.
Output 3. Building the capacity of MoLSA to effectively monitor the social protection system. | 3.1 Support MoLSA and Addis Ababa BoLSA develop monitoring tools and processes to better implement and track social protection programming. | X | X | X | X | X | X | UNICEF (lead), ILO | MoLSA, Addis Ababa BoLSA
| 3.2 Increasing the capacity of MoLSA to facilitate the establishment of effective coordination mechanisms for social protection policy and strategy | X | X | X | X | X | X | UNICEF, ILO | MoLSA, BoLSAs, MoA, FUJCFSA, | Social protection platform(s) fully functional under MoLSA/BoLSA(s) management 'Gap analysis conducted to revise the National Social Protection Policy/Strategy (NSPP).
| 3.3 Developing a knowledge management platform for inclusive social protection | X | X | X | X | X | X | ILO, UNICEF | MoLSA, Consultant | MoLSA/BoLSA(s) fully capacitated on use of knowledge management tools/platform

## Nepal 2022-23 to be validated
GLO/19/53/EUR - SC 190731 |  | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Nepal
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output | Annual target/s |  | List of activities | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| 2022 | 2023 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT 1 : Increased capacity of GON and key stakeholders to develop resilient, inclusive national social protection policies, sustainable financing strategies and legal frameworks at Federal and Provincial levels. | 1. Action Plan to implement the National policies in place | 1. Action plan implemended | A1.1 Technical assistance to NPC to develop SP policy, including ensuring adequate and sustainable financing for social protection through an inclusive consultations and informed participation of stakeholders . 2. Report on the overall coverage and adequacy of SP system, in line with the World Social Protection Report 2020-22 | [7 empty] | UNICEF, ILO, Social Protection Task Team (SPTT) members | NPC, Academicians, key SP institutes, CSOs, Wos, Eos
| 2. Integrated M & E framework endorsed by the key stakeholders |  | 1) Desk review of relevant documents and drafting of a integrated policy framework (UNICEF); 2)Interministerial consultations on the zero draft ( UNICEF) 3)Consultatons with ILO constituents and compilations of inputs on the draft policy framework (ILO) 4) Consultations with civil society org and copilation of inputs (WSM) 5. Finalisation of draft policy framework (UNICEF) 6. Support to NPC in the process of Government's approval of the Policy
| 3. Draft Policy document endorsed by key stakeholders in P2 & P6 |  | .A1.2.Technical assistance to two Provincial Governments ( P6, P2) to formulate inclusive Provincial Social Protection Policy , regularly monitor the implementation of the policy agenda and backstop Municipalities in improving their SP services through effective monitoring and feedback. | [7 empty] | UNICEF, ILO | Local Government ( P2, P6 & selected Municipalities) & IT serice providers, Academicians
| 4. Provincial level M & E framework endorsed by key stakeholders in P2 and P6 |  | 1) SP context analysis in 2 Provinces (ILO) 2) Training to stakeholders for informed policy making (ILO) 3) Consultations for policy formulation (ILO/UNICEF) 4) Writing of policy document(UNICEF) 5) Sharing workshop on lessons learned with other 5 Provinces
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output |  |  | List of activities | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| 2022 | 2023 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT: 2 Government enabled to establish and operationalise a high-level social protection coordination, monitoring and evaluation mechanism at Federal level. | 1. Institutional framework for federal level coordination and monitoring of SP systems agreed by stakeholders. 2. TA to NPC designed, agreed from the relevant government and implemented to operationalise the Institutional mechanism of coordination. | TA implemented | A2.1Technical support to an appropriate Government Agency to establish and operationalise the institutional framework 1) A review of current institutional framework and gap analysis 2) Policy dialogue with parliamentarians and key government agencies on the need of a institutional framework 3) Sharing of international practices 4)TA to the NPC to recommend the institutional framework,including modus operandi, resource requirements, necessary legal and technical tools, including a M and E framework for the establishment and operationalisation of the coordination mechanism (UNICEF/ILO). | [7 empty] | UNICEF, ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos
3. Regulations drafted for the establishment and operationalisation of the institutional framework
RESULT 3 Increased capacity of Federal and Provincial Governments to plan, budget, implement and monitor extension of contribution –based social protection systems and programmes, overcoming the challenges such as informality, while ensuring financial sustainability of the contributory system. | 3. Relevant Government Officials trained on SP financing | Actuarial valuations of 4 schemes | A 3.1. Technical support to build government's capacity on sustainable SP financing and through effective and innovative communication ensure the generated knowledge and results have a meaningful impact in SP financing. 1) Actuarial valuations of 4 contributory schemes to be implemented by SSF 2) Orientation to Social Security Fund Board members to understand the actuarial valuations 3. Redesign the schemes based on Actuarial recommendations 3) Study on the contributory capacity of informal economy workers 4)Assessment of public care services expenditure, cost and financial space and recommendations to improve the care services. 5)estimate the potential fiscal space that could be created assuming a potential increase in social security (contribution-based) coverage or contribution rates or both 6) Design and use communication products to disseminate the knowledge generated and to ensure recommendations are used in policy/programme making 6) Training to relevant government officials on social protection financing 7) Support design of schemes for the informal sector including support to tripartite consultations 8) Support in the first phase implementation of social security schemes to the informal sector 9) Strenghten communications and outreach strategy for the SSF and support in the implementation of communications and outreach plan | [7 empty] | ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos
| 4. Financing options studied and discussed at Federal and Provincial levels targeting selected informal sectors. | [9 empty] | ILO
| Capacity development plan implemented in collaboration with various DPS | Capacity development plan implemented in collaboration with various DPS | A 3.2 Technical Assistance to the SSF for the systems (general administration and HR management, registration, eligibility verification, collection of contributions, case management and distribution of benefits, complaints and appeals mechanisms, and monitoring, evaluation and reporting) improvement and effective implementation of the systems ( ILO) | [8 empty] | SSF, NPC, Workers, Employers
| TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | 1) Internal review of the systems and recommendations on areas for improvement 1) Agree on the specif priority areas for improvement and provide technical support for improvement 2) Provide support of IT expert, especially to strengthen the data security and large data handling capacity 3) technical support to SSF establish and operationalise an appeal and grievance handling system 4) Assess the technical capacity gap among the SSF team, determine the learning methods and design a learning plan 5) Plan and organise training programmes 6) Study visit for SSF board members and key SSF Officials to learn from successful experience in the Region 7) Technical support on financial and internal control mechanism | [7 empty] | ILO
RESULT 4 Increased capacity of Federal and Local Governments to revise policies, set standards, oversee, monitor and report the social assistance programmes and to identify options to create fiscal space. | 1. Support DoNIDCR to produce "Analytical Annual Report" knowledge product on Social Production ( SSA) 2. Endline Survery of Coverage of SSA completed |  | 4.1 Generate evidences, policy advocacy and develop/improve necessary tools to improve policies and strengthen quality service delivery, with special attention to the child grant and PWDs. 1. Costing and financing gaps analysis of target 1.3 of SDG (child grant, disability, and old age) 2. Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant (schemes with high exclusion errors) 3. Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) | [7 empty] | UNICEF, NPC, ILO, DONIDCR, NGOs | Research organiazations, Federal government, province and local government
| 3. Strengthened complaints and appeal mechanism, the grievance redressal mechanism (GRM) 4. Learning and study visit on shock responsive social protection |  | 4.2 Support capacity development of Provincial and Local Government in effective Implementation of SSA, (registration, timely delivery monitoring, evaluation and reporting). 1. Training Workshop involving Province and Selected Local Government 2. SMS based technology (RapidPro) for real time monitoring of implementation of social protection and other social services in Provinces 2 and 6 (UNICEF). 3. Learning and study visit on shock responsive social protection 4. Improve complaints and appeal mechanism, the grievance redressal mechanism (GRM) . 5. Support to Province 2 and 6 to develop, test and refine improved processes for the assessment of PWD(UNICEF) | [7 empty] | UNICEF, NPC, DONIDCR, NGOs | Research organiazations, Federal government, province and local government
| 5. Strengthen "Case management" system to include excluded eligible beneficiaries into Social Protection system |  | Technical support to DoNIDCR/NPC to generate evidence, policy advocacy and develop/improve necessary tools to improve policies and procedures for delivering social protection services with special attention to the child grant and PWDs. i.Support the DoNIDCR to conduct a review of MIS system, registration process, grievance handling, payment systems,agree on the actions technical support for improvement including revision of SSA- Guidelines. ii.Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant agree on reforms to simplify and improve the processes, update SSA guidance, and provide iii.Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) iv.Support DoNIDCR to produce an "Analytical Annual Report" knowledge product on Social Protection Social Assistance) v.Strengthen social protection system preparedness and response to disaster and emergencies. vi.Develop and implement communication awareness strategy
6. Monitoring report on timely payment produced.
RESULT 5 Enhanced accountability mechanism at local government level in Province 2 and 6 | 1. Functional Grievance handling Committee |  | Strengthen accountability systems (Programme awareness, registration, eligibility verification, grievance handling, monitoring timely fund flow, payment, and reporting focusing on the child and disability grant). i.Review accountability mechanism of SSAs ii. Strengthen local level Grievance handling mechanism (Publicize list of eligible beneficiaries, simplify complain procedure and improve case management or facilitating eligible but excluded people facilitate to obtain required legal documents) iii. Training Workshop on social protection to Province and selected Local Governments iv.Learning and study visit on shock responsive social protection v. Support ongoing process of pre-identify and register disaster vulnerable HHs and link them with payment structure in additional municipalities vi.Strengthen Local Government capacity to build awareness, identify beneficiaries, organize public audits on social protection. vii. Technical assistance to province-led gender-focused social protection initiatives (i.e. Beti Bachao Beti Padhao programme in Province 2) to reduce gender inequality through social protection. | [7 empty] | UNICEF
RESULT 6 Nepali Civil Society Organisations and Trade Unions are meaningfully and structurally involved in the development, implementation and monitoring of policy processes regarding social protection and public finance management due to improved coordination and enhanced capacities | Local government more accountable/ functioning |  | i.Work with DoNIDCR to translate and share revised policy documents, procedure, analytical findings, monitoring reports, with the local government to inform programme performance and its challenges. ii. Ensure citizens' participation in monitoring access to social protection and facilitate eligible individuals or HHS to access social protection. iii. Ensure timely payment as specified in the operational guidelines "2 weeks window" in every trimester by strengthening monitoring process. iv. Collaborate with CSOs to monitor and implement social protection mobilizing a consistent community monitoring approach to track social protection service delivery in focus provinces. | [7 empty] | ILO WSM,UNICEF | Civil society networks, Community groups , l;ocal government
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check with UNICEF colleague as they are the lead on this.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UNICEF

## Paraguay 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Paraguay
Impact
|  | 2022 |  |  |  | 2023 | Metas Anuales
Results | Activities | Q1 | Q2 | Q3 | Q4 | Q1 | 2022 | Productos | Status | Observaciones al 07 de marzo de 2022.
1. Se identifican las oportunidades para el espacio fiscal y el aumento de la eficacia y eficiencia de las finanzas públicas del SPS. | 1.1 Desarrollar un diagnóstico de la eficiencia presupuestaria y el espacio fiscal del SPS para financiar su expansión | [6 empty] | Producto 1: Informe de avance. | Completado | Observaciones generales: Se realizará una revisión de los TDRs para la actualización de actividades y culminar el estudio durante el primer semestre de 2022. Acuerdos de la reunión de revisión 7 de marzo de 2022: Revisión de los tiempos de forma conjunta con la Consultora para acomodar los tiempos a la disponibilidad de las instituciones.
[8 empty] | Producto 2: Informe de Antecedentes e Inventario de esquemas e indicadores de Protección Social a partir del documento de configuración del SPS Vamos, aprobado por el Gabinete Social. Producto 3: Revisión de indicadores y formulación de nuevos cuando sea necesario. | Parcialmente completado: Revisión 2022
[8 empty] | Producto 4: Estimación de costos y brechas de financiamiento | Completado
[8 empty] | Producto 5: Análisis y cuantificación de opciones de espacio fiscal | En proceso: Revisión 2022
[8 empty] | Producto 6: Informe consolidado y Prdocuto 7: Difusión del conocimiento | No iniciado: Revisión 2022
| 1.2 Proporcionar evidencia científica sobre los beneficios económicos y sociales de invertir en protección social | [6 empty] | Producto único: Base de datos para estudio internacional VAR | Completado: en revisión a nivel de sede en Ginebra. | Observaciones generales: Producto Entregado. Este producto sirve de insumo para el estudio liderado por la Universidad de San Pablo y administrado centralmente por la OIT.
[8 empty] | Producto 1: Informe de avance | Completado | Observaciones generales: Prodcuto terminado. Se realizará una revisión final del documento para su publicación y difusión. Acuerdos de la reunión de revisión 7 de marzo de 2022: Se pasa a la etapa de revisión final y edición para publicación.
[8 empty] | Producto 2: Informe final y Producto 3: Difusión | Completado
[8 empty] | Producto 1: Esquema anotado y propuesta metodológica | Completado | Observaciones Generales: Se realizará la edición final (versión resumida) para su publicación durante el primer semestre del 2022. Acuerdos de la reunión de revisión 7 de marzo de 2022: OIT y la consultora para avanzarán con la edición del documento.
[8 empty] | Producto 2: Informe preliminar | Completado
[8 empty] | Producto 3: Informe final y productos relacionados | Completado
[8 empty] | Producto 4: Difusión del conocimiento | Completado
[8 empty] | TBD | En proceso: Revisión 2022 | Observaciones Generales: Se planea una serie de workshops durante el 2022 para difundir los estudios durante el segundo semestre de 2022. Actividad complementaria con el Resultado 3 (Workshops). Acuerdos de la reunión de revisión 7 de marzo de 2022: OIT preparará una propuesta y compartirá con MH y UTGS para seguir la planificación para el segundo semestre 2022. UTGS sugiere tener en cuenta la planificación durante la Semanda de Protección Social 2022 a realizarse en setiembre 2022.
2. Primera fase del SPS ¡Vamos! en territorios seleccionados implementados. | 2.1. Identificación y registro de beneficiarios de SPS en 4 distritos seleccionados. | [6 empty] | TBD | En proceso | Observaciones Generales: Esta actividad sigue vigente. El llamado ya ser realizó y está en proceso de selección. Se realizará en Villeta. La meta es contar con el informe para cerrar en agosto. Acuerdos de la reunión de revisión 7 de marzo de 2022:
| 2.2.Desarrollar una hoja de ruta de servicios dirigidos a niños de edades comprendidas entre 0 y 4 años en 4 distritos locales. | [6 empty] | Producto 1: Minuta de reuniones (Actividad 1). Metodología y plan de trabajo aprobado (Actividad 1). | Completado | La consultoría ha finalizado y el producto se ha desarrollado. Se espera el lanzamiento para el segundo semestre de 2022 en conjunto con otros productos que la UTGS quiere lanzar.
[8 empty] | Producto 2: Minuta de reuniones. Proyecto de aplicación móvil, resultante de fase de diseño (Actividad 2). | Completado
[8 empty] | Producto 3: Validación de UTGS y UNICEF de diseño de aplicación móvil (Actividad 3). Minutas de reuniones. | Completado
[8 empty] | Producto 4: Prototipo de aplicación en base a diseño de aplicación móvil (Actividad 4). Minutas de reuniones. | Completado
[8 empty] | Producto 5: Informes quincenales de avances. Aplicación funcionando, en tiempo y forma (Actividad 5). Minutas de reuniones. | Completado
[8 empty] | Producto 6: Manuales para a) para administrador b) usuarios diseñados. Informe Final de la consultoría y código fuente (Actividad 5). | Completado
| 2.3. Establecer mecanismos de coordinación subnacionales de todos los sectores involucrados en la implementación en los 4 distritos seleccionados. | [6 empty] | Primer producto • Plan de trabajo • Informe de Avance Productos mensuales • Informes de Avance, que reportará las gestiones realizadas conforme al Plan de Trabajo, declarando las restricciones encontradas durante el periodo reportado y anexando los entregables que el profesional haya desarrollado en el marco del cumplimiento de sus tareas. | En proceso | Observaciones Generales: Los contratos con las consultoras finalizan el 30 de diciembre y serán renovados por 11.5 meses más. Se realizarán mínimos ajustes a TDR. Acuerdos de la reunión de revisión 7 de marzo de 2022: Los contratos fueron renovados y están vigentes hasta el 30 de diciembre del 2022.
| 2.4 Capacitación de capacidades de recursos humanos a nivel local para planificar y monitorear la prestación de servicios a niños de 0 a 4 años. | [6 empty] | TBD |  | Observaciones Generales: Acuerdos de la reunión de revisión 7 de marzo de 2022: Se revisará el TDR ya elaborado, se iniciará el proceso de llamado a consultoría, selección e implementación. Se espera finalizar la actividad para el mes de septiembre del año en curso.
| 2.5 Elaboración de los manuales de implementación del SPS ¡Vamos! a nivel local, con herramientas y / o instrumentos relacionados | [5 empty] | Manual (es) de implementación del SPS ¡Vamos! a nivel local, con herramientas y / o instrumentos relacionados elaborados | TBD | A definir tiempo de ejecución | Acuerdos de la reunión de revisión 7 de marzo de 2022: Se considera pertinente ejecutar la actividad durante el año 2022. Se constuirán los TDRs para contratación.
| 2.6. Evaluación de la implementación del SPS vamos en distritos seleccionados con recomendaciones para ampliar | [5 empty] | Implementación del SPS vamos en distritos seleccionados con recomendaciones de escalamiento evaluadas. | TBD | A definir tiempo de ejecución | Acuerdos de la reunión de revisión 7 de marzo de 2022: Se considera pertinente ejecutar la actividad durante el año 2022.
3. Fortalecimiento de la capacidad de los profesionales del servicio público y las organizaciones de la sociedad civil para monitorear y evaluar los programas de protección social en el contexto de un presupuesto basado en resultados. | 3.1 Programa de desarrollo de habilidades diseñado para profesionales del servicio público y miembros de la sociedad civil sobre sistemas de protección social con enfoque de ciclo de vida y presupuestos basados ​​en resultados | [6 empty] | Producto 1: Malla curricular. | Completado | Observaciones generales: Etapa culminada
[8 empty] | Producto 2: Contenidos de la malla curricular y estrategia pedagógica | Completado
[8 empty] | Producto 3: Estrategia de convocatoria | Completado
[8 empty] | Material Pedagógico | Completado | Observaciones generales: Diplomado a Iniciar en marzo y finalizar en setiembre de 2022. Acuerdos de la reunión de revisión 7 de marzo de 2022: Se avanza con el diplomado según el plan.
[8 empty] | Ejecución de Diplomado | En proceso
| 3.2 Fortalecimiento de la capacidad en la Dirección General de Presupuestos para el monitoreo y evaluación de los programas de protección social en el contexto de la presupuestación basada en resultados con un enfoque en los programas incluidos en el SPS ¡Vamos! | [5 empty] | Se proporcionan herramientas sobre la evaluación y el seguimiento de los programas de protección social en el contexto de la presupuestación basada en resultados. 1 (uno) Taller para el personal de la Dirección General de Presupuestos sobre el uso de herramientas de evaluación y monitoreo para programas de protección social en el contexto de la elaboración de presupuestos basados ​​en resultados. | TBD | No iniciado: Revisión 2022 | Observaciones generales: Verificar la relevancia de esta actividad y tener en cuenta el tiempo de las personas (muchas participando del diplomado). Acuerdos de la reunión de revisión 7 de marzo de 2022: Pendiente de conversación con la DGP.
| 3.3 Desarrollo de habilidades para profesionales del servicio público y miembros de la sociedad civil sobre financiamiento público para protección social | [5 empty] | 3 (tres) Participantes en el curso "Finanzas públicas para analistas de protección social". | Culminado | Completado | Observaciones generales: Participantes 2020: MH: María Cristina Pereira Cáceres, Katherine Raquel Soledad Viveros Medina y Daysy Fabiola Gaona Benítez. UTGS: María Patricia Martínez Cartillo y Nathalia María Giménez. OIT: Verónica Herken y Andrea Ocampos.
[8 empty] | Producto 1: Adaptación | Completado | Observaciones generales: Actividad culminada con éxito.
[8 empty] | Producto 2: Curso | Completado
[8 empty] | Participación en curso en su versión en Inglés. | Completado | Observaciones generales: Participantes 2021: MH: José Acuña. UTGS: María José Mendez. OIT: Verónica Herken.
[8 empty] | Producto 1: Adaptación | No iniciado: Revisión 2022 | Observaciones generales: Se realizará una nueva reunión con ITC-ILO para verificar los siguientes pasos y la viabilidad de esta actividad. De realizarse, será durante el primer semestre de 2023 (febrero a abril como tope). Acuerdos de la reunión de revisión 7 de marzo de 2022: Se verificará con ITC-ILO si la actividad se puede realizar durante el 2023.
[8 empty] | Producto 2: Curso | No iniciado: Revisión 2022
[8 empty] | TBD | No iniciado: Revisión 2022 | Observaciones generales: Propuesta de actividad basa en materiales que se están produciendo, ligada también al producto Resultado 1 de difusión de los estudios a realizarse durante el segundo semestre de 2022. Acuerdos de la reunión de revisión 7 marzo de 2022: Actividad ligada al Resultado 1 de difusión de productos. UTGS recomienda involucrar a otras Agencias y también ligar esta actividad con la Semana de la Protección Social. OIT preparará una propuesta para construirla conjuntamente con la UGTS y el MH.
4. Conocimiento, propiedad y demanda de SPS ¡Vamos! dentro de las instituciones públicas, los proveedores de servicios y los beneficiarios aumentaron. | 4.1 Diseño de una estrategia de comunicación general para el SPS ¡Vamos! | [6 empty] | Producto 1: Documento de planteamiento metodológico para realizar el diseño de la estrategia de comunicación, que incluya: # Plan de trabajo y cronograma # Propuesta metodológica para el diseño de la Estrategia de Comunicación. # Identificación de roles involucrados | Completado | Finalizado
[8 empty] | Producto 2. Documento de diagnóstico comunicacional y levantamiento de información en la UTGS, así como de los talleres con comunicadores de instituciones aliadas, que incluya: # Resultado de revisión documental del SPS y materiales de comunicación. Experiencia internacional de estrategias de comunicación en la instalación de Sistemas de Protección Social. # Resultado de talleres impartidos en la UTGS y con instituciones aliadas. # Estudio de percepción desarrollado en localidades donde se llevará a cabo la primera etapa. (la implementación del estudio de percepción no forma parte de esta consultoría) # Primera estructura de Documento de Estrategia de Comunicación; que incluya el marco de referencia, la introducción los objetivos, públicos meta y acciones. | Completado
[8 empty] | Producto 3. Segunda entrega de Documento de Estrategia de Comunicación; que detalle los objetivos, públicos meta, el conjunto de acciones, productos, plazos, responsables (incluyendo equipo humano). # Documento que describa las principales líneas de contenido identificadas, el medio de documentación, desarrollo de la línea editorial y su bajada discursiva para voceros (debe formar parte de la estrategia). | Completado
[8 empty] | Producto 4. Tercera entrega de Documento de Estrategia de Comunicación; que incorpore ajustes recibidos de la UTGS/UGPR. Incluir el proceso de transición entre Gobiernos, de tal forma a generar condiciones para trascender a una Política de Estado. # Documento de branding y desarrollo de imagen gráfica del SPS con su manual de uso y aplicación. | Completado
[8 empty] | Producto 5. Documento de Estrategia de Comunicación; que detalle los objetivos, públicos meta, el conjunto de acciones, productos, plazos, responsables y recursos requeridos final. | Completado
[8 empty] | Producto 6. Informe final conteniendo todos los productos especificados para esta consultoría y su protocolo de uso. | Completado
[8 empty] | Producto 1: Plan de trabajo. - Informe de avance de tareas. | En proceso | El contrato se ha renovado y está vigente hasta el 31 de mayo de 2022.
[8 empty] | Producto mensual: Informe sobre avances de las acciones y resultados en las diferentes líneas de acción mencionadas en el plan de trabajo, que incluya las versiones preliminares/finales de los entregables definidos en las actividades - Minutas de reuniones | En proceso
| 4.2 Diseño de productos de comunicación para sensibilizar a los tomadores de decisiones sobre el SPS ¡Vamos! | [6 empty] | TBD | A definir tiempo de ejecución | Los productos a ser diseñados serán parte del resultado del diseño de la estrategia de comunicación. Acuerdos de la reunión de revisión 19/04/2021: Sigue siendo vigente, con miras a las actividades de comunicación a ser implementadas próximamente. Se acuerda que ésta actividad se ejecutará durante el segundo y tercer cuatrimestre del 2021. Acuerdos de la reunión de revisión 7 de marzo de 2022: la actividad sigue vigente, se prevee finalizarla para el mes de noviembre del corriente año.
| 4.3 Implementar actividades de difusión en instituciones públicas involucradas en la implementación del SPS Vamos! a nivel nacional y local | [6 empty] | TBD | A definir tiempo de ejecución | Acuerdos de la reunión de revisión 19/04/2021: Esta actividad sigue vigente. Se considera oportuno ejecutarla durante el segundo semestre del año 2021 en el nivel central, y continuar durante el año 2022, en el nivel territorial. Acuerdos de la reunión de revisión 7 de marzo de 2022: la actividad sigue vigente, se prevee finalizarla para el mes de noviembre del corriente año.
| 4. 4. Aumentar la conciencia, el nivel de conocimiento y la demanda de SPS Vamos entre los beneficiarios en 4 distritos seleccionados. Aumentar la conciencia. | [5 empty] | Se incrementó la conciencia, el nivel de conocimiento y la demanda de SPS Vamos entre los beneficiarios en 5 distritos seleccionados | TBD | A definir tiempo de ejecución | Acuerdos de la reunión de revisión 19/04/2021: La actividad sigue siendo relevante. Se considera que será oportuna ejecutarla durante el año 2022. Se acuerda postergarla. Acuerdos de la reunión de revisión 7 de marzo de 2022: la actividad sigue vigente, se prevee finalizarla para el mes de noviembre del corriente año.

## Senegal 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Senegal
|  | 2022 | [11 empty] | 2023
Objectives | Responsible Organization | Jan | Feb | Mar | Apr | May | June | July | Ago | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
5.1 (SO1) To improve Senegal's design and financing of social protection systems in support to their efforts towards SDGs 1 and 10
5.1.1 (R1.1) Adequate, sustainable and gender-sensitive social protection financing through improved cross-sector co-ordination in coherence with national macro-economic, fiscal, digital and SDG strategies as well as diversification of sources of financing and increased fiscal space available for all social sectors to progressively achieving universal social protection
5.1.1.1 (output) Tools, mecanisms and unified budget framework for an adequat, sustainable, gender and disability sensitive are available.
5.1.1.1. Estimate the cost the Plus component (integrated social services) of the PNBSF in view of sustainable financing through national resources | UNICEF | bar: 2022 Oct to 2023 Mar
5.1.1.2 Strengthen national capacities on public finance management and financing of social protection (with reference to the ILO Handbook on Fiscal Space) | ILO | bar: 2022 May to 2022 July
5.1.1.3 Deepen the fiscal space analysis, design and implement innovative financing options, including new taxes, budget reallocation, measures and mechanisms for capturing the contributory capacity of workers of the informal and rural economy | ILO/UNICEF | bar: 2022 Apr to 2022 Sep
5.1.1.4 Support the updating of the social protection financing strategy/plan and the development and implementation of monitoring tools and framework of the national social protection (including budgets, in relation with EU budget supports). | ILO/UNICEF | bar: 2022 May to 2022 Sep
5.1.2. (R1.2) Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability-inclusive social protection), with participation of regional bodies as well as civil society organisations
5.1.2.1 (output) The social protection systems is reinforced with tools and evidences to guide policy making for its improvement.
5.1.2.1 Conduct a gender and a disability-sensitive review of the social protection system. | ILO/UNICEF | bar: 2022 Jan to 2022 Dec
5.1.2.2. Support a public expenditures review of the social protection schemes and programmes (PER) | ILO/UNICEF | bar: 2022 Jan to 2022 Dec
5.1.2.3 Realize a efficiency analysis of public allocation (DEA) in Education sector in the context of free fees policy | UNICEF
5.2. (SO2) To support governments in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability
5.2.1. (R2.1) Strengthened capacities of partner countries to achieve the best impact of diversified sources of funding for social protection, prioritizing women, children, persons with disabilities, informal economy and migrant workers.
5.2.1.1 (output) Technical capacity of institutional actors, including social partenrs and the civil society, to extend social protection coverage to workers in the informal and rural economy, as also a strategy for sustainable and adequat social protection financing, and people with disability are strengthened.
5.2.1.1 Provide technical assistance for the effective implementation of the simplified scheme for independent workers and workers in the informal economy | ILO | bar: 2022 May to 2022 June; 2022 Oct to 2022 Nov; 2023 Jan to 2023 Mar
5.2.1.2 Build capacity of the line Ministries, IPRES, CSS, ANCMU, workers’ organizations to effectively run the simplified scheme and support its scaling up | ILO | bar: 2022 May to 2022 June; 2022 Oct to 2022 Nov
5.2.1.3 Provide technical services and strengthen capacities for the improvement of the coverage, effectiveness, and financial sustainability of the Universal Health Care Coverage (CMU) programme. | ILO | bar: 2022 June to 2022 Dec
5.2.1.2 (output) Capacities of institutional actors and civil society for an improved targeting of non-contributory programmes beneficiairies and people with disabilities are strengthened in view of reinforcing advocacy for adequat and diversified social protection financing
5.2.1.4.Provide technical assistance for improving the CEC programme, including a better definition of a disability-sensitive service package | ILO | bar: 2022 May to 2022 June; 2022 Sep to 2022 Dec
5.2.1.5. Support the updating of the database of the national unified registry (RNU), in relation with the EU budget support***. | UNICEF | bar: 2022 Jan to 2022 Feb
5.2.1.6. Support the promotion of essential family practices (Behaviour change communication activities) - monitoring of key family practices*** | UNICEF | bar: 2022 July to 2023 Mar
5.2.2. (R2.2) Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society.
5.2.2.1 (output) Build capacity of sub-national government’s institutions for an improved implementation of the SNPS and social protection programmes (platform)
5.2.2.1 Build capacity of sub-national government’s institutions for an improved implementation of the SNPS and social protection programmes (platform)*** | UNICEF | bar: 2022 July to 2022 Sep; 2023 Jan to 2023 Mar
5.2.2.2 Build capacity of the OSBS for a real-time monitoring, adequacy and sustainability of public spending in social protection sectors*** | UNICEF | bar: 2022 Apr to 2023 Mar
5.2.2.3. Strengthen knowledge and capacity of parliamentarians and members of the CESE, HCCT, HCDS for a better understanding of the Pluriannual Budget Programme Documents and draft national budgets*** | ILO/UNICEF | bar: 2022 July to 2022 Dec
5.2.2.4. Document and disseminate good practices of gender-sensitive and disability-sensitive social protection interventions and extension to workers in the informal economy (briefs, videos and experience sharing with sub-national government entities). | ILO/UNICEF | bar: 2022 July to 2023 Apr
5.2.2.5. Capitalize and share documented good practices and country experiences, notably through the Regional social accountability platform for West and Central Africa. | UNICEF
5.2.2.2 (output) Capacities of the civil society, social partners, and actors of the private sector and local actors for an improved transparency, monitory and accountability of national social protection budgets are strengthened
5.2.2.6. Enhanced local and national media and press capacities to support and relay advocacy for increased social protection financing. | UNICEF | bar: 2022 Apr to 2022 Sep
5.2.2.7. With support of the Global coalition for social protection floors, implement information and capacity building activities of actors of the civil society and workers' representatives in the budget planning and monitoring tools, for accelerated advocacy for extending gender- and disability-sensitive adequate social protection, and secured by transparent and sustainable financing | CGSPF | bar: 2022 Jan to 2022 Mar
Activités 5.2.2.7.1 Organiser des rencontres de concertation entre OSC et syndicats (comité de pilotage OSC/syndicats, comité technique, ..) | [18 empty] | Pas de responsable, n'apparaît pas dans le workplan de l'année dernière. Peut-on l'enlever? | bar: 2022 Jan to 2022 Mar
5.2.2.7.2. Organiser des séminaires ateliers de renforcerment de l'expertise thématique: Gestion des finances publiques, stratégies d'extension de la protection sociale, mobilisation des ressources domestiques, financement de la protection sociale, elaboration/mise en oeuvre et évaluation des politiques de protection sociale, etc) | [18 empty] | Pas de responsable, n'apparaît pas dans le workplan de l'année dernière | bar: 2022 Jan to 2022 Mar
5.2.2.7.3. Mener des actions de lobby et plaidoyer auprès des décideurs nationaux et des collectivités locales (articulation des systèmes de protection sociale, financement durable de la protection sociale, loi sur la protection sociale, ….) | [18 empty] | Pas de responsable, n'apparaît pas dans le workplan de l'année dernière | bar: 2022 Jan to 2022 Mar
5.2.2.7.4. Organiser les actions d'appropriation et dissémination des recherches réalisées par d'autres acteurs sur financement de l'UE (BIT, UNICEF, OSCAR, REPROSOC): ateliers, production des pamphlets accessibles, communication et sensiblisation | [18 empty] | Pas de responsable, n'apparaît pas dans le workplan de l'année dernière | bar: 2022 Jan to 2022 Mar
5.2.2.8. Organize awareness-raising activities among employers and private sector on the importance of social protection, governance and monitoring tools of the social protection sector and also prevent COVID 19 in the world of work | BIT/UNICEF | [17 empty] | Regarder les commentaires | bar: 2022 May to 2022 July
5.2.2.9. Support Citizens Budgets to improve public understanding and ownership of social protection programmes and spending*** | UNICEF | bar: 2022 Apr to 2023 Mar
5.3. (SO3) To assist partner countries in developing and applying shock-sensitive social protection programmes and systems adapted to the needs of those living in protracted fragility and crises, including forcibly displaced persons
5.3.1. (R3.1) Increased capacities of partner countries in the context of emergencies, natural disasters, forced displacements, protracted fragility and crises to establish contingency plans and multi-year funding strategies to run adaptive social protection mechanisms
5.3.1.1 (output) National capacities to implement mechanisms and measures to finance social protection in the context of crisis, natural disasters and displaced people are reinforced
5.3.1.1. Conduct a child poverty analysis (Multiple Overlapping Deprivation Analysis) in order to strengthen children-sensitive cash transfers and better meet children needs, notably in terms of nutrition and food security | UNICEF | bar: 2022 Apr to 2022 Dec
5.3.1.2 Propose mechanisms for improving coordination between food insecurity interventions and existing social protection measures and programmes | UNICEF | bar: 2022 July to 2022 Dec
6.3.Communication and visibility | ILO/UNICEF
6.4. Validation workshops
6.4.1 Validation workshop and dissemination results of the estimation cost of the plus component of PNBSF | UNICEF | bar: 2022 Mar
6.4.2 Validation workshop and dissemination results PER of social protection programme | UNICEF
6.4.3 Validation workshop and dissemination results of the social fiscal expenditure | UNICEF
6.4.4 Validation workshop and dissemination results of the efficiency analysis of public allocation (DEA) in Education sector | UNICEF | bar: 2022 Dec
6.4.5 Validation workshop and dissemination results of the Child Poverty and Multiple Deprivation Report (MODA) | UNICEF
6.4.6 Validation workshop and dissemination results of the final evalution of the project | UNICEF | bar: 2023 Mar
6.4.7 Validation workshop and dissemination results of the gender and the disability-sensitive review of the social protection system | ILO/UNICEF
6.4.8. Workshop of the project's launch | ILO/UNICEF
6.4.9 Validation workshop and dissemination results of legal, institutional, operational and administrative framework and IT system of the simplified scheme | ILO | bar: 2022 Jan to 2022 June
6.4.10 Validation workshop and dissemination results of options for improving disability-sensitive social programmes, including the CEC | ILO | bar: 2022 Jan to 2022 Mar
6.4.11 Validation workshop and dissemination results of options for improving the CMU coverage | ILO | bar: 2022 May to 2022 July
6.4.12 Meetings and workshops of the working group and steering committee | ILO | bar: 2022 May to 2022 June; 2022 Nov to 2022 Dec; 2023 Mar to 2023 May
New activities
Audit of the RNU database | UNICEF
Evaluation of the process of using RNU for food assistance Force Covid-19 | UNICEF
Feasibility study for the extension of the RNU to specific population groups | ILO/UNICEF
Communication strategy et site website of the DGPSN | UNICEF
Note on A47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 000 de UNICEF à ajouter à "approfondi" Reply: Le BIT a déjà rélisé cette activité là. Atelier de lancement sera pris en charge par BIT Reply: 10,000 USD de UNICEF porté sur la ligne 5.1.1.3 Approfondissement espace fiscal

## Uganda 2022-23
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan 2022-23
Uganda
Overall objective: To increase the population's universal social protection coverage in partner countries preferably but not limited to those benefiting from EU funded budget support operations
Outcome/s and Result/s | Annual target/s | List of activities | 2022 |  |  |  | 2023 |  | Responsible PUNO/s | Implementing partner/s involved
| 2021 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Outcome (SO 1): To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10. |  | Support to the GoU in publishing programmatic documents and establishing mechanisms to scale and sustain SP for children | [6 empty] | UNICEF | MoGLSD / KCCA
Result (R 1.1): Increased dialogue and coherence among sectors for the sustainable and adequate financing of universal social protection | Participation in at least 3 coordination meetings with government, donors, and/or CSOs per year | A.1.1.1a Technical support for the implementation of the National Social Protection Policy; Participation in sector working groups and steering committee meetings; |  |  | X | X | X |  | UNICEF | MoGLSD / KCCA
| Compile national dialogue report | A.1.1.1b Assessment Based National Dialogue (ABND) Social Protection Policy Options Tools (SPPOT) | X | X | X | X | X | X | ILO | MoGLSD
| Facilitate at least 4 CSO and TU advocacy activities | A.1.1.2 Facilitate civil society and trade union advocacy activities towards key social protection policy and budgetary processes for improved and expanded social protection |  |  | X | X |  |  | HAI | Uganda Social Protection Platform, relevant trade unions
Result (R 1.2): Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations. | 3 operational research studies implemented and leveraged for evidence-based decision-making by GoU; 1 policy brief on key issues of SP and PFM published; | A.1.2.1a Qualitative research studies on gender- and age-responsive social protection; A.1.2.1b Quantitative administrative and policy advocacy data, as well as operational research in the context of KCCA's urban social protection programme for adolescent girls; A.1.2.1c Development of policy advocacy briefs on key issues of SP and PFM that support KCCA in advocating for increased investments in social protection for vulnerable groups with MoFPED and others; |  |  | X | X |  |  | UNICEF | MoGLSD / KCCA / MoFPED /
| Research on informal and rural economy economy | A.1.2.1d Study on informal and rural economy, including recommendations for increasing coverage and exploring innovative financing options (ILO) | X | X | X | X | X | X | ILO | MGLSD
| Actuaurial review of NSSF | A.1.2.1e Governance and administrative review of National Social Security Fund |  |  | X | X | X | X | ILO | NSSF
| Research on social accountability mechanisms for social protection | A.1.2.1f Study on the effectiveness of Uganda’s social accountability mechanisms in improving the design and implementation of social protection programmes | [6 empty] | HAI | Uganda Social Protection Platform
|  | A.1.2.1g Civil society advocacy policy briefs on expanded and improved social protection, impacts of Uganda’s social protection programmes and voices of beneficiaries (based on social accountability initiatives) age, gender and disability lens (HAI) |  |  | X | X |  |  | HAI | Uganda Social Protection Platform
Outcome (SO 2): To support the government in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability. |  | Support to the GoU and collaboration with key stakeholders towards the development and piloting of a shared civil society social accountability approach | [6 empty] | HAI | GoU, CSOs
Result (R2.1): Strengthened capacities of partners to achieve the best impact of diversified sources of funding for social protection, prioritizing children, workers in the informal sector, and older persons. | At least 2 strategically selected officials from MoFPED, KCCA, NSSF, and/or MoGLSD supported to attend PFM and SP training (ILO) | A.2.1.1 Support for strategically selected government officials to participate in PFM and SP training (ILO) |  |  | X | X | X |  | ILO | MoFPED, KCCA, NSSF, and/or MoGLSD
|  | A.2.1.2 Facilitate international peer-learning and knowledge exchange on social protection and PFM |  |  |  | X |  |  | HAI | Uganda Social Protection Platform; GCSPF target countries in Action
| At least 60 CSO and Trade Union members are trained on social protection and public financial management | A.2.1.3 Increase capacity of CSO and Trade Union members on social protection, public financial management |  | X | X | X |  |  | HAI | Uganda Social Protection Platform, relevant trade unions
Result (R 2.2): Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society | Support for 6 gov. officials to attend relevant SP conferences (UNICEF supporting 4, ILO supporting 2); | A.2.2.1 Build the capacity of national policymakers for planning and management of social protection programmes through knowledge-sharing and coordination activities, including supporting the participation of government officials in relevant SP conferences; | X | X | X | X |  |  | UNICEF, ILO | MoGLSD / KCCA / WB
| Pilot the approach to grassroots/community-based social accountability for relevant social assistance programmes | A.2.2.2 Develop and pilot a shared civil society approach to grassroots/community-based social accountability for relevant social assistance programmes |  |  | X | X |  |  | HAI | Uganda Social Protection Platform
|  | A.2.2.3 Increase capacity of CSOs on grassroots/community-based social accountability |  |  |  | X | X |  | HAI | Uganda Social Protection Platform
| One programme document on urban social protection programme for adolescent girls; | A.2.2.4 Support to GoU (KCCA) in the development of programmatic documents for their urban social protection programme for adolescent girls; Support to GoU (KCCA) in establishing mechanisms to sustain and scale SP for children; |  |  | X | X |  |  | UNICEF | MoGLSD/KCCA
| At least one multi-stakeholder dialogue event to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | A.2.2.5 Organise multi-stakeholder dialogue events to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP |  |  | X | X |  |  | ILO | GOU, DPs, CSOs, UNICEF, HAI