## Workplan
Work plan
Outcome 1 |  |  |  | Enhanced conception, coordination, tracking and financing of gender-sensitive and inclusive schemes and programmes, of the social protection system of Burkina Faso towards SDGs 1 and 10
Output | Annual target/s |  |  | List of activities |  | Année 1 (oct 2019-déc 2020) | [6 empty] | Année 2 (jan 2021-déc 2021) |  |  |  | Année 3 (jan 2022-mai 2023) | [5 empty] | PUNO/s involved | Implementing partner/s involved
| Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023) |  |  | Q4 | Q1 | Q2 avril | Q2 mai | Q2 juin | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Total Cost (USD)
Outputs 1.1 An overall review of the national social protection system using ISPA tools allows stakeholders adopting consensual recommendations for improving the social protection system in Burkina Faso and provide evidences for the adoption of the new PNPS | 1 launch Workshop | 1 inventory matrix of plans and programs | 1 capitalisation document of the national dialogue process | Activitie1.1.1 Provide technical support the SP-CNPS and develop tools to reinforce the multisector coordination and facilitate a national dialogue through technical committees and working groups for the formulation of the social protection floor guaranties | Préparer les supports de communication (préparation de pages dans les plateforme internet identifiées, template de présentations et documents, etc.) |  |  | X | [13 empty] | 0 | BIT / UNICEF | SP-CNPS
[5 empty] | Intégrer les réponses interagences et PTF et gouvernement face à la pandémie COVID 19 et mettre à disposition l'expertise du projet dans le cdomaine de la protection sociale |  |  | X | X | X
| 2 Workshops | 1 workshop | 1 workshop | Activité 1.1.2 Implement capacity building activities in order to secure the active participation of all actors of the social protection sector in the national dialogue for the overall review and adoption of recommendations for strengthening the system | [18 empty] | BIT / UNICEF | SP-CNPS | bar: Q4; Année 2 (jan 2021-déc 2021) Q2
| 1 review document |  |  | Activité 1.1.3 Conduct in consultation with the stakeholders, and referring to ISPA tools, an inventory (coverage, financing and architecture), an analysis of the performance and gaps of contributory and non-contributory social protection programmes and measures and assess the adequacy of internal or external financing to meet the social protection | Préparer la matrice de collecte de données pour la revue globale, sur la base des outils CODI et SPPOT |  |  | X | X | [13 empty] | BIT | SP-CNPS, ministères techniques | bar: Q3 to Q4
[5 empty] | Réaliser une revue documentaire et une collecte des données immédiatement disponibles (internet, échanges à distance avec les parties prenantes) |  |  | X | X | X | bar: Q3 to Q4
|  | 4 national dialogue sessions |  | Activité 1.1.4 Provide technical support to the SP-CNPS for the development of recommendations and reforms to support the coordinated and effective implementation of the PNPS, within the framework of a participatory and inclusive national dialogue | [18 empty] | BIT | SP-CNPS | bar: Q4 to Année 2 (jan 2021-déc 2021) Q1
|  |  | Recommendations for the new PNPS | Activité 1.1.5 Support the SP-CNPS for the integration of reforms in updating PNPS and the drafting of a progressive implementation strategy | [18 empty] | BIT / UNICEF | SP-CNPS | bar: Année 2 (jan 2021-déc 2021) Q2 to Année 3 (jan 2022-mai 2023) Q1
Output 1.2 : Burkina Faso has a sustainable and adequate financing strategy of its national system of social protection |  | 1 review of public spending on social protection |  | Activité 1.2.1 Conduct a social protection expenditures review, including external financing. This review will take in consideration aspects related to gender, children, young people, people with disabilities as well as the impact of shocks on vulnerable populations | [17 empty] | 0 | BIT / UNICEF | SP-CNPS, Ministère de l'Economie, des Finances et du Développement | bar: Q4 to Année 2 (jan 2021-déc 2021) Q1
|  | 1 costing (RAP) of recommendations |  | Activité 1.2.2 Assess the costs of the guaranties of a national social protection floor and recommendations for strengthening the social protection system emanating from the review of the system | [18 empty] | BIT | SP-CNPS | bar: Année 2 (jan 2021-déc 2021) Q2 to Année 2 (jan 2021-déc 2021) Q3
|  | 1 document analysing medium- and long-term funding sources |  | Activité 1.2.3 Identify opportunities for mobilising sustainable resources within the available budgetary space | [18 empty] | BIT | SP-CNPS, Ministère de l'Economie, des Finances et du Développement | bar: Année 2 (jan 2021-déc 2021) Q1 to Année 2 (jan 2021-déc 2021) Q2
|  |  | A medium-term financing framework document for the social protection sectore | Activité 1.2.4 Provide technical and methodological support to the SP-CNPS and the Ministry of Finance in adopting options for sustainable financing in the national social protection system | [18 empty] | BIT / UNICEF | SP-CNPS, Ministère de l'Economie, des Finances et du Développement | bar: Année 2 (jan 2021-déc 2021) Q4 to Année 3 (jan 2022-mai 2023) Q1
|  | 1 capacity building workshop |  | Activité 1.2.5 Implement training activities to reinforce capacities of government institutions and technical ministries, social partners and other actors on social protection (ILO and UNICEF guides and methodologies) in order to take informed decisions regarding the social protection budget | [18 empty] | BIT / UNICEF | SP-CNPS | bar: Q4; Année 2 (jan 2021-déc 2021) Q4
|  |  | 1 capitalisation document | Activité 1.2.6 Prepare the argument and to undertake advocacy actions for increased social protection public financing | [18 empty] | BIT / UNICEF | SP-CNPS | bar: Année 2 (jan 2021-déc 2021) Q3 to Année 2 (jan 2021-déc 2021) Q4
Outcome 2 |  |  |  | To support institutional and technical actors in the implementation of universal health coverage and strengthening of local mechanisms for the extension of social protection schemes and programmes at the municipal level, adapted in particular to the needs of persons in situations of temporary and lasting vulnerability and fragility, including displaced persons
Output | Annual target/s |  |  | List of activities |  | Année 1 (oct 2019-déc 2020) |  |  |  |  | Année 2 (jan 2021-déc 2021) Q1: 2021; Année 3 (jan 2022-mai 2023) Q1: 2022 |  | PUNO/s involved | Implementing partner/s involved
| Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023) |  |  | Q4 | Q1 | Q2 avril | Q2 mai | Q2 juin | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 |  | Q4 | Total Cost (USD)
Output 2.1 Strengthened capacities of institutional and technical actors and tools to monitor the national social protection system |  | 1 mapping of data sources |  | Activité 2.1.1 Carry out a mapping of the social protection statistical system (sources of production, collection and analysis of information) | [17 empty] | 0 | BIT | SP-CNPS | bar: Q4 to 2021 Q1
|  | 1 data compilation tool |  | Activité 2.1.2 Provide technical support to the development of a framework for monitoring and evaluating progress in the social protection sector (ILO SSI, social insurance performance indicators, and SDG indicators) | [18 empty] | BIT | SP-CNPS | bar: 2021 Q2 to 2021 Q3
|  | 1 capacity building workshop |  | Activité 2.1.3 Strengthen stakeholders' capacities to monitor and evaluate social protection programmes, taking into account gender aspects and non-discrimination of people living with disabilities | [18 empty] | BIT | SP-CNPS | bar: 2021 Q4
Output 2.2 Strengthened technical capacities of the schemes to ensure the quality and sustainability of minimum guarantees of social protection |  |  | 1 strategy for the implementation and expansion of the RAMU | Activité 2.2.1 Provide technical assistance to the CNAMU, the mutualist movement and social partners for the effective implementation of the RAMU and its extension to the formal and informal sectors and to the rural sector | [17 empty] | 0 | BIT | CNAMU, mutuelles, ministère du Travail, partenaires sociaux
|  |  | 15 pilot municipalities have targeting mechanisms | Activité 2.2.2 In pilot communes, design and test mechanisms for counselling beneficiaries, channelling central programmes to the local level, collecting data, targeting and registering vulnerable populations in the communal social services | [18 empty] | UNICEF | Ministère de l'Action sociale, autorités locales
|  |  | 15 pilot municipalities have targeting mechanisms | Activité 2.2.3 Provide technical support to the harmonization and strengthening of targeting mechanisms for poor and vulnerable households | [18 empty] | UNICEF | SP-CNPS
|  |  | 1 capitalisation document | Activité 2.2.4 Capitalize on these pilot experiences in order to integrate and scale up good practices in the revision of the PNPS in 2022 | [18 empty] | BIT / UNICEF | SP-CNPS
Outcome 3 |  |  |  | Shock-responsive programmes, tailored to the needs of people in situations of vulnerability, fragility and insecurity, including displaced persons, are integrated into the national social protection system, in coherence and synergy with social insurance schemes, and social assistance and social safety net programmes
Output | Annual target/s |  |  | List of activities |  | Année 1 (oct 2019-déc 2020) |  |  |  |  | 2021 Q1: 2021; 2022 Q1: 2022 |  |  |  | PUNO/s involved | Implementing partner/s involved
| Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023) |  |  | Q4 | Q1 | Q2 avril | Q2 mai | Q2 juin | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 |  | Q4 | Total Cost (USD)
Output 3.1 Strengthened capacities of mechanisms and programmes to ensure the construction of a social protection system that can also meet social protection needs in the context of crisis and fragility in Burkina Faso |  |  | a national approach nexus humanitarian development | Activité 3.1.1 Support consultation between social protection actors and those of the humanitarian country team and humanitarian clusters to strengthen the coherence of humanitarian responses with social protection programmes, and propose steps for their integration into the social protection system | [17 empty] | 0 | BIT / UNICEF | SP-CNPS, Equipe humanitaire pays | bar: Q4 to 2021 Q4
|  |  | 1 system for registering and caring for shock victims | Activité 3.1.2 Provide technical support, where possible, to the identification, registration and integration of beneficiaries of humanitarian responses and displaced people in the single social registry, the communal social services and the universal health scheme | [18 empty] | BIT / UNICEF | SP-CNPS, Equipe humanitaire pays | bar: 2021 Q4 to 2022 Q3
|  |  | intégration des réponses integration of humanitarian responses into the data compilation tool | Activité 3.1.3 Provide technical support to the integration of data (on coverage, benefits, financing, etc.) of humanitarian responses into the national social protection information system | [18 empty] | BIT / UNICEF | SP-CNPS, Equipe humanitaire pays | bar: 2021 Q3 to 2021 Q4
|  |  | 1 document capitalizing on good practices | Activité 3.1.4 Document good practices in linking social protection and humanitarian responsesDocumenter les bonnes pratiques du lien entre protection sociale et réponses humanitaires | [18 empty] | BIT / UNICEF | SP-CNPS, Equipe humanitaire pays | bar: 2022 Q2 to 2022 Q3