## Workplan
Work plan SENEGAL | SEN/19/50/EUR
Outcome 1 |  |  |  |  | To improve Senegal's design and financing of social protection systems in support to their efforts towards SDGs 1 and 10
Output | Annual target/s |  |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Results 1.1 Adequate, sustainable and gender-sensitive social protection financing through improved cross-sector co-ordination in coherence with national macro-economic, fiscal, digital and SDG strategies as well as diversification of sources of financing and increased fiscal space available for all social sectors to progressively achieving universal social protection |  |  | 1 technical report/1 workshop |  | 1.1.1. Estimate the cost the Plus component (integrated social services) of the PNBSF in view of sustainable financing through national resources | [14 empty] | UNICEF | DGPSN | bar: 2021 Q3 to 2022 Q4
| 1 workshop | 1 workshop | 1 workshop |  | 1.1.2 Strengthen national capacities on public finance management and financing of social protection (with reference to the ILO Handbook on Fiscal Space) | [14 empty] | ILO/UNICEF | MFB, MEPC, MTRIDS, MEDCEST | bar: 2020 Q3; 2021 Q2; 2022 Q2
|  | 1 report of the review |  |  | 1.1.3 Deepen the fiscal space analysis, design and implement innovative financing options, including taxes reforms and mechanisms for capturing the contributory capacity of workers of the informal and rural economy | [14 empty] | ILO / UNICEF | MFB, MEPC, MTRIDS, MEDCEST, MSAS, MEN, GCSPF, workers and employers' representatives | bar: 2021 Q1 to 2021 Q3
|  |  | 1 plan/strategy | monitoring framework | 1.1.4 Support the updating of the social protection financing strategy/plan, the development and implementation of monitoring tools and framework of the national social protection (including budgets, in relation with EU budget supports). | [14 empty] | ILO / UNICEF | MFB, MEPC, MTRIDS, MEDCEST, DGPSN, MSAS, MEN, GCSPF, workers and employers' representatives | bar: 2020 Q3 to 2023 Q1
Result 1.2: Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations |  | 1 technical report / 1 workshop |  |  | 1.2.1 Conduct a gender and a disability-sensitive review of the social protection system | [14 empty] | ILO/UNICEF | MTRIDS, MSAS, GCSPF, workers and employers' representatives | bar: 2020 Q3 to 2021 Q4
|  | 1 technical report / 1 workshop |  |  | 1.2.2 Support a public expenditures review of the social protection schemes and programmes (PER) | [14 empty] | ILO / UNICEF | MFB, MEPC | bar: 2020 Q3 to 2021 Q4
| 1 training session on the methodology | 1 technical report/ 1 worskshop |  |  | 1.2.3 Realize a efficiency analysis of public allocation (DEA) in Education sector in the context of free fees policy | [14 empty] | UNICEF | MEN, MEPC, MFB | bar: 2020 Q3 to 2021 Q4
Outcome 2 |  |  |  |  | To support governments in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability
Output | Annual target/s |  |  |  | List of activities | 2020 Q2: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023 |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 |  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Result 2.1. Strengthened capacities of partner countries to achieve the best impact of diversified sources of funding for social protection, prioritizing women, children, persons with disabilities, informal economy and migrant workers. | 2 workshops/ 1 technical note | 1 workshop/ 1 technical note | 1 workshop |  | 2.1.1 Provide technical assistance for the effective implementation and monitoring of the simplified scheme for independant workers and workers in the informal economy | [14 empty] | ILO | MTRIDS, IPS, GCSPF,HCDS, workers and employers' representatives | bar: 2020 Q3 to 2023 Q1
| 2 training sessions | 3 training sessions | 1 technical note 1 training session |  | 2.1.2 Build capacity of the line Ministries, IPRES, CSS, ANCMU, workers’ organizations to effectively run the simplified scheme and support its scaling up | [14 empty] | ILO | MTRIDS, IPS, GCSPF, workers and employers' representatives | bar: 2020 Q3 to 2020 Q4; 2021 Q2; 2021 Q4; 2022 Q2; 2022 Q4 to 2023 Q1
| 2 workshops | 1 workshop | technical note |  | 2.1.3 Provide technical services and strengthen capacities for improving the link between the CMU and the PNBSF, and the CMU and the extension to workers in the informal and rural economy. | [14 empty] | ILO | ACMU, MDCEST | bar: 2020 Q2 to 2020 Q3; 2021 Q2; 2021 Q4 to 2022 Q2
|  | technical note / 1 workshop | technical note / 1 workshop |  | 2.1.4. Provide technical assistance for improving the CEC programme, including a better definition of a disability-sensitive service package | [14 empty] | ILO | MSAS, GCSPF | bar: 2021 Q3 to 2023 Q1
|  | RNU updated |  |  | .2.1.5. Support the updating of the database of the national unified registry (RNU), in relation with the EU budget support. | [14 empty] | UNICEF | DGPSN | bar: 2020 Q2 to 2021 Q1
| At least 2 workshop/training | At least 1 monitoring of key family practices |  |  | 2.1.6. Support the promotion of essential family practices (Behaviour change communication activities) - monitoring of key family practices | [14 empty] | UNICEF | DGPSN | bar: 2020 Q3 to 2021 Q4
Result 2.2. Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society. | At least 1 platform implemnted | At least 1 platform implemnted |  |  | 2.2.1 Build capacity of sub-national government’s institutions for an improved implementation of the SNPS and social protection programmes (platform) | [14 empty] | UNICEF | MCDEST, DGPSN, HCCT | bar: 2020 Q3 to 2021 Q4
| At least 1 training session |  |  |  | 2.2.2 Build capacity of the OSBS for a real-time monitoring, adequacy and sustainability of public spending in social protection sectors | [14 empty] | UNICEF | MEPC-OSBS; technical ministries; MFB | bar: 2020 Q3 to 2021 Q2
|  | 2 workshops | 2 workshops |  | 2.2.3. Strengthen knowledge and capacity of parliamentarians and members of the CESE, HCCT, HCDS for a better understanding of the Pluriannual Budget Programme Documents and draft national budgets | [14 empty] | ILO / UNICEF | MFB, CESE, HCDS, HCCT, Parlamentarians | bar: 2021 Q2; 2021 Q4; 2022 Q2; 2022 Q4
|  | 1 practice | 1 practice |  | 2.2.4. Document and disseminate good practices of gender-sensitive and disability-sensitive social protection interventions and extension to workers in the informal economy (briefs, videos and experience sharing with sub-national government entities). | [14 empty] | ILO / UNICEF | GCSPF | bar: 2021 Q1 to 2021 Q4; 2022 Q3 to 2023 Q1
| 1 workshop/ south-south cooperation | 1 workshop/ south-south cooperation |  |  | 2.2.5. Capitalize and share documented good practices and country experiences, notably through the Regional social accountability platform for West and Central Africa. | [14 empty] | UNICEF | UNICEF R.O | bar: 2020 Q3 to 2021 Q4
|  | At least 1 training session/ 1 televivion or radio report | At least 1 training session/ 1 televivion or radio report |  | 2.2.6. Enhanced local and national media and press capacities to support and relay advocacy for increased social protection financing | [14 empty] | UNICEF | DGPSN, Medias | bar: 2020 Q4 to 2022 Q3
| Technical support/ events | Technical support/ events | Technical support/ events | Technical support/ events | 2.2.7. With support of the Global coalition for social protection floors, implement information and capacity building activities of actors of the civil society and workers' representatives in the budget planning and monitoring tools, for accelerated advocacy for extending gender- and disability-sensitive adequate social protection, and secured by transparent and sustainable financing | [14 empty] | GCSPF
| 1 workshop |  |  |  | 2.2.8. Organize employers' and private sector's awareness raising activities on the importance of social protection and governance and monitoring tools of the social protection sector | [14 empty] | ILO / UNICEF | Employers' representatives | bar: 2020 Q4
|  | 1 draft of citizen budget on social protection available |  |  | 2.2.9. Support Citizens Budgets to improve public understanding and ownership of social protection programmes and spending | [14 empty] | UNICEF | MEPC, MFB, GCSPF, workers and employers' representatives | bar: 2021 Q1 to 2021 Q4
Outcome 3 |  |  |  |  | To assist partner countries in developing and applying shock-sensitive social protection programmes and systems adapted to the needs of those living in protracted fragility and crises, including forcibly displaced persons
Output | Annual target/s |  |  |  | List of activities | 2020 Q2: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023 |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 |  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Output 3.1 Increased capacities of partner countries in the context of emergencies, natural disasters, forced displacements, protracted fragility and crises to establish contingency plans and multi-year funding strategies to run adaptive social protection mechanisms |  | 1 report available |  |  | 3.1.1. Conduct a child poverty analysis (Multiple Overlapping Deprivation Analysis) in order to strengthen children-sensitive cash transfers and better meet children needs, notably in terms of nutrition and food security | [14 empty] | UNICEF | DGPSN, MSAS, MEN, SECNA | bar: 2020 Q3 to 2021 Q4
|  |  |  | 1 mechanism to respond to food insecurity | 3.1.2 Propose mechanisms for improving coordination between food insecurity interventions and existing social protection measures and programmes | [14 empty] | UNICEF | DDPSN, MEN, SECNA | bar: 2022 Q1 to 2023 Q2
Evaluation
| Annual target/s |  |  |  | List of activities | 2020 Q2: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023 |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Evaluation of the project |  |  |  | 1 evaluation report available | Documentation and lesson learned on the project | [14 empty] | ILO / UNICEF | Consultants | bar: 2022 Q1 to 2023 Q1
Delegation generale de la Protection sociale et de la Solidarite nationale (DGPSN) du MDCEST
Ministere du Travail, des Relations institutionnelles et du Dialogue sociale (MTRIDS)
Ministere des Finances et du Budget (MFB)
Ministere de l'Economie, du Plan et de la Cooperation (MEPC)
Ministere de la Sante et de l'Action sociale (MSAS)
Ministere de l'Education nationale (MEN)
Global Coalition for social protection floors (GCSPF)
Institutions de Prevoyance sociale (IPS)
Agence national de la Couverture Maladie Universelle (ACMU)
Commission economique, sociale et environnementale (CESE)
Haut conseil du Dialogue social (HCDS)
Haut conseil des Collectivites territoriales (HCCT)
Conseil national de la Sécurité alimentaire (SECNSA)