## Workplan
Work plan Approach 2 | GLO/20/50/EUR
Outcome 1 |  |  |  |  | A minimum of 10 countries receive on-demand high quality, gender-responsive, disability-inclusive technical advisory services that are relevant and produce technically, financially and politically feasible recommendations on how to improve the national social protection system, programmes or delivery mechanisms
Output | Annual target/s |  |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Outputs 1.1 Selection of 10 countries through a minimum of two call for proposals, based on criteria of relevance and sound operations | min. 15 requests received | min. 15 requests received |  |  | 1.1.1 Launch and disseminate the calls for proposals, receive the proposals | [14 empty] | ILO | EU Delegation, Government | bar: 2020 Q2 to 2020 Q3
| min. 5 requests approved | min. 5 requests approved |  |  | 1.1.2 Organise the selection of requests through the operational steering committee | [14 empty] | ILO | Operational Committee | bar: 2020 Q3
| min. 5 of requests supported | min. 10 of requests supported |  |  | 1.1.3 Support services to develop the proposals | [14 empty] | ILO | Government, social partners, CSO | bar: 2020 Q2 to 2020 Q3
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | Composition of the team | min. 3 of countries receiving services and backstopping missions | min. 3 of countries receiving services and backstopping missions | min. 3 of countries receiving services and backstopping missions | 1.2.1. Set up a multidisciplinary technical team to deliver the services in line with the request | [14 empty] | ILO | Experts and academias | bar: 2020 Q4 to 2021 Q4
| TDR of the participatory process | min. 7 countries with a process for participatory implementation |  |  | 1.2.2. Establish a process for participatory implementation of the advisory services , to the extent possible drawing on existing consultation or dialogue structures | [14 empty] | ILO | EU Delegation, Governments, UN agencies | bar: 2020 Q3 to 2023 Q1
|  | min. 3 countries with social protection data and information | min. 5 countries with social protection data and information |  | 1.2.3. Create evidence base to address the request, including information and data on gender, disability, shock-responsiveness, costs, financing and digitalization | [14 empty] | ILO | Goverrnments, including National Statistical agencies, UN agencies | bar: 2021 Q1 to 2022 Q4
|  | min. 3 of countries with identified scenarios | min. 5 of countries with identified scenarios |  | 1.2.4. Identify different scenarios to improve the social protection system, programme or delivery mechanisms (in line with the request) - scenarios are designed ensuring coherence and coordination within the social protection system across sectors and administrative levels and beyond social protection sector and with related policy areas such as employment policies. | [14 empty] | ILO | EU Delegation, Governments, social partners, CSO, UN agencies | bar: 2021 Q1 to 2022 Q3
|  | min. 3 scenarios that are costed per country | min. 3 scenarios that are costed per country |  | 1.2.5. Analyse the identified scenarios regarding their cost, financing sources, political economy implications, institutional capacity, technical feasibility and taking into consideration implications regarding their effects on gender, disability, shock-responsiveness and potential of using new technologies in their implementation | [14 empty] | ILO | EU Delegation, Governments, social partners, CSO, UN agencies | bar: 2021 Q3 to 2022 Q4
|  | min. 1 dissemination and advocacy events (per country) | nb. of dissemination and advocacy events (per country) | nb. of dissemination and advocacy events (per country) | 1.2.6. Disseminate findings so that national stakeholders, including social partners are well-informed about social protection needs and possible actions to address them | [14 empty] | ILO | EU Delegation, Governments, social partners, CSO, UN agencies | bar: 2022 Q3 to 2023 Q1
|  |  | min. 1 outcome document at country level | min. 1 outcome document at country level | 1.2.7. Summarize delivered technical advisory services in an outcome document (country report, strategy, roadmap, draft policy, etc.) | [14 empty] | ILO | Operational Committee, Governments | bar: 2022 Q3 to 2023 Q2
| min. 3 countries with a monitoring framework | min.8 of countries with a monitoring framework |  | min.8 of countries with a monitoring framework completed | 1.2.8. Establish a framework and tools for monitoring progress in implementing the project outcomes (country report, strategy, roadmap, draft policy, etc.) and in extending social protection | [14 empty] | ILO | Operational Committee, National statistical agencies | bar: 2020 Q4; 2021 Q4; 2022 Q4 to 2023 Q2