## Workplan
Work plan Approach 2 | GLO/20/50/EUR
Outcome 1 |  |  |  |  | A minimum of 10 countries receive on-demand high quality, gender-responsive, disability-inclusive technical advisory services that are relevant and produce technically, financially and politically feasible recommendations on how to improve the national social protection system, programmes or delivery mechanisms
Output | Annual target/s |  |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Outcome 1: To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10. |  | backstopping of 5 action research | backstopping of 5 action research | 1 research study with external validity | Activity 1.1: Research on multiplier effects and coordination of other research activities | [14 empty] | ILO | EU Delegation, Government
|  | backstopping of 4 tool applications or analytical work | backstopping of 4 tool applications or analytical work |  | Activity 1.2: Backstopping analytical work and tool applications, in particular on fiscal space
|  | Backstopping of country work (1) on shockresponsiveness | Backstopping of country work (1) on shockresponsiveness | Development of SPaN guidance package or other nexus tools | Activity 1.3: Further development of the EU SPaN Guidance Package
|  |  |  | Min. 3 tools refined | Activity 1.4: Refining of ISPA tools, TRANSFORM and ILO good practice guides
|  | Min. 2 events | Min. 2 events |  | Activity 1.5: Support to regional and global meetings/workshops/conferences
|  |  |  | 1 conference | Activity 1.6: End of project international (closing) workshop/confernece
| See communication plan indicators and targets |  |  |  | Activity 1.7: Communication and visibility | [14 empty] | ILO | Operational Committee
| 1 inception report | 1 financial and narrative progress report 1 evaluatbility report | 1 financial and narrative progress report | 1 final financial and narrative report 1 final evaluation | Activity 1.8: Overall management of the Action, including monitoring and final evaluation | [14 empty] | ILO | Government, social partners, CSO
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | 1 training on PFM | Min. 3 webinars or trainings | Min. 3 webinars or trainings |  | 2.1 Training and capacity building | [14 empty] | ILO | Experts and academias