## Work Plan
Outcome |  |  |  | The Sistema de Protección Social Vamos! (SPS)'s management, budget, programme design and territorial implementation is strengthened.
Output | Annual target/s |  |  | List of Activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 | Total Cost (EURO) | PUNO/s involved | Project Manager | Programme Officer | Project Staff
| 2020 | 2021 | 2022 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
1. Opportunities for fiscal space and increase in Public Finance efficacy and efficiency of the SPS are identified | 1 (one) Social protection gap analysis delivered with indicators developed. | 1 (one) Costing of identified social protection coverage gaps, fiscal space analysis and prioritization to cover identified gaps and projections with attention to gender and disability delivered. Publication and presentation of results (inculdes workshop with international expert) done. |  | 1.1 Develop a diagnostic of the SPS's budget efficiency and fiscal space to finance its expansion | [12 empty] | 280410 | Project Manager: ILO, Other collaborating unit: UNICEF | Guillermo Montt, ILO | Veronica Herken, ILO | National consultant (6 work/person/months) | bar: 2020 Q3; 2021 Q1 to 2021 Q3
| 1 (one) Analysis of the effects of social protection investment on poverty, employment, economic activity, child well-being in periods of crisis and economic growth delivered. 1 (one) Analysis on the political economy of fiscal space expansion for social protection delivered. 1 (one) Publication and presentation of results. |  |  | 1.2 Provide scientific evidence on the economic and social returns of investing in social protection | [13 empty] | Project Manager: ILO, Other collaborating unit: UNICEF | Guillermo Montt, ILO | Veronica Herken, ILO | Consultant from University of Sao Paulo | bar: 2020 Q3
2. First phase of the SPS ¡Vamos! in selected territories implemented. | List of identified and registered SPS beneficiaries in 5 selected districts elaborated. |  |  | 2.1. Identification and registration of SPS beneficiaries in 5 selected districts. | [12 empty] | 275954 | Project Manager: UNICEF, Other collaborating unit: ILO | Rigoberto Astorga, UNICEF | TBD | TBD | bar: 2020 Q2 to 2020 Q3; 2021 Q3 to 2021 Q4
| Road map of services targeting children aged (0-4 years) in 5 local districts developed. |  |  | 2.2.Develop a road map of services targeting children aged (0-4 years) in 5 local districts. | bar: 2020 Q2 to 2020 Q3
| Sub-national coordination mechanisms of all sectors involved with the implementation in the 5 selected districts established. |  |  | 2.3. Establish a sub-national coordination mechanisms of all sectors involved with the implementation in the 5 selected districts | bar: 2020 Q2 to 2020 Q3
| Training curriculum developed |  |  | 2.4 Training of human resources capacities at the local level to plan and monitor the delivery of services to children from 0 to 4 years. | bar: 2021 Q1 to 2021 Q2; 2021 Q4 to 2022 Q2
|  |  | Implementation manual(s) of the SPS ¡Vamos! at the local level, with related tools and/or instruments elaborated | 2.5 Elaboration of the implementation manual(s) of the SPS ¡Vamos! at the local level, with related tools and/or instruments | bar: 2021 Q1 to 2021 Q2; 2021 Q4 to 2022 Q2
|  |  | Implementation of the SPS vamos in selected districts with recommendations for scale up assessed. | 2.6. Assesment of the implementation of the SPS vamos in selected districts with recommendations for scale up | bar: 2022 Q1 to 2022 Q4
3. Strenghtened capacity of public service professionals and civil society organizations to monitor and evaluate social protection programmes in the context of a results-based budget |  | Skills development programme (online and face-to-face) for civil servants and civil society members designed and piloted. |  | 3.1 Skills development programme designed for public service professionals and civil society members on life-cycle approach social protection systems and results-based budgeting | [12 empty] | 250932 | Project Manager: ILO, Other collaborating unit: UNICEF | Guillermo Montt, ILO | Veronica Herken, ILO | Global/Regional training institution with online training platform Local training institutions | bar: 2020 Q3; 2021 Q1 to 2021 Q4
|  | 1 (one) Workshop for staff in the Dirección General de Presupuestos on the use of evaluation and monitoring tools for social protection programmes in the context of results-based budgeting delivered. | Tools on the evaluation and monitoring of social protection programmes in the context of results-based budgeting provided. 1 (one) Workshop for staff in the Dirección General de Presupuestos on the use of evaluation and monitoring tools for social protection programmes in the context of results-based budgeting delivered. | 3.2 Strengthened capacity in the Dirección General de Presupuestos for the monitoring and evaluation of social proection programmes in the context of results-based budgeting with a focus on those programmes included in the SPS ¡Vamos! | [13 empty] | Project Manager: ILO, Other collaborating unit: UNICEF | Guillermo Montt, ILO | Veronica Herken, ILO | International consultant | bar: 2020 Q3; 2021 Q1 to 2022 Q2
| 3 (three) Participants in the "Public Finance for Social Protection Analysts" course. 1 (one) Participant in the "Public Finance Management for Children" course on monitoring public investment in children and social protection. | 3 (three) Participants in the "Public Finance for Social Protection Analysts" course. 1 (one) Participant in the "Public Finance Management for Children" course on monitoring public investment in children and social protection. | 3 (three) Participants in the "Public Finance for Social Protection Analysts" course. | 3.3 Skills development for public service professionals and civil society members on public financing for social protection | [13 empty] | Project Manager: ILO, Other collaborating unit: UNICEF | Guillermo Montt, ILO | Veronica Herken, ILO | Global training institution | bar: 2021 Q1 to 2022 Q3
4. Knowledge, ownership and demand of SPS ¡Vamos! within public institutions, service providers and beneficiaries increased.. | General communication strategy for the SPS ¡Vamos! designed. |  |  | 4.1 Design of a general communication strategy for the SPS ¡Vamos! | [12 empty] | 207574 | Project Manager: UNICEF, Other collaborating unit: ILO | Rigoberto Astorga, UNICEF | TBD | TBD | bar: 2020 Q2 to 2020 Q3
|  | Communication products to raise awareness among decision makers about the SPS ¡Vamos! designed |  | 4.2 Design of communication products to raise awareness among decision makers about the SPS ¡Vamos! | bar: 2020 Q4 to 2021 Q2
|  | Dissemination activities in public institutions involved with the implementation of the SPS Vamos! at the national and local level implemented. |  | 4.3 Implement dissemination activities in public institutions involved with the implementation of the SPS Vamos! at the national and local level | bar: 2020 Q4 to 2021 Q1; 2021 Q4 to 2022 Q1
|  |  | Awareness, knowledge level and demand of SPS Vamos among beneficiaries in 5 selected districts increased | 4. 4. Increase awareness, knowledge level and demand of SPS Vamos among beneficiaries in 5 selected districits.4. Increase awareness. | bar: 2021 Q4 to 2022 Q2
Note on E3: ====== ID#AAAAJJWvGNM (2020-02-26 20:55:37) habria que verificar si cambiaron las actividades de lo presentado por UNICEF -Verónica Herken Agregado. -Valeria Walder