## Workplan
Work plan
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output | Annual target/s |  |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT 1 : Increased capacity of GON and key stakeholders to develop resilient, inclusive national social protection policies, sustainable financing strategies and legal frameworks at Federal and Provincial levels. | Draft Federal Policy document endorsed by key stakeholders | National Social Protection Policy adopted by the government | Action Plan to implement the National policies in place | Action plan implemended | A1.1 Technical assistance to NPC to develop SP policy, including ensuring adequate and sustainable financing for social protection through an inclusive consultations and informed participation of stakeholders . | [14 empty] | UNICEF, ILO, Social Protection Task Team (SPTT) members | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2020 Q4
|  | Integrated M & E framework endorsed by the key stakeholders |  |  | 1) Desk review of relevant documents and drafting of a integrated policy framework (UNICEF); 2)Interministerial consultations on the zero draft ( UNICEF) 3)Consultatons with ILO constituents and compilations of inputs on the draft policy framenwork (ILO) 4) Consultations with civil society org and copilation of inputs (WSM) 5. Finalisation of draft policy framework (UNICEF) 6. Support to NPC in the process of Government's approval of the Policy | bar: 2021 Q1
|  | Draft Policy document endorsed by key stakeholders in P2 & P6 |  |  | .A1.2.Technical assistance to two Provincial Governments ( P6, P2) to formulate inclusive Provincial Social Protection Policy , regularly monitor the implementation of the policy agenda and backstop Municipalities in improving their SP services through effective monitoring and feedback. | [14 empty] | UNICEF, ILO | Local Government ( P2, P6 & selected Municipalities) & IT serice providers, Academicians | bar: 2021 Q4
|  | Provincial level M & E framework endorsed by key stakeholder sin P2 and P6 |  |  | 1) SP context analysis in 2 Provinces (ILO) 2) Training to stakeholders for informed policy making (ILO) 3) Consultations for policy formulation (ILO/UNICEF) 4) Writing of policy document(UNICEF) 5) Sharing workshop on lessions learned with other 5 Provinces | bar: 2021 Q4 to 2022 Q1
|  | SMS -based monitoring tool developed and tested |  |  | 6) M and E framework for P2 and P6 (UNICEF) 7) Support to implement SMS based technology (RapidPro) for real-time monitoring of implementation of social protection and other social services in Provinces 2 and 6 (UNICEF). 8)Support to Province 2 and 6 to develop, test and refine improved processes for the assessment of PWD(UNICEF) | bar: 2021 Q3 to 2022 Q1
PWD assessment tool developed and tested in P2 & P6 | bar: 2020 Q4 to 2021 Q3
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output | Annual target/s |  |  |  | List of activities | 2020 Q2: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023 | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT: 2 Government enabled to establish and operationalise a high-level social protection coordination, monitoring and evaluation mechanism at Federal level. | Awareness rasied among relevant policy makers on the need of high level coordination for SP policies, strategies & programmes | 1. Institutional framework for federal level coordination and monitoring of SP systems agreed by stakeholders. | TA to NPC designed, agreed from the relevant government and implemented to operationalise the Institutional mechanism of coordination. | TA implemented | A2.1Technical support to an appropriate Government Agency to establish and operationailes the institutional framework 1) A review of current institutional framework and gap analysis 2) Policy dialogus with parliamentarians and key government agencies on the need of a institutional framework 3) Shairing of international practices 4)TA to the NPC to recommend the institutional framework,including modus operandi, resource requirements, necessary legal and technical tools, including a M and E framework for the establishment and operationalisation of the coordination mechanism (UNICEF/ILO). | [14 empty] | UNICEF, ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2021 Q1; 2021 Q3 to 2021 Q4; 2022 Q2 to 2023 Q2
2. Regulations drafted for th eestablishment and operationalisation of the institutional framework | bar: 2021 Q1 to 2021 Q3
RESULT 3 Increased capacity of Federal and Provincial Governments to plan, budget, implement and monitor extension of contribution –based social protection systems and programmes, overcoming the challenges such as informality, while ensuring financial sustainability of the contributory system. | Actuarial valuations of 4 schemes | 1. Schemes redesigned in line with Actuarial valuations | 3. Relevant Government Officials trained on SP fianacing |  | A 3.1. Technical support to build government's capacity on sustainable SP financing and through effective and innovative communication ensure the generated knowledge and results have a meaningful impact in SP financing. 1) Actuarial valuations of 4 contributory schemes to be implemented by SSF 2) Orientation to Social Security Fund Board members to understand the actuarial valuations 3. Redesign the schemes based on Actuarial recommendations 3) Study on the contributory capacity of informal economy workers 4)Assessment of public care services expenditure, cost and financial space and recommendations to improve the care services. 5)estimate the potential fiscal space that could be created assuming a potential increase in social security (contribution-based) coverage or contribution rates or both 6) Design and use communication products to disseminate the knowledge generated and to ensure recommendations are used in policy/programme making 6) Training to relevant government officials on social protection financing | [14 empty] | ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4; 2022 Q2
|  | 2. Communication products designed & used to enahance Policy makers'competency in SP financiang | 4. Financing options studied and discussed at Federal and Provincial levels targeting selected informal sectors. | [16 empty] | ILO | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
| 1. Particiaptory Review of SSF systems. 2. Recommendations for system improvement discussed at SSF Board and agreed. 3. IT system evaluated for data security and large data handling, recommendations for improvement made and agreed by SSF. | Capacity development plan implemented in collaboration with various DPS | Capacity development plan implemented in collaboration with various DPS | Capacity development plan implemented in collaboration with various DPS | A 3.2 Technical Assistance to the SSF for the systems (general administration and HR management, registration, eligibility verification, collection of contributions, case management and distribution of benefits, complaints and appeals mechanisms, and monitoring, evaluation and reporting) improvement and effective implementation of the systems ( ILO) | [15 empty] | SSF, NPC, Workers, Employers
| 4. Orientation to SSF Officials on various components of SP. 5. Technical/mangerail capacity development needs of different SSF Units identified and HR development paln prepared and agreed by SSF board. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | 1) Internal review of the systems and recommendations on areas for improvement 1) Agree on the specif priority areas for improvement and provide technical support for improvement 2) Provide support of IT expert, especially to strengthen the data security and large data handling capacity 3) technical support to SSF establish and operationalise an appeal and grievance handling system 4) Assess the technical capacity gap among the SSF team, determine the learning methods and design a learning plan 5) PLan and organise training programmes 6) Study visit for SSF board members and key SSF Officials to learn from successful experience in the Region | [14 empty] | ILO
RESULT 4 Increased capacity of Federal and Local Governments to revise policies, set standards, oversee, monitor and report the social assistance programmes and to identify options to create fiscal space. | 1. Analytical Report Social Assistance produced by DoNIDCR 2. Revise SSA- Social Security guidelines 3. Develop and implement communication strategy | 1. Costing and financing gaps analysis of target 1.3 of SDG (child grant, disability, and old age) 2. Support selected Flood/Disaster prone Palikas to pre- identify and register disaster vulnerable HHs. | 1. Support DoNIDCR to produce "Analytical Annual Report" knowledge product on Social Production ( SSA) Endline Survery of Coverage of SSA completed |  | 4.1 Generate evidences, policy advocacy and develop/improve necessary tools to improve policies and strengthen quality service delivery, with special attention to the child grant and PWDs. 1. Costing and financing gaps analysis of target 1.3 of SDG (child grant, disability, and old age) 2. Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant (schemes with high exclusion errors) 3. Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) | [14 empty] | UNICEF, NPC, DONIDCR, NGOs | Research organiazations, Federal government, province and local government | bar: 2020 Q3 to 2023 Q2
| 4.Training Workshop involving Province and Selected Local Government 5. Learning and study visit on shock responsive social protection | 1. SMS based technology (RapidPro) for real*time monitoring of implemented in Province 2 &6 2. Selected Palikas in 2 and 6 Eastablish regular screenings to identify and register PWD into SSAs. | Strengthened complaints and appeal mechanism, the grievance redressal mechanism (GRM) . |  | 4.2 Support capacity development of Provincial and Local Government in effective Implementation of SSA, (registration, timely delivery monitoring, evaluation and reporting). 1. Training Workshop involving Province and Selected Local Government 2. SMS based technology (RapidPro) for real*time monitoring. 3. Learning and study visit on shock responsive social protection 4. improve complaints and appeal mechanism, the grievance redressal mechanism (GRM) . | [14 empty] | UNICEF, NPC, DONIDCR, NGOs | Research organiazations, Federal government, province and local government | bar: 2020 Q2 to 2021 Q3; 2022 Q1 to 2023 Q2
| Sharing Social Protection related evidences, reports | Strengthen local level Grievance handling mechanism (Publicize list of eligible beneficiaries, | Strengthen "Case management" system to include excluded eligible beneficiaries into Social Protection system |  | Technical support to DoNIDCR/NPC to generate evidence, policy advocacy and develop/improve necessary tools to improve policies and procedures for delivering social protection services with special attention to the child grant and PWDs. i.Costing and financing gaps analysis in achieving of SDG target 1.3 focusing on child grant, disability, and old age. ii.Support the DoNIDCR to conduct a review of MIS system, registration process, grievance handling, payment systems,agree on the actions technical support for improvement including revision of SSA- Guidelines. iii.Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant agree on reforms to simplify and improve the processes, update SSA guidance, and provide iv.Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) v.Support DoNIDCR to produce an "Analytical Annual Report" knowledge product on Social Protection Social Assistance) vi.Strengthen social protection system preparedness and response to disaster and emergencies. vii.Support to implement SMS based technology (RapidPro) for real -time monitoring viii.Develop and implement communication awareness strategy | bar: 2020 Q3 to 2021 Q2; 2021 Q4 to 2023 Q1
| Social Security Guidelines revised as per SS Act 2018 # of local government officials trained in SP | Simplify complain procedure and case management- or facilitating to obtain required legal documents) DONIDCR Annual Report Published | Monitoring report ion timely payment produced. | bar: 2020 Q3 to 2021 Q2; 2021 Q4 to 2023 Q1
RESULT 5 Enhanced accountability mechanism at local government level in Province 2 and 6 |  | Palikas agree to publicize the list of beneficiaries and conducting public Audit | Functional Grievance handling Committee |  | Technical support to DoNIDCR/NPC to generate evidence, policy advocacy and develop/improve necessary tools to improve policies and procedures for delivering social protection services with special attention to the child grant and PWDs. i.Training Workshop on social protection to Province and selected Local Governments ii.Support to P6 and P2 to design and integrate an M&E framework that tracks the performance of the programmes (PWDs, elderly above 80 years, disadvantaged women and children). iii.Learning and study visit on shock responsive social protection iv. Support ongoing process of pre-identify and register disaster vulnerable HHs and link them with payment structure in additional municipalities v. Support the local government to organise regular screenings, to identify and register PWDs into SSAs in Provinces 2 and 6. vi. Technical assistance to province-led gender-focused social protection initiatives (i.e. Beti Bachao Beti Padhao programme in Province 2) to reduce gender inequality through social protection. | [14 empty] | UNICEF | bar: 2020 Q4 to 2021 Q1; 2021 Q4 to 2023 Q1
| Informaiton dessiomination | Finding of veruious evaluation shared. | bar: 2020 Q4 to 2021 Q1; 2021 Q4 to 2023 Q1
RESULT 6 Nepali Civil Society Organisations and Trade Unions are meaningfully and structurally involved in the development, implementation and monitoring of policy processes regarding social protection and public finance management due to improved coordination and enhanced capacities.6 | Grivance handling committee formed | Palikas agree to publicize the list of beneficiaries and conducting public Audit |  |  | Strengthen accountability systems (Programme awareness, registration, eligibility verification, grievance handling, monitoring timely fund flow, payment, and reporting focusing on the child and disability grant). | [14 empty] | ILO WSM,UNICEF | Civil society networks, Community groups , l;ocal government | bar: 2020 Q3 to 2020 Q4; 2021 Q2 to 2023 Q1
| Review improve accountability mechanism of SSAs | Local government Officials trained in Accountability |  |  | i.Review improve accountability mechanism of SSAs ii.Work with DoNIDCR to translate and share revised policy documents, procedure, analytical findings, monitoring reports, with the local government to inform programme performance and its challenges. iii.Strengthen local level Grievance handling mechanism (Publicize list of eligible beneficiaries, simplify complain procedure and improve case management or facilitating eligible but excluded people facilitate to obtain required legal documents) iv. Strengthen Local Government capacity to build awareness, identify beneficiaries, organize public audits on social protection. v. Ensure citizens' participation in monitoring access to social protection and facilitate eligible individuals or HHS to access social protection. vi. Ensure timely payment as specified in the operational guidelines "2 weeks window" in every trimester by strengthening monitoring process. vii. Collaborate with CSOs to monitor and implement social protection mobilizing a consistent community monitoring approach to track social protection service delivery in focus provinces. | bar: 2020 Q3 to 2020 Q4; 2021 Q2 to 2023 Q1
| Awareness rasied among the local government, csos and communities on social protection | Citizens' participation in monitoring access to social protection and facilitate eligible individuals or HHS to access social protection. | Local government more accountable fuctioning | bar: 2020 Q3 to 2020 Q4; 2021 Q2 to 2023 Q2