## Sheet1
EC Programme on “Improving synergies between Social Protection and Public Finance Management for Ethiopia”
ILO/UNICEF Joint Work Plan: 2020-2023
Outcome: Improving the social protection system for Ethiopia through a sustainable financing strategy
Output | Annual target/s |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| Year 1 (Oct 2019-Dec 2020) | Year 2 (Jan 2021-Dec 2021) | Year 3 (Jan 2022-May 2023) |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Output 1 Financing Strategy for Social Protection in Ethiopia | Vulnerability analysis on COVID-19 is done | Draft Fiscal space analysis and investment case produced and consultations with stakeholders is held | - Final fiscal space analysis and investment case documents are completed | 1.1. Building an evidence base for financing non-contributory social protection programmes (such as vulnerability analysis on COVID-19, an investment case for social protection and fiscal space analysis) | [13 empty] | 426110 | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | bar: 2020 Q2 to 2022 Q4
|  | - Draft of the actuarial evaluation submitted - Consultations made with key stakeholders | - final Actuarial evaluation document submitted to PSSA and POESSA | 1.2. Technical/Expertise contribution to actuarial valuation (contributory) | [14 empty] | ILO (lead), UNICEF | POESSA, PSSA | bar: 2020 Q4 to 2022 Q3
|  |  | - Final financing strategy produced | 1.3. Financing strategy (including the research component, policy paper, consultations and validation) | [14 empty] | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | bar: 2021 Q2 to 2023 Q2
|  | - 1 training related to financing social protection | - 1 knowledge exchange forum - - 1 national conference on PFM &SP conducted | 1.4. Awareness raising, workshops, and policy advocacy related to financing social protection | [14 empty] | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | bar: 2021 Q1 to 2023 Q2
Output 2 Extending social security to informal economy workers and supporting labour legislation related to social protection |  | - Draft final of the analytical study on extending SP to informal economy workers submitted | - Final version of the analytical study on extending SP to informal economy workers submitted | 2.1 Technical assessment to extend social security to informal sector workers including COVID-19 social protection responses | [13 empty] | 200000 | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA | bar: 2020 Q3 to 2022 Q3
| -Training and awareness needs assessments done at Federal and selected Regions level. | -1 awareness raising training/ workshops organised at Federal and Regional levels on extension of SP to informal economy workers. | - 1 awareness raising training/workshops organised at Federal and Regional levels on extension of SP to informal economy workers. | 2. 2. Awareness raising through media and/or workshops (Federal/Regional) for consensus building on the extension of social security to informal economy workers including COVID-19 social protection responsive programmes | [14 empty] | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA | bar: 2020 Q3 to 2020 Q4; 2021 Q3 to 2021 Q4; 2022 Q2; 2022 Q4 to 2023 Q1
|  | - 1st and 2nd round of tripartite consolations on minimum wage done with MoLSA, CETU and EEC aiming at establishing a wage board. | - 3rd and 4th round of tripartite consultations done with tripartite partners and the wage board aiming at drafting the minimum wage legislation. | 2.3 Tripartite consultation among government, workers’ and employers’ representatives on minimum wage and related social protection schemes | [14 empty] | ILO (lead), UNICEF | MoLSA, CETU, EEC | bar: 2021 Q1; 2021 Q3; 2022 Q1 to 2022 Q2; 2023 Q1 to 2023 Q2
Output 3. Building the capacity of MoLSA to effectively monitor the social protection system. |  |  |  | 3.1 Support MoLSA and Addis Ababa BoLSA develop monitoring tools and processes to better implement and track social protection programming. | [13 empty] | 387175 | UNICEF (lead), ILO | MoLSA, Addis Ababa BoLSA | bar: 2020 Q2 to 2023 Q2
| -MoLSA and key stakeholders consulted and agreement on cooridnation mechanisms and governance principles established | Social protection platform(s) recognised and formally established | Social protection platform(s) fully functional under MoLSA/BoLSA(s) management | 3.2 Increasing the capacity of MoLSA to facilitate the establishment of effective coordination mechanisms for social protection policy and strategy | [14 empty] | UNICEF, ILO | MoLSA, BoLSAs, MoA, FUJCFSA, | bar: 2020 Q2 to 2023 Q2
|  | Knowledge management tools (e.g. SSI) tested and functional | MoLSA/BoLSA(s) fully capacitated on use of knowledge management tools/platform | 3.2 Developing a knowledge management platform for inclusive social protection | [14 empty] | ILO, UNICEF | MoLSA, Consultant | bar: 2020 Q3 to 2023 Q2
Total | [17 empty] | 817647