## Workplan
Work plan
Outcome |  |  | Outcome1: Based on the results of the rapid socio-economic impact assessment on the informal sector, recommendations are made and national capacities are strengthened to improve and extend the social protection measures initiated as part of the response to the COVID-19.
Output | Annual target/s |  | List of activities | [6 empty] | Implementing partners involved
| 2020 | 2021 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Total Cost
Outcome 1 |  |  | Based on the results of the rapid socio-economic impact assessment on the informal sector, recommendations are made and national capacities are strengthened to improve and extend the social protection measures initiated as part of the response to the COVID-19.
Output 1: A report on the impact of COVID-19 through the social protection dimension is prepared. | A report on the impact of COVID-19 through the social protection dimension is prepared. | Capacities of relevanttechnical services, workers and employers oragnisation and informal sector' actors reinforced on social protection issues in adressing COVID-19 | 5.1.1.1: Analyse the results of the COVID-19 impact study on the informal economy from a social protection perspective, taking into account the following aspects: vulnerable people, geographical areas, sectors of the economy, type and level of benefits, roles of trade union organizations and other informal economy, actors and formulate response options through social protection measures | [5 empty] | 22387.975 | CNPPS, ANADEB, FENASEI, CNSS, Coordination du programme NOVISSI, COVID-19 National Pandemic Response Coordination (CNGR)
|  |  | 5.1.1.2: Develop recommendations to improve and expand social protection measures initiated to address the COVID-19 including the relevant actor’s capacities building. | [6 empty] | CNPPS, ANADEB, FENASEI, CNSS, Coordination du programme NOVISSI, COVID-19 National Pandemic Response Coordination (CNGR)
Output 2: Technical services are provided to the government, social partners and informal economy actors for the extension of social protection measures initiated during the COVID-19 period |  | Options to extend social protection in response to the COVID-19adopted by all stakeholders | 5.1.2.1: Organize consensus among tripartite constituents and other stakeholders on recommendations to improve and expand social protection measures, implemented as part of the response to COVID-19 | [5 empty] | 22387.975 | CNPPS, FENASEI, CNSS, Social partners
|  |  | 5.1.2.2: Provide technical support and build the capacity of the Government, social partners and informal economy actors for the implementation of the options adopted for the extension of social protection in response to the COVID-19 | [6 empty] | CNPPS, FENASEI, CNSS, Social partners
Outcome 2 |  |  | Experiences, knowledge and evidence generated from the implementation of social protection measures benefiting actors in the informal economy as a response to COVID-19 are capitalized and recommendations are formulated to accelerate the sustainable extension of social coverage
Output 3: The modalities of implementation of social protection measures as a response to COVID-19, including the opportunities, strengths and shortcomings of the programs are analysed (the criteria for selecting beneficiaries, registration mechanisms, database, beneficiary management system, payment mechanisms, complaint and satisfaction feedback mechanisms, total cost, including administrative costs, are taken into account). |  | The Universal Solidarity Income implementation modalities analized | 5.2.1.1 : Organize workshops with the main actors of the NOVISSI program, the members of the National Committee for the Promotion of Social Protection and the group of TFPs working on social protection (possibly virtual by videoconference), to share ILO tools for analysing the implementation of the minimum income program | [5 empty] | 28388 | CNPPS, FENASEI, CNSS
|  |  | 5.2.1.2 : Examine the implementation modalities of the Universal Solidarity Income and analyze the forces and weaknesses of the program (beneficiary selection criteria, registration and selection mechanisms, database and beneficiary management system, payment mechanisms, complaint and satisfaction feedback mechanisms, total cost, including administrative costs). | [6 empty] | CNPPS, ANADEB, FENASEI, CNSS, Coordination du programme NOVISSI, COVID-19 National Pandemic Response Coordination(CNGR)
5.2.2 : A report containing the lessons learned from the social protection measures implemented in the response to COVID-19 and recommendations for the scaling up and sustainability of the social protection system based on existing social protection schemes, mechanisms and organizations (CNSS, INAM, professional organizations, mutual insurance companies, etc.) elaborated |  | Lessons learned from social messures in the respond of COVID-19 capitalized | 5.2.1.1 : Organize sharing sessions (possibly virtual by videoconference) to discuss the results of the Universal Solidarity Income Program implementation evaluation. | [5 empty] | 9000 | CNPPS, ANADEB, FENASEI, CNSS, Coordination du programme NOVISSI, COVID-19 National Pandemic Response Coordination(CNGR)
5.2.1.2 : Provide technical support to capitalize lessons learned from the Universal Solidarity Income experience and formulate recommendations for scaling up and sustaining the social protection system based on the results of the evaluation.
Outcome 3 |  |  | 5.3 : An information system, technical and financial parameters and an institutional coordination architecture for the extension of the general social security system managed by the National Social Security Fund (CNSS) and the compulsory health insurance managed by INAM, to the actors of the informal economy are adopted.
5.3.1 : CNSS and INAM information systems strengthened and adapted for the extension of the general social security scheme managed by the National Social Security Fund (CNSS) and the compulsory health insurance managed by INAM to informal economy actors |  | CNSS an INAM arer using an integrated information system for registering informal economy actors. | 5.3.1.1 : Elaborate a technical evaluation report on the information systems of the CNSS and INAM in relation to the needs for extending social protection to the private sector, particularly the informal economy. | [5 empty] | 18577.0698 | CNSS, INAM, CNPPS
|  |  | 5.3.1.2 : Based on the recommendations resulting from the technical evaluation, support CNSS and INAM to adopt a technical protocol and operational modalities for registering informal economy actors. | [6 empty] | CNSS, INAM, CNPPS
5.3.2 : Technical report of the financial assessment of the sustainability and scaling up of the extension of benefits to the informal economy linked to existing and emerging social protection systems |  | Financial parameters elaborated for the extension of social security to workers in the informal economy | 5.3.2.1 : Reinforce capacities, share the ILO approach as well as international experiences on social insurance schemes for the self-employed and those in the informal economy. | [5 empty] | 22800.97 | CNSS, INAM, CNPPS, FENASEI, Social partners Unicef
|  |  | 5.3.2.2 : Support decision making through an actuarial evaluation. | [6 empty] | CNSS, INAM, CNPPS, FENASEI, Social partners, Unicef
|  |  | 5.3.2.3 : Based on the experience of the response to COVID-19, develop a financial estimate of the extension of benefits to the informal economy liked to existing and emerging social protection systems. | [6 empty] | CNSS, INAM, CNPPS, FENASEI, Social , Ministry of Finance, Unicef,
5.3.3 : Technical report on the institutional architecture and operational modalities for extending benefits to the informal economy by linking to existing and emerging social protection systems. |  | The institutional architecture developed and operational for extending benefits to the informal economy by linking to existing and emerging social protection systems. | 5.3.3.1 : Conduct an assessment of the existing institutional and operational frameworks for social protection and identify opportunities and achievements for building the regime of extension to the informal economy | [5 empty] | 21643.8698 | CNSS, INAM, CNPPS
|  |  | 5.3.3.2 : Prepare an institutional architecture document and terms of reference for the operational modalities of coverage extension schemes, based on the lessons learned from the Universal Solidarity Income and other social protection measures. | [6 empty] | CNSS, INAM, CNPPS
|  |  | 5.3.3.3 : Provide technical support to CNSS, INAM and organizations representing the informal economy (mutuals, cooperatives, federations, etc.) for the establishment and application of service delegation agreements, procedures and mechanisms for affiliation, payment of benefits, etc. | [6 empty] | CNSS, INAM, CNPPS, FENASEI,
|  |  | 5.3.3.4 : Prepare a skills development plan for staff at management and operational levels for the implementation of future schemes to expand into the informal economy | [6 empty] | CNSS, INAM, CNPPS
|  |  | 5.3.3.5 : Provide technical support to strengthen the technical capacities of organizations representing the informal economy (mutuals, cooperatives, federations, etc.) in the various areas of the services delegated to them (awareness raising, identification, collection of social contributions, quality control of services, etc.). | [6 empty] | Ministry of Labour, CNSS, INAM, Social parteners, CNPPS, DOSI
5.3.4 : Technical recommendations for developing the legal framework for extending benefits to the informal economy by linking to existing and emerging social protection systems, in line with international labour standards on social security. |  | The legal framework adapted for extending benefits to the informal economy; Workers' organizations, cooperatives, mutual societies and other structures of the informal economy efficiently assume their roles in the extension of social protection. | 5.3.4.1 : Conduct a legal and institutional analysis of existing and emerging social protection systems, in relation to the social protection needs of the informal economy. | [5 empty] | 12750 | Ministry of Labour, CNSS, INAM, Social parteners, CNPPS, DOSI
|  |  | 5.3.4.2 : Make recommendations for the development of the legal framework for the extension of benefits to the informal economy by linking to existing and emerging systems of social protection, in line with international labour standards on social security. | [6 empty] | Ministry of Labour, CNSS, INAM, Social parteners, CNPPS, DOSI
|  |  | 5.3.4.3 : Provide technical support for the development of regulatory texts and technical architecture for the extension of social security and health insurance schemes to the informal economy | [6 empty] | Ministry of Labour, CNSS, INAM, Social parteners, CNPPS, DOSI
|  |  | 5.3.4.4 : Organize training sessions for technical service managers, workers' and employers' organizations in the design, planning, implementation and monitoring-evaluation of social protection. | [5 empty] | 5000 | Ministry of Labour, CNSS, INAM, Social parteners, CNPPS, DOSI