| Post 2015 UN Development Agenda |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Dates | Context/Lead UN Agencies/Stakeholders | Outputs | End Date |
| Outcome |  |  |  |  |
| High Level meeting on the MDG and beyond of the General Assembly | The 68th Session of the UNGA, 23 September, 2013 | - The 2010 MDG Summit requested the President of the GA at its 68th session to organize a special event to follow up efforts made towards achieving the MDG - Report of the Secretary General to be drafted by DESA - Report of the Intergovernmental Group | - Outcome TBC: Draft resolution? Launch the negotiation process? | September 2013 – September 2014 |
| UN Secretariat driven process |  |  |  |  |
| UN System Task Team on the Post 2015 agenda | February 2012 | - Established by the UN Secretary-General - Led by UNDP and DESA - Inclusive of all UN agencies - First meeting Included 45 organization and entities within the UN System and 19 institutions ranging from academia to NGOs | - Final Report “Realizing the Future We Want for All” was delivered in June 2012 - Intermediary outputs: 18 Thematic Think Pieces - Subgroups on technical support, partnership development and indicators and monitoring | Ongoing |
| National Consultations | First meeting May 2012 | - Led by UNDG in 50 countries (Table 2) - UN RC’s to provide overall strategic guidance | - Influence the intergovernmental process by amplifying the voices of the poor - Recommendations for governments | May 2013 |
| Thematic Events | First meeting May 2012 | - Total of 9 thematic events (Table 3) | - Recommendations for governments | February 2013 |
| SG’s High Level Panel of Eminent Persons | July 1, 2012 | - Co-chaired by President Yudoyono of Indonesia, President Johnson Sirleaf of Liberia and Prime Minister Cameron of the UK, and 26 members from governments and other sectors. | - Informed by UN Task Team report, Rio+20 and thematic consultations - First and final meetings in NY on 25 September and 6 May - Intermediary meetings in Jakarta, Liberia and London - Report to be delivered to the SG | May 2013 |
| SG’s report to the 2013 GA | June 2012 | - DESA and SG’s office | - Final report to the GA informed by all the above mentioned initiatives | September 2013 |
| - Inter-governmental process |  |  |  |  |
| Working Group on SDGs | September 2012 | - UN Conference on Sustainable Development (Rio+20) agreed to establish an ‘inclusive and transparent’ intergovernmental process on SDGs and to establish the working group before the 67th Session of the GA - 30 representatives nominated by Member States from 5 UN regional groups - Methods of work, involvement of stakeholders, and expertise from the UN system to be decided by the WG - The SG to establish an inter-agency technical support team to serve as the Secretariat | - A report to the UNGA containing a proposal for sustainable development goals and appropriate action | September 2013 |

Table 2

| UNDG-led national consultations in 50 countries |  |  |  |  |
| --- | --- | --- | --- | --- |
| Africa | Latin America and the Caribbean | Arab States | Europe | Asia & Pacific |
| Angola Burkina Faso CAR DRC Ethiopia Ghana Kenya Mali Malawi Mauritius Mozambique Niger Nigeria Senegal South Africa Tanzania Togo Uganda Zambia | Brazil Bolivia Costa Rica Colombia El Salvador Honduras Peru Santa Lucia Haiti | Djibouti Jordan Egypt Sudan Morocco Algeria | Armenia Bosnia H Kazakhstan Moldova Tajikistan Turkey | Pakistan Bangladesh India Indonesia Timor-Leste China Lao PDR PNG Solomon Islands Viet Nam |

Table 3

| 9 global thematic consultations |  |  |  |
| --- | --- | --- | --- |
|  | Lead UN Agencies | Events | Donor |
| Growth and Employment | ILO, UNCTAD, UNDP | Tokyo, 15-16 May 2012 | Japan |
| Inequalities | UNICEF, UN Women, ILO | Global consultation in Feb/March 2013, Denmark | Denmark |
| Education | UNESCO, UNICEF | TBD | Canada |
| Environmental Sustainability | UNDP, UNEP | TBD |  |
| Food Security and Nutrition | FAO, WFO | TBD |  |
| Governance | UNDP, OHCHR | Global Consultation in Jan/Feb 2013, South Africa | Germany |
| Conflict and Fragility | UNDP | TBD |  |
| Population Dynamics | UNFPA, UN Habitat | TBD |  |
| Health | WHO, UNAIDS, UNICEF | Global Consultation in Jan/Feb 2013, Botswana | Sweden |