## Approach 1
GLO/19/53/EUR - SC 190731 | Improving synergies between social protection and public finance management
Work plan cross-country component of Approach 1
Outcome 1 |  | To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10.
Output | List of activities | Annual target/s |  |  |  | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
|  | 2020 | 2021 | 2022 | 2023 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Output 1.1 (Result 1.2 of the logframe): Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations. | Activity 1.1: Research on multiplier effects and coordination of other research activities | Annual target/s 2021: backstopping of 5 action research; Annual target/s 2022: backstopping of 5 action research; Annual target/s 2023: 1 research study with external validity |  | ILO | UNICEF, GCSPF
| Activity 1.2: Backstopping analytical work and tool applications, in particular on fiscal space | Annual target/s 2021: backstopping of 4 tool applications or analytical work; Annual target/s 2022: backstopping of 4 tool applications or analytical work |  | ILO | UNICEF, GCSPF
| Activity 1.3: Further development of the EU SPaN Guidance Package | Annual target/s 2023: Development of SPaN guidance package or other nexus tools |  | ILO | UNICEF
| Activity 1.4: Refining of ISPA tools, TRANSFORM and ILO good practice guides | Annual target/s 2023: Min. 3 tools refined |  | ILO | UNICEF, GCSPF
| Activity 1.5: Support to regional and global meetings/workshops/conferences | Annual target/s 2021: Min. 5 events; Annual target/s 2022: Min. 5 events |  | ILO | UNICEF, GCSPF
| Activity 1.7: Communication and visibility | Annual target/s 2020: See communication plan indicators and targets |  | ILO | UNICEF, GCSPF, Steering committee
| Activity 1.8: Overall management of the Action, including monitoring and final evaluation | Annual target/s 2020: 1 inception report; Annual target/s 2021: 1 financial and narrative progress report 1 evaluatbility report; Annual target/s 2022: 1 financial and narrative progress report; Annual target/s 2023: 1 final financial and narrative report 1 final evaluation |  | ILO | UNICEF, GCSPF
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | 2.1 Training and capacity building | Annual target/s 2021: Min. 3 webinars or trainings; Annual target/s 2022: Min. 3 webinars or trainings |  | ILO | UNICEF, GCSPF, country teams, EU Delegations

## Approach 2
GLO/19/53/EUR | Improving synergies between social protection and public finance management
Work plan Approach 2
Outcome 1 |  | A minimum of 10 countries receive on-demand high quality, gender-responsive, disability-inclusive technical advisory services that are relevant and produce technically, financially and politically feasible recommendations on how to improve the national social protection system, programmes or delivery mechanisms
Output | List of activities | Annual target/s |  |  |  | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | Executing agency | Implementing partner/s involved
|  | 2020 | 2021 | 2022 | 2023 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD)
Outputs 1.1 Selection of 10 countries through a minimum of two call for proposals, based on criteria of relevance and sound operations | 1.1.1 Launch and disseminate the calls for proposals, receive the proposals | Annual target/s 2020: min. 15 requests received; Annual target/s 2021: min. 15 requests received |  | ILO | EU Delegation, Government
| 1.1.2 Organise the selection of requests through the operational steering committee | Annual target/s 2020: min. 5 requests approved; Annual target/s 2021: min. 5 requests approved |  | ILO | Operational Committee
| 1.1.3 Support services to develop the proposals | Annual target/s 2020: min. 5 of requests supported; Annual target/s 2021: min. 10 of requests supported |  | ILO | Government, social partners, CSO
Output 1.2 : Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | 1.2.1. Set up a multidisciplinary technical team to deliver the services in line with the request | Annual target/s 2020: Composition of the team; Annual target/s 2021: min. 3 of countries receiving services and backstopping missions; Annual target/s 2022: min. 3 of countries receiving services and backstopping missions; Annual target/s 2023: min. 3 of countries receiving services and backstopping missions |  | ILO | Experts and academias
| 1.2.2. Establish a process for participatory implementation of the advisory services , to the extent possible drawing on existing consultation or dialogue structures | Annual target/s 2020: TDR of the participatory process; Annual target/s 2021: min. 7 countries with a process for participatory implementation |  | ILO | EU Delegation, Governments, UN agencies
| 1.2.3. Create evidence base to address the request, including information and data on gender, disability, shock-responsiveness, costs, financing and digitalization | Annual target/s 2021: min. 3 countries with social protection data and information; Annual target/s 2022: min. 5 countries with social protection data and information |  | ILO | Goverrnments, including National Statistical agencies, UN agencies
| 1.2.4. Identify different scenarios to improve the social protection system, programme or delivery mechanisms (in line with the request) - scenarios are designed ensuring coherence and coordination within the social protection system across sectors and administrative levels and beyond social protection sector and with related policy areas such as employment policies. | Annual target/s 2021: min. 3 of countries with identified scenarios; Annual target/s 2022: min. 5 of countries with identified scenarios |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.5. Analyse the identified scenarios regarding their cost, financing sources, political economy implications, institutional capacity, technical feasibility and taking into consideration implications regarding their effects on gender, disability, shock-responsiveness and potential of using new technologies in their implementation | Annual target/s 2021: min. 3 scenarios that are costed per country; Annual target/s 2022: min. 3 scenarios that are costed per country |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.6. Disseminate findings so that national stakeholders, including social partners are well-informed about social protection needs and possible actions to address them | Annual target/s 2021: min. 1 dissemination and advocacy events (per country); Annual target/s 2022: nb. of dissemination and advocacy events (per country); Annual target/s 2023: nb. of dissemination and advocacy events (per country) |  | ILO | EU Delegation, Governments, social partners, CSO, UN agencies
| 1.2.7. Summarize delivered technical advisory services in an outcome document (country report, strategy, roadmap, draft policy, etc.) | Annual target/s 2022: min. 1 outcome document at country level; Annual target/s 2023: min. 1 outcome document at country level |  | ILO | Operational Committee, Governments
| 1.2.8. Establish a framework and tools for monitoring progress in implementing the project outcomes (country report, strategy, roadmap, draft policy, etc.) and in extending social protection | Annual target/s 2020: min. 3 countries with a monitoring framework; Annual target/s 2021: min.8 of countries with a monitoring framework; Annual target/s 2023: min.8 of countries with a monitoring framework completed |  | ILO | Operational Committee, National statistical agencies

## Angola
| GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Angola
Plano de Trabalho do Programa "Melhorar as Sinergias entre a Protecção Social e a Gestão das Finanças Publicas" |  | Agência e modalidades de implementação | Parceiros de implementação | 2020 | [6 empty] | 2021 | [10 empty] | 2022 | [11 empty] | Metas anuais |  |  | Linha de base
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q2 | Q4 | Q1 | Q2 | Q4 | Q2 | Q2 | Q4 | Q3 | Q2 | Q4 | Q4 | Q2 | Q4 | Q1 | Q2 | Q4 | Q2 | Q3 | Q4 | Q3 | Q2 | Q4 | Q4 | Q2 | Q4
[34 empty] | 2020 | 2021 | 2022
PRODUTO 1. Uma Política de Acção Social é implementada e custeada | [33 empty] | "*Relatório de diagnóstico e custoeamento das opções, * Opções de financiamento da proteção social disponível" | * 1 Relatório de diagnóstico e estimativa de custos |  | 0
1.1 | Definição do Plano de Acção da Estratégia de Implementação da Política Nacional de Acção Social | UNICEF & OIT
1.1.1 | Realizar um diagnóstico do sistema de Protecção Social angolano, utilizando a ferramenta CODI-ISPA para avaliar os esquemas e programas existentes, a estrutura legal, a população coberta, o conteúdo e o nível de benefícios, lacunas, mecanismos de coordenação, entre outros. | Utilização da metodologia do Diálogo Nacional Baseado na Avaliação da OIT, consultoria internacional, sinergias com o projecto ACTION PORTUGAL na componente Protecção Social Contributiva | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO SAUDE MINISTERIO DA EDUCAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT INSS OCS FMI BM
1.1.2 | Identificar as diferentes acções estratégicas no âmbito da implementação da Estratégia de Operacionalização da Politica de Acção Social em direção a uma cobertura universal e melhorar a eficiência e eficácia dos gastos com proteção social
1.1.3 | Identificar os diferentes cenários para as diferentes acções estratégicas e as diferentes abordagens para a sua implementação. (fases / calendário / cobertura regional etc.)
1.2 | Custeamento das acções estratégicas | OIT | UNICEF
1.2.1 | Formular a abordagem metodológica e as suposições do modelo de custeamento das opções estratégicas | Trabalho técnico interno da OIT | MASFAMU MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT OCS FMI BM
1.2.2 | Recolher dados macroeconomicos, financeiros, da despesa e socio-economicos relevantes e estimar os parâmetros-chave
1.2.3 | Elaborar o documento de custeamento das diferentes opções estratégicas
1.2.4 | Estimar as lacunas de financiamento na proteção social para atingir a meta do ODS
1.2.5 | Identificar e avaliar as opções de financiamento das acções estratégicas com base na viabilidade económica, fiscal, social e política do país
1.3 | Dialogo Social e Advocacia | OIT | OIT
1.3.1 | Organizar consultas nacionais para concertação, validação, monitorização das acções estratégicas definidas, as opções de implementação e financiamento | Dialogo Social e trabalho técnico interno da OIT, consultoria nacional para a advocacia | MASFAMU MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT OCS FMI BM
1.3.2 | Preparar um documento: Plano de Acção da Estratégia de Implementação da Política Nacional de Acção Social com as acções estratégicas, seu custeamento e modalidades de financiamento resultantes do processo de validação ao nível do dialogo social para validação e aprovação
1.3.3 | Preparar uma estratégia de advocacia do documento Plano de Acção da Estratégia de Implementação da Política Nacional de Acção Social resultantes do processo de validação ao nível do dialogo social para validação e aprovação
PRODUTO 2. Um modelo de orçamentação baseado no desempenho em instituições de proteção social é implementado |  | UNICEF & OIT | UNICEF & OIT | [30 empty] | * TdR do grupo de trabalho interministerial para o piloto de Orçamentação baseado no desempenho é definida *O ciclo de orçamentação é sistematizado | *Uma nota metodológica do Modelo de orçamentação baseado no desempenho está disponível * Um plano de acção e um manual sobre Modelo de orçamentação baseado no desempenho estão disponíveis | Formação sobre o Modelo de orçamentação baseado no desempenho | 0
2.1 | Criação e operacionalização de um grupo de trabalho inter-ministerial | UNICEF | UNICEF
2.1.1 | Criação de um grupo de trabalho interministerial para o piloto de Orçamentação Baseado no Desempenho integrando técnicos do Ministério das Finanças, Ministério da Economia e Planeamento e as instituições que regulam o sistema de Protecção Social em Angola |  | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS INSS
2.1.2 | Elaborar um programa de formação baseado nos objectivos do Grupo de Trabalho
2.2 | Modelo de orçamentação baseado no desempenho | UNICEF | UNICEF
2.2.1 | Sistematizar a avaliação do ciclo de orçamentação de acordo com os padrões internacionais, usando o processo PEFA em curso e as quatro fases principais em que o ciclo é dividido |  | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS INSS
2.2.2 | Desenvolver uma nota metodológica e conceitual sobre os fundamentos teóricos da orçamentação baseada no desempenho, incluindo os seus componentes
2.2.3 | Preparar um manual sobre como implementar um orçamento baseado no desempenho no setor de proteção social
2.2.4 | Formular um Plano de Ação com teste piloto incluído para lançar um orçamento baseado no desempenho em uma amostra de instituições sociais
PRODUTO 3: A coordenação do sistema de proteção social é reforçada |  | UNICEF & OIT | UNICEF & OIT | [30 empty] | *Relatório de mapeamento dos mecanismos de coordenação existentes * A arquitectura do Comitê de Coordenação Multissetorial é proposta *Documentos normativos para o Comitê de Coordenação | *É criado o Comitê de Coordenação Nacional * 2 reuniões do Comitê de Coordenação | *É criado o Comitê de Coordenação Nacional * 2 reuniões do Comitê de Coordenação | 0
3.1 | Operacionalização dos Comités Nacionais de Proteção Social | UNICEF | UNICEF
3.1.1 | Realizar um mapeamento dos mecanismos de coordenação em proteção social e a sua avaliação através de uma análise SWOT ou metodologia similar | Trabalho técnico da UNICEF com apoio de um consultoria | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO SAUDE MINISTERIO DA EDUCAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT INSS OCS FMI BM
3.1.2 | Propor uma arquitetura de fortalecimento da coordenação entre os diferentes Conselhos incluindo os mecanismos de articulação entre instituições e programas de proteção social, incluindo o programa para ex-combatentes | Trabalho técnico da UNICEF
3.1.3 | Desenvolver as ferramentas e procedimentos operacionais para a ligação entre os conselhos | Trabalho técnico da UNICEF
3.1.4 | Preparar um plano de comunicação e advocacia que fortaleca dos mecanismos de coordenação | Dialogo Social e trabalho técnico interno da OIT
3.1.5 | Apoio técnico para o funcionamento dos Comites Nacionais de Proteção Social, como o apoio à promoção e facilitação do dialogo social, diálogos interministeriais, formações, troca de experiências, facilitação de sessões técnicas especializadas, entre outros. | Dialogo Social e trabalho técnico interno da OIT
PRODUTO 4. Instituições públicas com melhores capacidades para melhorar o orçamentação e a prestação de serviços de Protecção Social |  | UNICEF & OIT | UNICEF & OIT | [30 empty] | *15 funcionários formadas em orçamentação baseada no desempenho *20 funcionários devidamente formados em estratégias para melhorar a capacidade de prestação de serviços * 10 funcionários formados em estatísticas de proteção social para fins de política | *20 funcionários formadas em orçamentação baseada no desempenho *30 funcionários devidamente formados em estratégias para melhorar a capacidade de prestação de serviços * 10 funcionários formados em estatísticas de proteção social para fins de política | *15 funcionários formadas em orçamentação baseada no desempenho *50 funcionários devidamente formados em estratégias para melhorar a capacidade de prestação de serviços * 10 funcionários formados em estatísticas de proteção social para fins de política | 0
4.1 | Reforço das capacidades nas àreas de planificação, orçamentação e controle de gastos | OIT | OIT
4.1.1 | Realizar um diagnóstico das instituições e dos seus recursos humanos para avaliar a capacidade institucional nas àreas de planificação, orcamentação e controle de gastos | trabalho técnico interno da OIT | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT INSS OCS
4.1.2 | Preparar um plano de capacitação institucional que respondas às necessidades identificadas no diagnóstico (4.1.1)
4.2 | Reforço das capacidades institucionais na gestão de programas de Proteção Social | UNICEF & OIT
4.2.1 | Apoio tecnico e formação na implementação dos programas que visam a extensão da segurança social contributiva para trabalhadores da economia informal e trabalhadores de baixos rendimentos e rural | Trabalho técnico e formativo da OIT e em parceria com o projecto ACTION Portugal | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT INSS OCS
4.2.2 | Apoio técnico e formação na implementação dos programas e serviços sociais no âmbito da Protecção Social de Base | Trabalho técnico e formativo da UNICEF
4.2.3 | Formação para a Comissão da OIT em matérias ligadas à extensão da cobertura da protecção Social em Angola e o estabelecimento de um Piso de Protecção Social em Angola | Trabalho técnico e formativo da OIT em parceria com o projecto ACTION
4.3 | Avaliar os efeitos da capacitação institucional relizada pelo projecto | UNICEF & OIT
| Realizar um no final da implementação do projecto para avaliar os efeitos da capacitação institucional na gestão, planaificação e financiamento de programas de Protecção Social | Consultoria independente | MASFAMU MAPTSS MINISTERIO PLANIFICAÇÃO MINISTERIO FINANCAS COMISSÃO DA OIT INSS OCS

## Burkina Faso
| GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Burkina Faso
Workplan under discussion with the Government
Outcome 1 | Enhanced conception, coordination, tracking and financing of gender-sensitive and inclusive schemes and programmes, of the social protection system of Burkina Faso towards SDGs 1 and 10
Output | List of activities Plan de travail initial |  | 2021 | [11 empty] | Annual target/s
|  | responsable | janv | fev | mar | avr | mai | jui | jul | aou | sep | oct | nov | dec | Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023)
Inception phase | [14 empty] | Prodoc
Outputs 1.1 An overall review of the national social protection system using ISPA tools allows stakeholders adopting consensual recommendations for improving the social protection system in Burkina Faso and provide evidences for the adoption of the new PNPS | Activitie1.1.1 Provide technical support the SP-CNPS and develop tools to reinforce the multisector coordination and facilitate a national dialogue through technical committees and working groups for the formulation of the social protection floor guaranties | [13 empty] | - Etude assurance chômage - Etude simulation cash transferts
| Activité 1.1.2 Implement capacity building activities in order to secure the active participation of all actors of the social protection sector in the national dialogue for the overall review and adoption of recommendations for strengthening the system | [14 empty] | 1 workshop | bar: 2021 avr
BIT | bar: 2021 avr; 2021 jui; 2021 sep; 2021 dec
| Activité 1.1.3 Conduct in consultation with the stakeholders, and referring to ISPA tools, an inventory (coverage, financing and architecture), an analysis of the performance and gaps of contributory and non-contributory social protection programmes and measures and assess the adequacy of internal or external financing to meet the social protection | [14 empty] | 1 review document | bar: 2021 mar
| Activité 1.1.4 Provide technical support to the SP-CNPS for the development of recommendations and reforms to support the coordinated and effective implementation of the PNPS, within the framework of a participatory and inclusive national dialogue | [14 empty] | 4 national dialogue sessions | bar: 2021 jul to 2021 oct
Activité 1.1.5 Support the SP-CNPS for the integration of reforms in updating PNPS and the drafting of a progressive implementation strategy | bar: 2021 jul to 2021 dec
Output 1.2 : Burkina Faso has a sustainable and adequate financing strategy of its national system of social protection | Activité 1.2.1 Conduct a social protection expenditures review, including external financing. This review will take in consideration aspects related to gender, children, young people, people with disabilities as well as the impact of shocks on vulnerable populations | [13 empty] | Etude de revue de dépenses publiques (UNICEF/fds Suède) | 1 review of public spending on social protection
| Activité 1.2.2 Assess the costs of the guaranties of a national social protection floor and recommendations for strengthening the social protection system emanating from the review of the system | [14 empty] | 1 costing (RAP) of recommendations | bar: 2021 jul to 2021 dec
| Activité 1.2.3 Identify opportunities for mobilising sustainable resources within the available budgetary space | [13 empty] | etude stratégie financement unicef | 1 document analysing medium- and long-term funding sources
| Activité 1.2.4 Provide technical and methodological support to the SP-CNPS and the Ministry of Finance in adopting options for sustainable financing in the national social protection system | [15 empty] | A medium-term financing framework document for the social protection sectore
| Activité 1.2.5 Implement training activities to reinforce capacities of government institutions and technical ministries, social partners and other actors on social protection (ILO and UNICEF guides and methodologies) in order to take informed decisions regarding the social protection budget | [14 empty] | 1 capacity building workshop
| Activité 1.2.6 Prepare the argument and to undertake advocacy actions for increased social protection public financing | [15 empty] | 1 capitalisation document
Outcome 2 | To support institutional and technical actors in the implementation of universal health coverage and strengthening of local mechanisms for the extension of social protection schemes and programmes at the municipal level, adapted in particular to the needs of persons in situations of temporary and lasting vulnerability and fragility, including displaced persons
Output | List of activities |  | 2021 janv: 2021 | Annual target/s
|  | responsable | janv | fev | mar | avr | mai | jui | jul | aou | sep | oct | nov | dec | Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023)
Output 2.1 Strengthened capacities of institutional and technical actors and tools to monitor the national social protection system | Activité 2.1.1 Carry out a mapping of the social protection statistical system (sources of production, collection and analysis of information) | [13 empty] | Etude indicateur SMART suivi PNPS UNICEF SP/CNPS | 1 mapping of data sources
| Activité 2.1.2 Provide technical support to the development of a framework for monitoring and evaluating progress in the social protection sector (ILO SSI, social insurance performance indicators, and SDG indicators) | [14 empty] | 1 data compilation tool | bar: 2021 mar to 2021 avr
| Activité 2.1.3 Strengthen stakeholders' capacities to monitor and evaluate social protection programmes, taking into account gender aspects and non-discrimination of people living with disabilities | [14 empty] | 1 capacity building workshop
Output 2.2 Strengthened technical capacities of the schemes to ensure the quality and sustainability of minimum guarantees of social protection | Activité 2.2.1 Provide technical assistance to the CNAMU, the mutualist movement and social partners for the effective implementation of the RAMU and its extension to the formal and informal sectors and to the rural sector | [15 empty] | 1 strategy for the implementation and expansion of the RAMU
| Activité 2.2.2 In pilot communes, design and test mechanisms for counselling beneficiaries, channelling central programmes to the local level, collecting data, targeting and registering vulnerable populations in the communal social services | [15 empty] | 15 pilot municipalities have targeting mechanisms | bar: 2021 avr to 2021 dec
| Activité 2.2.3 Provide technical support to the harmonization and strengthening of targeting mechanisms for poor and vulnerable households | [15 empty] | 15 pilot municipalities have targeting mechanisms | bar: 2021 avr to 2021 dec
| Activité 2.2.4 Capitalize on these pilot experiences in order to integrate and scale up good practices in the revision of the PNPS in 2022 | [15 empty] | 1 capitalisation document
Outcome 3 | Shock-responsive programmes, tailored to the needs of people in situations of vulnerability, fragility and insecurity, including displaced persons, are integrated into the national social protection system, in coherence and synergy with social insurance schemes, and social assistance and social safety net programmes
Output | List of activities |  | 2021 janv: 2021 | Annual target/s
|  | responsable | janv | fev | mar | avr | mai | jui | jul | aou | sep | oct | nov | dec | Année 1 (oct 2019-déc 2020) | Année 2 (jan 2021-déc 2021) | Année 3 (jan 2022-mai 2023)
Output 3.1 Strengthened capacities of mechanisms and programmes to ensure the construction of a social protection system that can also meet social protection needs in the context of crisis and fragility in Burkina Faso | Activité 3.1.1 Support consultation between social protection actors and those of the humanitarian country team and humanitarian clusters to strengthen the coherence of humanitarian responses with social protection programmes, and propose steps for their integration into the social protection system | [15 empty] | a national approach nexus humanitarian development
| Activité 3.1.2 Provide technical support, where possible, to the identification, registration and integration of beneficiaries of humanitarian responses and displaced people in the single social registry, the communal social services and the universal health scheme | [15 empty] | 1 system for registering and caring for shock victims
| Activité 3.1.3 Provide technical support to the integration of data (on coverage, benefits, financing, etc.) of humanitarian responses into the national social protection information system | [15 empty] | intégration des réponses integration of humanitarian responses into the data compilation tool
| Activité 3.1.4 Document good practices in linking social protection and humanitarian responsesDocumenter les bonnes pratiques du lien entre protection sociale et réponses humanitaires | [15 empty] | 1 document capitalizing on good practices

## Cambodia
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Cambodia
Outcome 1 | Improved design and monitoring of SP programs and increased use of evidence on SP impact system contributes to increased coverage of social protection
Output | List of activities | [11 empty] | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | 2020 | 2021 | 2022
Output 1.1. Evidence-based frameworks and tools to guide, monitor and evaluate the implementation of the National Social Protection Policy Framework are developed and implemented | 1.1.1 Technical assistance to selected budget entities in implementing NSPC M&E Framework and linking programme M&E frameworks with RB budgeting. | [11 empty] | UNICEF, (ILO) | GS-NSPC | - 1 research on role of SP on economic development finalized -M&E framework for CT programme (women and children) drafted | M&E framework for CT programme (women and children) drafted | - Actuarial Valuation for 3 branches of NSSF finalized - At least a policy revision initiated based on the actuarial revision recommendations | bar: Q2 to Q2
| 1.1.2 - Provide technical assistance and financial support to implement a gender-sensitive analysis of the financial situation (actuarial review) of the NSSF Schemes (actuarial review) | [11 empty] | ILO (OXFAM) | NSSF, GS-NSPC | bar: Q3 to Q4
| 1.1.3 - Develop research on the potential role of expanded Social Protection for Cambodia Socio-economic development | [11 empty] | ILO (OXFAM) | GS-NSPC | bar: Q2 to Q4
Output 1.2 –Feasibility studies and tools for expansion of the social protection schemes are developed | 1.2.1 Technical assistance to design and development of gender- and -child -sensitive integrated / family package of social assistance programmes (cash transfer for pregnant women and children, cash scholarships, disability allowance, and social pension for elderly) and administrative models /institutional arrangements for their delivery | [11 empty] | UNICEF, (ILO, OXFAM) | GS-NSPC, MOSVY | Family Package options paper and costed programme document developed and validated 50 districts with PwD identification system | 57 districts with PwD identification system | 50 Districts with PwD163,181 identification system All provinces have trained staff to support identification of PwD Revised Disability Allowance Sub-decree Costed Disability Allowance Programme | bar: Q2 to Q4
| 1.2.2 Technical assistance and financial support to strengthen the delivery of the disability allowance programme (identification, data collection and costing) | [11 empty] | UNICEF | MOSVY | bar: Q2 to Q4
Output 1.3. The CSO-Trade Union Network can engage effectively with decision makers for improvement of the design and monitoring of selected SP programs | 1.3.1 Capacity strengthening of the CSO-TU Network on gender-sensitive and results-based budgeting, design and monitoring of selected SP programmes. | [11 empty] | OXFAM | CSO-TU Network | 1 Common recommendation produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 1 recommendation produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF | 2 Common recommendations produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 2 recommendations produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF x gender sensitive policy improvements proposed | 5 Common recommendations produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 recommendations produced by the CSO-TU Network, including gender sensitive policy improvements, accepted by the relevant government institution NSPC and NSSF | bar: Q2 to Q1
| 1.3.2 Impact and needs analysis at the level of constituents of the CSO-TU Network regarding selected SP programs, including development of recommendations for improvement of budgeting, design and monitoring. | [11 empty] | OXFAM | CSO-TU Network | bar: Q3 to Q2
| 1.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for improvement of budgeting, design and monitoring of selected SP programs. | [11 empty] | OXFAM (ILO) | CSO-TU Network | bar: Q4 to Q4
| 1.3.4 Extract learning from the CSO-TU engagement on selected SP programs and share with relevant stakeholders, including GCSPF . | [11 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2
Outcome 2 | Social Protection institutions enhance their planning, budgeting and M&E capacities in alignment with the Public Finance Management Reform Programme
Output | List of activities | [11 empty] | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | 2020 | 2021 | 2020
Output 2.1 -Tools and Knowledge in place for improved planning, budgeting and tracking of social protection expenditures including a consistent mechanism for compilation of revenues and expenditures | 2.1.1 – Technical assistance to review implementation of the functional classification of social protection schemes by selected ministries implementing SP programmes | [11 empty] | ILO (UNICEF) | GS-NSPC; MEF | - 1 report integrating a list of social protection programs, coverage and costs, including a note on information gaps and respective briefing - 1 assessment on links among the SP M&E framework and the results structure/KPIs and budgets of SP agencies/budget entities - Assessment of existing budget formulation, execution and reporting documents and their alignment with RB and PB for 9 budget owners implementing social assistance (including at SNA level) | - 1 report integrating a list of social protection programs, coverage and costs, including a note on information gaps and respective briefing - Expenditure data base developed and the possibilities for extension into SP database explored (link to activity 2.1.2) - implemenation of functional classification of social protection schemes improved by at least 1 line Ministry '- 120 officials from MoSVY and DoSVYs, MoP and MoI trained on RB Budget formulation - Guidelines on improved budget process and hands-on training implemented | - financial review of the SP in Cambodia finalized including a list of social protection programs, coverage and costs - recommendations produced under the SP Financial Review incorporated into the revised SP Policy Framework revised Action Plan | bar: Q3 to Q2; Q1 to Q2
| 2.1.2 – Technical assistance to develop social protection tracking expenditure database for MoSVY-supported social assistance programmes | [11 empty] | UNICEF | GS-NSPC, MOSVY | bar: Q1 to Q4
| 2.1.3 Provide technical assistance and support to building the capacities of the selected line ministries and institutions responsible for social assistance to develop adequate/high-quality results-based frameworks in support of programme-based budget formulation, execution and reporting | [11 empty] | UNICEF (ILO = OXFAM) | GS-NSPC, MEF, MOSVY | bar: Q2 to Q4
| 2.1.4 – Technical assistance to implement a comprehensive gender-sensitive Financial Review of Social Protection in Cambodia as input to MTR of SPPF | [11 empty] | ILO (UNICEF) (OXFAM) | GS-NSPC | bar: Q2 to Q2
Output 2.2 – Social budget forecasting system established | 2.2.1 - Provide capacity building (training and coaching) on social budgeting forecasting model to MEF departments | [11 empty] | ILO | GS-NSPC; MEF |  | - a social budgeting model developed and operational - social budgeting model results used to inform the MTR of SPPF | - social budgeting model incorporated within MEF planning tools | bar: Q3 to Q4
| 2.2.2 Provide technical assistance and jointly develop tools to develop gender-sensitive social budgeting forecasting model for Cambodia | [11 empty] | ILO | GS-NSPC; MEF | bar: Q1 to Q4
Output 2.3 – The CSO-TU Network can engage effec-tively with decision makers for more fiscal space to increase the coverage of the informal economy workers under the NSPPF, especially women workers | 2.3.1 Capacity strengthening of the CSO-TU Network on overall PFM and financing of SP systems, including GRB | [11 empty] | OXFAM (ILO) | CSO-TU Network | 1 of common recommendation for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 1 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | 2 of common recommendations for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 2 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | 5 of common recommendations for IEW produced by the CSO-TU Network and submitted to the relevant government institution NSPC and NSSF 3 of common recommendations for IEW produced by the CSO-TU Network and accepted by the relevant government institution NSPC and NSSF | bar: Q2 to Q1
| 2.3.2 Needs and contributory capacity assessment of constituents of the CSO-TU Network, in particular of female informal economy workers, including development of recommendations for increased coverage | [11 empty] | OXFAM | CSO-TU Network | bar: Q3 to Q2
| 2.3.3 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased fiscal space for better coverage of informal economy workers, women in particular. | [11 empty] | OXFAM, (ILO) | CSO-TU Network | bar: Q4 to Q4
| 2.3.4 Extract learning and lessons from the CSO-TU engagement on increasing the coverage for informal economy workers and share with relevant stakeholders, including GCSPF | [11 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2
Outcome 3 | Service providers at sub-national level (SNAs) are better able to implement social protection services
Output | List of activities | [11 empty] | Agencies involved | Implementing partner/s involved | Annual targets
|  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | 2020 | 2021 | 2022
Output 3.1- Service providers have improved skills to deliver social protection services | 3.1.1 Technical assistance to develop training curriculum for sub-national administrations (SNAs) on social protection, with focus on disability allowance | [11 empty] | UNICEF (OXFAM) | MOSVY | Training curriculum | 140 key government officials and 140 sub-national officials trained Study on knowledge-sharing implemented Study on roles and existing mechanisms for SA at SNA level implemented | bar: Q3 to Q1
| 3.1.2 Provide financial support for implementation of a child and gender-sensitive training program on social assistance for national and subnational government officials (Focus on Provincial/Capital levels) | [11 empty] | UNICEF, (ILO, OXFAM) | MOSVY | bar: Q4 to Q4
| 3.1.3 Technical assistance to assess existing knowledge sharing and information dissemination channels and develop strategies for capacity building of SNAs | [11 empty] | UNICEF, (ILO, OXFAM) | MOSVY,MOI | bar: Q4 to Q1
| 3.1.4 Research (Assessment) of roles and existing mechanism at SNA level in implementing SA programmes | [11 empty] | UNICEF (OXFAM) | MOSVY
Output 3.2 - Increased capacity and engagement of the CSO-TU Network to engage in social accountability mechanisms related to SP delivery at subnational level | 3.2.1 Capacity strengthening of of the CSO-TU Network on the social accountability framework and how this applies to SP delivery at subnational level. | [11 empty] | OXFAM | CSO-TU Network | 1 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 1 of common recommendations on gender sensitive social accountability mechanisms accepted. | 2 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 2 of common recommendations on gender sensitive social accountability mechanisms accepted. | 3 of common recommendations on gender sensitive social accountability mechanisms produced by the CSO-TU Network and submitted to the relevant institutions. 3 of common recommendations on gender sensitive social accountability mechanisms accepted. | bar: Q2 to Q1
| 3.2.2 Advocacy by representatives of the CSO-TU Network to promote recommendations for increased social accountability in SP delivery at subnational level | [11 empty] | Oxfam | CSO-TU Network | bar: Q1 to Q2
| 3.2.3 Awareness building amongst constituents regarding social accountability mechanisms they can make use of. | [11 empty] | OXFAM | CSO-TU Network | bar: Q2 to Q4
| 3.2.4 Extract learning from the CSO-TU engagement on the use of social accountability mechanisms within SP delivery. | [11 empty] | OXFAM | CSO-TU Network, GCSPF | bar: Q1; Q2

## Ethiopia
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Ethiopia
ILO/UNICEF Joint Work Plan: 2020-2023
Outcome: Improving the social protection system for Ethiopia through a sustainable financing strategy
Output | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved | Annual target/s
|  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Total Cost (USD) |  |  | Year 1 (Oct 2019-Dec 2020) | Year 2 (Jan 2021-Dec 2021) | Year 3 (Jan 2022-May 2023)
Output 1 Financing Strategy for Social Protection in Ethiopia | 1.1. Building an evidence base for financing non-contributory social protection programmes (such as vulnerability analysis on COVID-19, an investment case for social protection and fiscal space analysis) | [13 empty] | 426110 | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH | Vulnerability analysis on COVID-19 is done | Draft Fiscal space analysis and investment case produced and consultations with stakeholders is held | - Final fiscal space analysis and investment case documents are completed | bar: 2020 Q2 to 2022 Q4
| 1.2. Technical/Expertise contribution to actuarial valuation (contributory) | [14 empty] | ILO (lead), UNICEF | POESSA, PSSA |  | - Draft of the actuarial evaluation submitted - Consultations made with key stakeholders | - final Actuarial evaluation document submitted to PSSA and POESSA | bar: 2020 Q4 to 2022 Q3
| 1.3. Financing strategy (including the research component, policy paper, consultations and validation) | [14 empty] | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH |  |  | - Final financing strategy produced | bar: 2021 Q2 to 2023 Q2
| 1.4. Awareness raising, workshops, and policy advocacy related to financing social protection | [14 empty] | UNICEF (lead), ILO | MoLSA, MoF, MoA, MoH |  | - 1 training related to financing social protection | - 1 knowledge exchange forum - - 1 national conference on PFM &SP conducted | bar: 2021 Q1 to 2023 Q2
Output 2 Extending social security to informal economy workers and supporting labour legislation related to social protection | 2.1 Technical assessment to extend social security to informal sector workers including COVID-19 social protection responses | [13 empty] | 200000 | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA |  | - Draft final of the analytical study on extending SP to informal economy workers submitted | - Final version of the analytical study on extending SP to informal economy workers submitted | bar: 2020 Q3 to 2022 Q3
| 2. 2. Awareness raising through media and/or workshops (Federal/Regional) for consensus building on the extension of social security to informal economy workers including COVID-19 social protection responsive programmes | [14 empty] | ILO (lead), UNICEF | MoLSA POESSA, FeMSEDA | -Training and awareness needs assessments done at Federal and selected Regions level. | -1 awareness raising training/ workshops organised at Federal and Regional levels on extension of SP to informal economy workers. | - 1 awareness raising training/workshops organised at Federal and Regional levels on extension of SP to informal economy workers. | bar: 2020 Q3 to 2020 Q4; 2021 Q3 to 2021 Q4; 2022 Q2; 2022 Q4 to 2023 Q1
| 2.3 Tripartite consultation among government, workers’ and employers’ representatives on minimum wage and related social protection schemes | [14 empty] | ILO (lead), UNICEF | MoLSA, CETU, EEC |  | - 1st and 2nd round of tripartite consolations on minimum wage done with MoLSA, CETU and EEC aiming at establishing a wage board. | - 3rd and 4th round of tripartite consultations done with tripartite partners and the wage board aiming at drafting the minimum wage legislation. | bar: 2021 Q1; 2021 Q3; 2022 Q1 to 2022 Q2; 2023 Q1 to 2023 Q2
Output 3. Building the capacity of MoLSA to effectively monitor the social protection system. | 3.1 Support MoLSA and Addis Ababa BoLSA develop monitoring tools and processes to better implement and track social protection programming. | [13 empty] | 387175 | UNICEF (lead), ILO | MoLSA, Addis Ababa BoLSA | bar: 2020 Q2 to 2023 Q2
| 3.2 Increasing the capacity of MoLSA to facilitate the establishment of effective coordination mechanisms for social protection policy and strategy | [14 empty] | UNICEF, ILO | MoLSA, BoLSAs, MoA, FUJCFSA, | -MoLSA and key stakeholders consulted and agreement on cooridnation mechanisms and governance principles established | Social protection platform(s) recognised and formally established | Social protection platform(s) fully functional under MoLSA/BoLSA(s) management | bar: 2020 Q2 to 2023 Q2
| 3.2 Developing a knowledge management platform for inclusive social protection | [14 empty] | ILO, UNICEF | MoLSA, Consultant |  | Knowledge management tools (e.g. SSI) tested and functional | MoLSA/BoLSA(s) fully capacitated on use of knowledge management tools/platform | bar: 2020 Q3 to 2023 Q2
Total | [14 empty] | 817647

## Nepal
GLO/19/53/EUR - SC 190731 |  | Improving Synergies between social protection and public finance management
Country Project Workplan
Nepal
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output | Annual target/s |  |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT 1 : Increased capacity of GON and key stakeholders to develop resilient, inclusive national social protection policies, sustainable financing strategies and legal frameworks at Federal and Provincial levels. | 1. Draft Federal Policy document endorsed by key stakeholders | 1. National Social Protection Policy adopted by the government | 1. Action Plan to implement the National policies in place | 1. Action plan implemended | A1.1 Technical assistance to NPC to develop SP policy, including ensuring adequate and sustainable financing for social protection through an inclusive consultations and informed participation of stakeholders . 2. Report on the overall coverage and adequacy of SP system, in line with the World Social Protection Report 2020-22 | [14 empty] | UNICEF, ILO, Social Protection Task Team (SPTT) members | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2020 Q4 to 2021 Q4
|  |  | 2. Integrated M & E framework endorsed by the key stakeholders |  | 1) Desk review of relevant documents and drafting of a integrated policy framework (UNICEF); 2)Interministerial consultations on the zero draft ( UNICEF) 3)Consultatons with ILO constituents and compilations of inputs on the draft policy framework (ILO) 4) Consultations with civil society org and copilation of inputs (WSM) 5. Finalisation of draft policy framework (UNICEF) 6. Support to NPC in the process of Government's approval of the Policy | bar: 2022 Q1 to 2022 Q4
|  |  | 3. Draft Policy document endorsed by key stakeholders in P2 & P6 |  | .A1.2.Technical assistance to two Provincial Governments ( P6, P2) to formulate inclusive Provincial Social Protection Policy , regularly monitor the implementation of the policy agenda and backstop Municipalities in improving their SP services through effective monitoring and feedback. | [14 empty] | UNICEF, ILO | Local Government ( P2, P6 & selected Municipalities) & IT serice providers, Academicians | bar: 2022 Q1 to 2023 Q1
|  | 2. Provincial level officials trained, and SP context analysis conducted | 4. Provincial level M & E framework endorsed by key stakeholders in P2 and P6 |  | 1) SP context analysis in 2 Provinces (ILO) 2) Training to stakeholders for informed policy making (ILO) 3) Consultations for policy formulation (ILO/UNICEF) 4) Writing of policy document(UNICEF) 5) Sharing workshop on lessons learned with other 5 Provinces | bar: 2021 Q4 to 2023 Q1
Objective:To support government at different levels in implementing and monitoring gender sensitive and disability-inclusive social protection systems while ensuring financial sustainability.
Output | Annual target/s |  |  |  | List of activities | 2020 Q2: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023 | PUNO/s involved | Implementing partner/s involved
| 2020 | 2021 | 2022 | 2023 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
RESULT: 2 Government enabled to establish and operationalise a high-level social protection coordination, monitoring and evaluation mechanism at Federal level. | 1. Awareness raised among relevant policy makers on the need of high level coordination for SP policies, strategies & programmes |  | 1. Institutional framework for federal level coordination and monitoring of SP systems agreed by stakeholders. 2. TA to NPC designed, agreed from the relevant government and implemented to operationalise the Institutional mechanism of coordination. | TA implemented | A2.1Technical support to an appropriate Government Agency to establish and operationalise the institutional framework 1) A review of current institutional framework and gap analysis 2) Policy dialogue with parliamentarians and key government agencies on the need of a institutional framework 3) Sharing of international practices 4)TA to the NPC to recommend the institutional framework,including modus operandi, resource requirements, necessary legal and technical tools, including a M and E framework for the establishment and operationalisation of the coordination mechanism (UNICEF/ILO). | [14 empty] | UNICEF, ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2021 Q3 to 2023 Q2
3. Regulations drafted for the establishment and operationalisation of the institutional framework | bar: 2021 Q3 to 2023 Q2
RESULT 3 Increased capacity of Federal and Provincial Governments to plan, budget, implement and monitor extension of contribution –based social protection systems and programmes, overcoming the challenges such as informality, while ensuring financial sustainability of the contributory system. |  | 1. Extension of schemes for informal sector and self-employed designed, including financing analysis | 3. Relevant Government Officials trained on SP financing | Actuarial valuations of 4 schemes | A 3.1. Technical support to build government's capacity on sustainable SP financing and through effective and innovative communication ensure the generated knowledge and results have a meaningful impact in SP financing. 1) Actuarial valuations of 4 contributory schemes to be implemented by SSF 2) Orientation to Social Security Fund Board members to understand the actuarial valuations 3. Redesign the schemes based on Actuarial recommendations 3) Study on the contributory capacity of informal economy workers 4)Assessment of public care services expenditure, cost and financial space and recommendations to improve the care services. 5)estimate the potential fiscal space that could be created assuming a potential increase in social security (contribution-based) coverage or contribution rates or both 6) Design and use communication products to disseminate the knowledge generated and to ensure recommendations are used in policy/programme making 6) Training to relevant government officials on social protection financing 7) Support design of schemes for the informal sector including support to tripartite consultations 8) Support in the first phase implementation of social security schemes to the informal sector 9) Strenghten communications and outreach strategy for the SSF and support in the implementation of communications and outreach plan | [14 empty] | ILO | NPC, Academicians, key SP institutes, CSOs, Wos, Eos | bar: 2021 Q2 to 2021 Q4; 2022 Q2; 2023 Q1 to 2023 Q2
|  | 2. Communication products designed & used to enahance Policy makers'competency in SP financiang | 4. Financing options studied and discussed at Federal and Provincial levels targeting selected informal sectors. | [16 empty] | ILO | bar: 2020 Q4 to 2022 Q2
| 1. IT system evaluated for data security and large data handling, recommendations for improvement made and agreed by SSF. | 1. Capacity development plan implemented in collaboration with various DPS 2. Participatory Systems Review Conducted; 3. Recommendations for system improvement discussed at SSF Board and agreed. 4. SSF Accounting and Financial Reporting Systems Reviewed and Stregthened | Capacity development plan implemented in collaboration with various DPS | Capacity development plan implemented in collaboration with various DPS | A 3.2 Technical Assistance to the SSF for the systems (general administration and HR management, registration, eligibility verification, collection of contributions, case management and distribution of benefits, complaints and appeals mechanisms, and monitoring, evaluation and reporting) improvement and effective implementation of the systems ( ILO) | [15 empty] | SSF, NPC, Workers, Employers
| 4. Orientation to SSF Officials on various components of SP. | 4. TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. 5. Technical/mangerail capacity development needs of different SSF Units identified and HR development paln prepared and agreed by SSF board. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | TA to SSF designed for systems improvement and TA implemented in collaboration with other DPs supporting SSF. | 1) Internal review of the systems and recommendations on areas for improvement 1) Agree on the specif priority areas for improvement and provide technical support for improvement 2) Provide support of IT expert, especially to strengthen the data security and large data handling capacity 3) technical support to SSF establish and operationalise an appeal and grievance handling system 4) Assess the technical capacity gap among the SSF team, determine the learning methods and design a learning plan 5) Plan and organise training programmes 6) Study visit for SSF board members and key SSF Officials to learn from successful experience in the Region 7) Technical support on financial and internal control mechanism | [14 empty] | ILO
RESULT 4 Increased capacity of Federal and Local Governments to revise policies, set standards, oversee, monitor and report the social assistance programmes and to identify options to create fiscal space. | 1. Revise SSA- Social Security guidelines 2. Develop and implement communication strategy | 1. Costing and financing gaps analysis of target 1.3 of SDG (child grant, disability, and old age) 2. Analytical Report Social Assistance produced by DoNIDCR 3. Support selected Flood/Disaster prone Palikas to pre- identify and register disaster vulnerable HHs. | 1. Support DoNIDCR to produce "Analytical Annual Report" knowledge product on Social Production ( SSA) 2. Endline Survery of Coverage of SSA completed |  | 4.1 Generate evidences, policy advocacy and develop/improve necessary tools to improve policies and strengthen quality service delivery, with special attention to the child grant and PWDs. 1. Costing and financing gaps analysis of target 1.3 of SDG (child grant, disability, and old age) 2. Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant (schemes with high exclusion errors) 3. Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) | [14 empty] | UNICEF, NPC, ILO, DONIDCR, NGOs | Research organiazations, Federal government, province and local government | bar: 2020 Q4 to 2023 Q3
| 3.Training Workshop involving Province and Selected Local Government | 4. SMS based technology (RapidPro) for real*time monitoring of implemented in Province 2 &6 5. Selected Palikas in 2 and 6 Establish regular screenings to identify and register PWD into SSAs. | 3. Strengthened complaints and appeal mechanism, the grievance redressal mechanism (GRM) 4. Learning and study visit on shock responsive social protection |  | 4.2 Support capacity development of Provincial and Local Government in effective Implementation of SSA, (registration, timely delivery monitoring, evaluation and reporting). 1. Training Workshop involving Province and Selected Local Government 2. SMS based technology (RapidPro) for real time monitoring of implementation of social protection and other social services in Provinces 2 and 6 (UNICEF). 3. Learning and study visit on shock responsive social protection 4. Improve complaints and appeal mechanism, the grievance redressal mechanism (GRM) . 5. Support to Province 2 and 6 to develop, test and refine improved processes for the assessment of PWD(UNICEF) | [14 empty] | UNICEF, NPC, DONIDCR, NGOs | Research organiazations, Federal government, province and local government
| 4. Sharing Social Protection related evidences, reports |  | 5. Strengthen "Case management" system to include excluded eligible beneficiaries into Social Protection system |  | Technical support to DoNIDCR/NPC to generate evidence, policy advocacy and develop/improve necessary tools to improve policies and procedures for delivering social protection services with special attention to the child grant and PWDs. i.Support the DoNIDCR to conduct a review of MIS system, registration process, grievance handling, payment systems,agree on the actions technical support for improvement including revision of SSA- Guidelines. ii.Analysis of the registration process from a beneficiary's viewpoint: specially the PWDs, eligible households of child grant agree on reforms to simplify and improve the processes, update SSA guidance, and provide iii.Generate updated evidence on access and exclusion rates of SSAs schemes (end-line survey) iv.Support DoNIDCR to produce an "Analytical Annual Report" knowledge product on Social Protection Social Assistance) v.Strengthen social protection system preparedness and response to disaster and emergencies. vi.Develop and implement communication awareness strategy
|  | 6. Simplify complain procedure and case management- or facilitating to obtain required legal documents) 7. DONIDCR Annual Report Published | 6. Monitoring report on timely payment produced.
RESULT 5 Enhanced accountability mechanism at local government level in Province 2 and 6 |  | 1. Palikas agree to publicize the list of beneficiaries and conducting public Audit | 1. Functional Grievance handling Committee |  | Strengthen accountability systems (Programme awareness, registration, eligibility verification, grievance handling, monitoring timely fund flow, payment, and reporting focusing on the child and disability grant). i.Review accountability mechanism of SSAs ii. Strengthen local level Grievance handling mechanism (Publicize list of eligible beneficiaries, simplify complain procedure and improve case management or facilitating eligible but excluded people facilitate to obtain required legal documents) iii. Training Workshop on social protection to Province and selected Local Governments iv.Learning and study visit on shock responsive social protection v. Support ongoing process of pre-identify and register disaster vulnerable HHs and link them with payment structure in additional municipalities vi.Strengthen Local Government capacity to build awareness, identify beneficiaries, organize public audits on social protection. vii. Technical assistance to province-led gender-focused social protection initiatives (i.e. Beti Bachao Beti Padhao programme in Province 2) to reduce gender inequality through social protection. | [14 empty] | UNICEF | bar: 2020 Q4 to 2023 Q1
| 1. Information dissemination | 2. Review improve accountability mechanism of SSAs | bar: 2020 Q4 to 2023 Q1
3. Train local government officials on SP | bar: 2020 Q4 to 2023 Q1
RESULT 6 Nepali Civil Society Organisations and Trade Unions are meaningfully and structurally involved in the development, implementation and monitoring of policy processes regarding social protection and public finance management due to improved coordination and enhanced capacities.6 | Awareness rasied among the local government, csos and communities on social protection | Citizens' participation in monitoring access to social protection and facilitate eligible individuals or HHS to access social protection. | Local government more accountable/ functioning |  | i.Work with DoNIDCR to translate and share revised policy documents, procedure, analytical findings, monitoring reports, with the local government to inform programme performance and its challenges. ii. Ensure citizens' participation in monitoring access to social protection and facilitate eligible individuals or HHS to access social protection. iii. Ensure timely payment as specified in the operational guidelines "2 weeks window" in every trimester by strengthening monitoring process. iv. Collaborate with CSOs to monitor and implement social protection mobilizing a consistent community monitoring approach to track social protection service delivery in focus provinces. | [14 empty] | ILO WSM,UNICEF | Civil society networks, Community groups , l;ocal government | bar: 2020 Q3 to 2023 Q2

## Paraguay
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Paraguay
Impacto
Resultados | Listado de Actividades | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 | TDRs en proceso |  | Metas Anuales
|  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Título de TDR | Productos | 2020 | 2021 | 2022
1. Se identifican las oportunidades para el espacio fiscal y el aumento de la eficacia y eficiencia de las finanzas públicas del SPS. | 1.1 Desarrollar un diagnóstico de la eficiencia presupuestaria y el espacio fiscal del SPS para financiar su expansión | [12 empty] | Indicadores-Costeo- Analsis de Espacios Fiscales | Producto 1: Informe de avance. | 1 (uno) Análisis de brecha de protección social entregado con indicadores desarrollados. | 1 (uno) Costeo de brechas de cobertura de protección social identificadas, análisis del espacio fiscal y priorización para cubrir brechas y proyecciones identificadas con atención al género y la discapacidad entregadas. Publicación y presentación de resultados (incluye taller con experto internacional) realizado. | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
Producto 2: Informe de Antecedentes e Inventario de esquemas e indicadores de Protección Social a partir del documento de configuración del SPS Vamos, aprobado por el Gabinete Social. Producto 3: Revisión de indicadores y formulación de nuevos cuando sea necesario. | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
Producto 4: Estimación de costos y brechas de financiamiento | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
Producto 5: Análisis y cuantificación de opciones de espacio fiscal | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
Producto 6: Informe consolidado y Prdocuto 7: Difusión del conocimiento | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4
| 1.2 Proporcionar evidencia científica sobre los beneficios económicos y sociales de invertir en protección social | [12 empty] | Recolección de datos para VAR | Producto único: Base de datos para estudio internacional VAR | 1 (uno) Análisis de los efectos de la inversión en protección social sobre la pobreza, el empleo, la actividad económica, el bienestar infantil en períodos de crisis y el crecimiento económico entregado. | bar: 2020 Q3 to 2020 Q4
[14 empty] | Análisis de Inversión en Protección Social - Consultor Lider de Proceso - Modelo de Equilibrios Generales | Producto 1: Informe de avance | bar: 2021 Q1; 2021 Q3
[14 empty] | Recolección de datos y apoyo para Modelo de EG. | Producto 2: Informe final y Producto 3: Difusión | bar: 2021 Q1; 2021 Q3
[14 empty] | Economia Política de la Protección Social en Paraguay | Producto 1: Esquema anotado y propuesta metodológica | 1 (uno) Análisis sobre la economía política de la expansión del espacio fiscal para la protección social entregado. | bar: 2020 Q4 to 2021 Q1
Producto 2: Informe preliminar | bar: 2020 Q4 to 2021 Q1
Producto 3: Informe final y productos relacionados | bar: 2020 Q4 to 2021 Q1
Producto 4: Difusión del conocimiento | bar: 2020 Q4 to 2021 Q1
[14 empty] | TBD | TBD | 1 (uno) Publicación y presentación de resultados. | bar: 2021 Q4 to 2022 Q2
2. Primera fase del SPS ¡Vamos! en territorios seleccionados implementados. | 2.1. Identificación y registro de beneficiarios de SPS en 4 distritos seleccionados. | [12 empty] | Aplicación de la Ficha Integrada de Protección Social en el Distrito de Mariscal Estigarribia (Boquerón) | TBD | Lista de beneficiarios de SPS identificados y registrados en 4 distritos seleccionados elaborada. | bar: 2021 Q3 to 2022 Q1
| 2.2.Desarrollar una hoja de ruta de servicios dirigidos a niños de edades comprendidas entre 0 y 4 años en 4 distritos locales. | [12 empty] | Diseño, desarrollo y puesta en marcha de una aplicación para dispositivos móviles para el Sistema de Protección Social. | Producto 1: Minuta de reuniones (Actividad 1). Metodología y plan de trabajo aprobado (Actividad 1). | Se desarrolló una hoja de ruta de servicios dirigidos a niños de edades comprendidas entre 0 y 4 años en 4 distritos locales | bar: 2021 Q1; 2021 Q3
Producto 2: Minuta de reuniones. Proyecto de aplicación móvil, resultante de fase de diseño (Actividad 2). | bar: 2021 Q1; 2021 Q3
Producto 3: Validación de UTGS y UNICEF de diseño de aplicación móvil (Actividad 3). Minutas de reuniones. | bar: 2021 Q1; 2021 Q3
Producto 4: Prototipo de aplicación en base a diseño de aplicación móvil (Actividad 4). Minutas de reuniones. | bar: 2021 Q1; 2021 Q3
Producto 5: Informes quincenales de avances. Aplicación funcionando, en tiempo y forma (Actividad 5). Minutas de reuniones. | bar: 2021 Q1; 2021 Q3
Producto 6: Manuales para a) para administrador b) usuarios diseñados. Informe Final de la consultoría y código fuente (Actividad 5). | bar: 2021 Q1; 2021 Q3
| 2.3. Establecer mecanismos de coordinación subnacionales de todos los sectores involucrados en la implementación en los 4 distritos seleccionados. | [12 empty] | Contratación de Enlace Territorial de la Unidad Técnica del Gabinete Social para la implementación del Sistema de Protección Social (para cada territorio: 4) | Primer producto • Plan de trabajo • Informe de Avance Productos mensuales • Informes de Avance, que reportará las gestiones realizadas conforme al Plan de Trabajo, declarando las restricciones encontradas durante el periodo reportado y anexando los entregables que el profesional haya desarrollado en el marco del cumplimiento de sus tareas. | Mecanismos de coordinación subnacionales de todos los sectores involucrados con la implementación en los 4 distritos seleccionados establecidos. | bar: 2021 Q1; 2021 Q3 to 2021 Q4
| 2.4 Capacitación de capacidades de recursos humanos a nivel local para planificar y monitorear la prestación de servicios a niños de 0 a 4 años. | [12 empty] | Capacitación en planificación, monitoreo y gestión territorial con énfasis en Gestión Basada en Resultados (GbR), para RRHH del nivel central y territorial vinculado al paquete de servicios del Sistema de Protección Social Vamos! | TBD | Plan de estudios de capacitación desarrollado | bar: 2022 Q1 to 2022 Q4
| 2.5 Elaboración de los manuales de implementación del SPS ¡Vamos! a nivel local, con herramientas y / o instrumentos relacionados | [12 empty] | TBD | TBD |  |  | Manual (es) de implementación del SPS ¡Vamos! a nivel local, con herramientas y / o instrumentos relacionados elaborados | bar: 2022 Q1 to 2022 Q4
| 2.6. Evaluación de la implementación del SPS vamos en distritos seleccionados con recomendaciones para ampliar | [12 empty] | TBD | TBD |  |  | Implementación del SPS vamos en distritos seleccionados con recomendaciones de escalamiento evaluadas. | bar: 2022 Q1 to 2022 Q4
3. Fortalecimiento de la capacidad de los profesionales del servicio público y las organizaciones de la sociedad civil para monitorear y evaluar los programas de protección social en el contexto de un presupuesto basado en resultados. | 3.1 Programa de desarrollo de habilidades diseñado para profesionales del servicio público y miembros de la sociedad civil sobre sistemas de protección social con enfoque de ciclo de vida y presupuestos basados ​​en resultados | [12 empty] | Desarrollo de Programa - Diplomado en PpR y SPS | Producto 1: Malla curricular. |  | Programa de desarrollo de habilidades (en línea y presencial) para funcionarios públicos y miembros de la sociedad civil diseñados y puestos a prueba. | bar: 2021 Q1
Producto 2: Contenidos de la malla curricular y estrategia pedagógica | bar: 2021 Q1
Producto 3: Estrategia de convocatoria | bar: 2021 Q1
[14 empty] | Diplomando en PpR y SPS | TBD | bar: 2022 Q1 to 2022 Q2
| 3.2 Fortalecimiento de la capacidad en la Dirección General de Presupuestos para el monitoreo y evaluación de los programas de protección social en el contexto de la presupuestación basada en resultados con un enfoque en los programas incluidos en el SPS ¡Vamos! | [12 empty] | Uso de herramientas de evaluación y monitoreo para programas de protección social en el contexto de la elaboración de presupuestos basados ​​en resultados. | TBD |  | 1 (uno) Taller para el personal de la Dirección General de Presupuestos sobre el uso de herramientas de evaluación y monitoreo para programas de protección social en el contexto de la elaboración de presupuestos basados ​​en resultados. | Se proporcionan herramientas sobre la evaluación y el seguimiento de los programas de protección social en el contexto de la presupuestación basada en resultados. 1 (uno) Taller para el personal de la Dirección General de Presupuestos sobre el uso de herramientas de evaluación y monitoreo para programas de protección social en el contexto de la elaboración de presupuestos basados ​​en resultados. | bar: 2021 Q4
| 3.3 Desarrollo de habilidades para profesionales del servicio público y miembros de la sociedad civil sobre financiamiento público para protección social | [12 empty] | Curso Online - Finanzas públicas y protección Social | Culminado | 3 (tres) Participantes en el curso "Finanzas públicas para analistas de protección social". 1 (uno) Participante en el curso "Gestión de las finanzas públicas para niños" sobre el seguimiento de la inversión pública en niños y la protección social. | 3 (tres) Participantes en el curso "Finanzas públicas para analistas de protección social". 1 (uno) Participante en el curso "Gestión de las finanzas públicas para niños" sobre el seguimiento de la inversión pública en niños y la protección social. 1 (uno) Participante en el curso "Gestión de las finanzas públicas para niños" sobre el seguimiento de la inversión pública en niños y la protección social. 1 (one) Participant in the "Public Finance Management for Children" course on monitoring public investment in children and social protection. | 3 (tres) Participantes en el curso "Finanzas públicas para analistas de protección social". | bar: 2020 Q4
[14 empty] | Adaptación al español del Curso Finanzas Públicas y Protección Social. | Producto 1: Adaptación | bar: 2020 Q4 to 2021 Q1
Producto 2: Curso | bar: 2021 Q3
4. Conocimiento, propiedad y demanda de SPS ¡Vamos! dentro de las instituciones públicas, los proveedores de servicios y los beneficiarios aumentaron. | 4.1 Diseño de una estrategia de comunicación general para el SPS ¡Vamos! | [12 empty] | Consultoría Institucional para la elaboración de la estrategia de comunicación del sistema de protección social VAMOS | Producto 1: Documento de planteamiento metodológico para realizar el diseño de la estrategia de comunicación, que incluya: # Plan de trabajo y cronograma # Propuesta metodológica para el diseño de la Estrategia de Comunicación. # Identificación de roles involucrados | Estrategia general de comunicación para el SPS ¡Vamos! diseñado. | bar: 2021 Q1
Producto 2. Documento de diagnóstico comunicacional y levantamiento de información en la UTGS, así como de los talleres con comunicadores de instituciones aliadas, que incluya: # Resultado de revisión documental del SPS y materiales de comunicación. Experiencia internacional de estrategias de comunicación en la instalación de Sistemas de Protección Social. # Resultado de talleres impartidos en la UTGS y con instituciones aliadas. # Estudio de percepción desarrollado en localidades donde se llevará a cabo la primera etapa. (la implementación del estudio de percepción no forma parte de esta consultoría) # Primera estructura de Documento de Estrategia de Comunicación; que incluya el marco de referencia, la introducción los objetivos, públicos meta y acciones. | bar: 2021 Q1
Producto 3. Segunda entrega de Documento de Estrategia de Comunicación; que detalle los objetivos, públicos meta, el conjunto de acciones, productos, plazos, responsables (incluyendo equipo humano). # Documento que describa las principales líneas de contenido identificadas, el medio de documentación, desarrollo de la línea editorial y su bajada discursiva para voceros (debe formar parte de la estrategia). | bar: 2021 Q1
Producto 4. Tercera entrega de Documento de Estrategia de Comunicación; que incorpore ajustes recibidos de la UTGS/UGPR. Incluir el proceso de transición entre Gobiernos, de tal forma a generar condiciones para trascender a una Política de Estado. # Documento de branding y desarrollo de imagen gráfica del SPS con su manual de uso y aplicación. | bar: 2021 Q1
Producto 5. Documento de Estrategia de Comunicación; que detalle los objetivos, públicos meta, el conjunto de acciones, productos, plazos, responsables y recursos requeridos final. | bar: 2021 Q1
Producto 6. Informe final conteniendo todos los productos especificados para esta consultoría y su protocolo de uso. | bar: 2021 Q1
[14 empty] | Consultoría de apoyo a la implementeción de la estrategia de comunicación para el Sistema de Protección Social (SPS) Vamos! | Producto 1: Plan de trabajo. - Informe de avance de tareas. | bar: 2021 Q1
Producto mensual: Informe sobre avances de las acciones y resultados en las diferentes líneas de acción mencionadas en el plan de trabajo, que incluya las versiones preliminares/finales de los entregables definidos en las actividades - Minutas de reuniones | bar: 2021 Q1
| 4.2 Diseño de productos de comunicación para sensibilizar a los tomadores de decisiones sobre el SPS ¡Vamos! | [12 empty] | TBD | TBD |  | Productos de comunicación para sensibilizar a los tomadores de decisiones sobre el SPS ¡Vamos! diseñado | bar: 2021 Q3
| 4.3 Implementar actividades de difusión en instituciones públicas involucradas en la implementación del SPS Vamos! a nivel nacional y local | [12 empty] | TBD | TBD |  | Actividades de difusión en instituciones públicas involucradas en la implementación del SPS Vamos! a nivel nacional y local implementado. | bar: 2021 Q3 to 2022 Q2
| 4. 4. Aumentar la conciencia, el nivel de conocimiento y la demanda de SPS Vamos entre los beneficiarios en 4 distritos seleccionados. Aumentar la conciencia. | [12 empty] | TBD | TBD |  |  | Se incrementó la conciencia, el nivel de conocimiento y la demanda de SPS Vamos entre los beneficiarios en 5 distritos seleccionados | bar: 2022 Q1 to 2022 Q3

## Senegal
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Senegal
|  | 2020 |  | 2021 |  |  |  | 2022 |  |  |  | 2023
Objectives | Responsible Organization | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
5.1 (SO1) To improve Senegal's design and financing of social protection systems in support to their efforts towards SDGs 1 and 10
5.1.1 (R1.1) Adequate, sustainable and gender-sensitive social protection financing through improved cross-sector co-ordination in coherence with national macro-economic, fiscal, digital and SDG strategies as well as diversification of sources of financing and increased fiscal space available for all social sectors to progressively achieving universal social protection
5.1.1.1 (output) Tools, mecanisms and unified budget framework for an adequat, sustainable, gender and disability sensitive are available.
5.1.1.1. Estimate the cost the Plus component (integrated social services) of the PNBSF in view of sustainable financing through national resources | UNICEF | bar: 2022 Q1 to 2022 Q2
5.1.1.2 Strengthen national capacities on public finance management and financing of social protection (with reference to the ILO Handbook on Fiscal Space) | BIT | bar: 2020 Q4; 2021 Q2
5.1.1.3 Deepen the fiscal space analysis, design and implement innovative financing options, including new taxes, budget reallocation, measures and mechanisms for capturing the contributory capacity of workers of the informal and rural economy | BIT/UNICEF | bar: 2021 Q1 to 2021 Q2; 2022 Q2
5.1.1.4 Support the updating of the social protection financing strategy/plan and the development and implementation of monitoring tools and framework of the national social protection (including budgets, in relation with EU budget supports). | BIT/UNICEF | bar: 2021 Q3 to 2021 Q4
5.1.2. (R1.2) Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations
5.1.2.1 (output) The social protection systems is reinforced with tools and evidences to guide policy making for its improvement.
5.1.2.1 Conduct a gender and a disability-sensitive review of the social protection system. | BIT/UNICEF | bar: 2020 Q3 to 2021 Q1
5.1.2.2. Support a public expenditures review of the social protection schemes and programmes (PER) | BIT/UNICEF | bar: 2021 Q3 to 2021 Q4
5.1.2.3 Realize a efficiency analysis of public allocation (DEA) in Education sector in the context of free fees policy | UNICEF | bar: 2021 Q1 to 2021 Q2
5.2. (SO2) To support governments in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability
5.2.1. (R2.1) Strengthened capacities of partner countries to achieve the best impact of diversified sources of funding for social protection, prioritizing women, children, persons with disabilities, informal economy and migrant workers.
5.2.1.1 (output) Technical capacity of institutional actors, including social partenrs and the civil society, to extend social protection coverage to workers in the informal and rural economy, as also a strategy for sustainable and adequat social protection financing, and people with disability are strengthened.
5.2.1.1 Provide technical assistance for the effective implementation of the simplified scheme for independent workers and workers in the informal economy | BIT | bar: 2021 Q3 to 2023 Q1
5.2.1.2 Build capacity of the line Ministries, IPRES, CSS, ANCMU, workers’ organizations to effectively run the simplified scheme and support its scaling up | BIT | bar: 2022 Q3 to 2023 Q1
5.2.1.3 Provide technical services and strengthen capacities for the improvement of the coverage, effectiveness, and financial sustainability of the Universal Health Care Coverage (CMU) programme. | BIT | bar: 2021 Q3 to 2022 Q4
5.2.1.2 (output) Capacities of institutional actors and civil society for an improved targeting of non-contributory programmes beneficiairies and people with disabilities are strengthened in view of reinforcing advocacy for adequat and diversified social protection financing
5.2.1.4.Provide technical assistance for improving the CEC programme, including a better definition of a disability-sensitive service package | BIT | bar: 2020 Q4 to 2021 Q1
5.2.1.5. Support the updating of the database of the national unified registry (RNU), in relation with the EU budget support***. | UNICEF | bar: 2020 Q3 to 2021 Q1
5.2.1.6. Support the promotion of essential family practices (Behaviour change communication activities) - monitoring of key family practices*** | UNICEF | bar: 2020 Q4 to 2021 Q2; 2022 Q1 to 2022 Q2
5.2.2. (R2.2) Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society.
5.2.2.1 Build capacity of sub-national government’s institutions for an improved implementation of the SNPS and social protection programmes (platform)
5.2.2.1 Build capacity of sub-national government’s institutions for an improved implementation of the SNPS and social protection programmes (platform)*** | UNICEF | bar: 2021 Q1; 2022 Q1; 2023 Q1
5.2.2.2 Build capacity of the OSBS for a real-time monitoring, adequacy and sustainability of public spending in social protection sectors*** | UNICEF | bar: 2021 Q2; 2022 Q2; 2023 Q1
5.2.2.3. Strengthen knowledge and capacity of parliamentarians and members of the CESE, HCCT, HCDS for a better understanding of the Pluriannual Budget Programme Documents and draft national budgets*** | BIT/UNICEF | bar: 2021 Q2; 2022 Q2
5.2.2.4. Document and disseminate good practices of gender-sensitive and disability-sensitive social protection interventions and extension to workers in the informal economy (briefs, videos and experience sharing with sub-national government entities). | BIT/UNICEF | bar: 2022 Q1 to 2022 Q2; 2023 Q1 to 2023 Q2
5.2.2.5. Capitalize and share documented good practices and country experiences, notably through the Regional social accountability platform for West and Central Africa. | UNICEF | bar: 2020 Q4 to 2021 Q1
5.2.2.2 (output) Capacities of the civil society, social partners, and actors of the private sector and local actors for an improved transparency, monitory and accountability of national social protection budgets are strengthened
5.2.2.6. Enhanced local and national media and press capacities to support and relay advocacy for increased social protection financing. | UNICEF | bar: 2021 Q1; 2022 Q1; 2023 Q1
5.2.2.7. With support of the Global coalition for social protection floors, implement information and capacity building activities of actors of the civil society and workers' representatives in the budget planning and monitoring tools, for accelerated advocacy for extending gender- and disability-sensitive adequate social protection, and secured by transparent and sustainable financing | CGSPF | bar: 2020 Q4 to 2022 Q1
5.2.2.8. Organize awareness raising activities among employers and private sector on the importance of social protection, governance and monitoring tools of the social protection sector and also prevent COVID 19 in the world of work | BIT/UNICEF | bar: 2020 Q4 to 2021 Q1; 2021 Q3 to 2021 Q4; 2022 Q3 to 2022 Q4
5.2.2.9. Support Citizens Budgets to improve public understanding and ownership of social protection programmes and spending*** | UNICEF | bar: 2021 Q1 to 2021 Q2; 2022 Q1 to 2022 Q2; 2023 Q1
5.3. (SO3) To assist partner countries in developing and applying shock-sensitive social protection programmes and systems adapted to the needs of those living in protracted fragility and crises, including forcibly displaced persons
5.3.1. (R3.1) Increased capacities of partner countries in the context of emergencies, natural disasters, forced displacements, protracted fragility and crises to establish contingency plans and multi-year funding strategies to run adaptive social protection mechanisms
5.3.1.1 (output) National capacities to implement mecanisms and measures to finance social protection in context of crisis, natural disasters and displaced people are reinforced
5.3.1.1. Conduct a child poverty analysis (Multiple Overlapping Deprivation Analysis) in order to strengthen children-sensitive cash transfers and better meet children needs, notably in terms of nutrition and food security | UNICEF | bar: 2020 Q4 to 2021 Q1; 2021 Q4
5.3.1.2 Propose mechanisms for improving coordination between food insecurity interventions and existing social protection measures and programmes | UNICEF | bar: 2021 Q1 to 2021 Q2; 2022 Q1
6.3.Communication and visibility costs | BIT/UNICEF
6.4. Validation workshops
6.4.1 Validation workshop and dissemination results of the estimation cost of the plus component of PNBSF | UNICEF | bar: 2022 Q1
6.4.2 Validation workshop and dissemination results PER of social protection programme | UNICEF | bar: 2021 Q1
6.4.3 Validation workshop and dissemination results of the social fiscal expenditure | UNICEF | bar: 2021 Q3
6.4.4 Validation workshop and dissemination results of the efficiency analysis of public allocation (DEA) in Education sector | UNICEF | bar: 2022 Q4
6.4.5 Validation workshop and dissemination results of the Child Poverty and Multiple Deprivation Report (MODA) | UNICEF | bar: 2021 Q3
6.4.6 Validation workshop and dissemination results of the final evalution of the project | UNICEF | bar: 2023 Q1
6.4.7 Validation workshop and dissemination results of the gender and the disability-sensitive review of the social protection system | BIT/UNICEF | bar: 2021 Q3 to 2021 Q4
6.4.8. Workshop of the project's launch | BIT/UNICEF | bar: 2021 Q1 to 2021 Q2
6.4.9 Validation workshop and dissemination results of legal, institutional, operational and administrative framework and IT system of the simplified scheme | BIT | bar: 2021 Q4 to 2022 Q2
6.4.10 Validation workshop and dissemination results of options for improving disability-sensitive social programmes, including the CEC | BIT | bar: 2021 Q3 to 2021 Q4
6.4.11 Validation workshop and dissemination results of options for improving the CMU coverage | BIT | bar: 2021 Q2 to 2021 Q3
6.4.12 Meetings and workshops of the working group and steering committee | BIT | bar: 2021 Q1; 2022 Q1; 2023 Q1

## Uganda
GLO/19/53/EUR - SC 190731 | Improving Synergies between social protection and public finance management
Country Project Workplan
Uganda
Overall objective: To increase the population's universal social protection coverage in partner countries preferably but not limited to those benefiting from EU funded budget support operations
Outcome/s and Result/s | Annual target/s | List of activities | 2021 |  |  |  | Responsible PUNO/s | Implementing partner/s involved
| 2021 |  | Q1 | Q2 | Q3 | Q4
Outcome (SO 1): To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10. |  | Support to the GoU in publishing programmatic documents and establishing mechanisms to scale and sustain SP for children |  |  |  |  | UNICEF | MoGLSD / KCCA
Result (R 1.1): Increased dialogue and coherence among sectors for the sustainable and adequate financing of universal social protection | Participation in at least 3 coordination meetings with government, donors, and/or CSOs per year | A.1.1.1a Technical support for the implementation of the National Social Protection Policy; Participation in sector working groups and steering committee meetings; |  |  |  | X | UNICEF | MoGLSD / KCCA
| Compile national dialogue report | A.1.1.1b Assessment Based National Dialogue (ABND) Social Protection Policy Options Tools (SPPOT) | X | X | X | X | ILO | MoGLSD
| Facilitate at least 4 CSO and TU advocacy activities | A.1.1.2 Facilitate civil society and trade union advocacy activities towards key social protection policy and budgetary processes for improved and expanded social protection | X | X | X | X | HAI | Uganda Social Protection Platform, relevant trade unions
Result (R 1.2): Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations. | 3 operational research studies implemented and leveraged for evidence-based decision-making by GoU; 1 policy brief on key issues of SP and PFM published; | A.1.2.1a Qualitative research studies on gender- and age-responsive social protection; A.1.2.1b Quantitative administrative and policy advocacy data, as well as operational research in the context of KCCA's urban social protection programme for adolescent girls; A.1.2.1c Development of policy advocacy briefs on key issues of SP and PFM that support KCCA in advocating for increased investments in social protection for vulnerable groups with MoFPED and others; |  |  |  | X | UNICEF | MoGLSD / KCCA / MoFPED /
| Research on informal and rural economy economy | A.1.2.1d Study on informal and rural economy, including recommendations for increasing coverage and exploring innovative financing options (ILO) | X | X |  |  | ILO | MGLSD
| Actuaurial review of NSSF | A.1.2.1e Governance and administrative review of National Social Security Fund | X | X | X | X | ILO | NSSF
| Research on social accountability mechanisms for social protection | A.1.2.1f Study on the effectiveness of Uganda’s social accountability mechanisms in improving the design and implementation of social protection programmes | X | X | X | X | HAI | Uganda Social Protection Platform
|  | A.1.2.1g Civil society advocacy policy briefs on expanded and improved social protection, impacts of Uganda’s social protection programmes and voices of beneficiaries (based on social accountability initiatives) age, gender and disability lens (HAI) |  |  | X | X | HAI | Uganda Social Protection Platform
Outcome (SO 2): To support the government in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability. |  | Support to the GoU and collaboration with key stakeholders towards the development and piloting of a shared civil society social accountability approach |  |  |  |  | HAI | GoU, CSOs
Result (R2.1): Strengthened capacities of partners to achieve the best impact of diversified sources of funding for social protection, prioritizing children, workers in the informal sector, and older persons. | At least 2 strategically selected officials from MoFPED, KCCA, NSSF, and/or MoGLSD supported to attend PFM and SP training (ILO) | A.2.1.1 Support for strategically selected government officials to participate in PFM and SP training (ILO) | x |  |  | X | ILO | MoFPED, KCCA, NSSF, and/or MoGLSD
|  | A.2.1.2 Facilitate international peer-learning and knowledge exchange on social protection and PFM |  |  |  | X | HAI | Uganda Social Protection Platform; GCSPF target countries in Action
| At least 60 CSO and Trade Union members are trained on social protection and public financial management | A.2.1.3 Increase capacity of CSO and Trade Union members on social protection, public financial management | X |  | X |  | HAI | Uganda Social Protection Platform, relevant trade unions
Result (R 2.2): Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society | Support for 6 gov. officials to attend relevant SP conferences (UNICEF supporting 4, ILO supporting 2); | A.2.2.1 Build the capacity of national policymakers for planning and management of social protection programmes through knowledge-sharing and coordination activities, including supporting the participation of government officials in relevant SP conferences; |  |  |  | X | UNICEF, ILO | MoGLSD / KCCA / WB
| Pilot the approach to grassroots/community-based social accountability for relevant social assistance programmes | A.2.2.2 Develop and pilot a shared civil society approach to grassroots/community-based social accountability for relevant social assistance programmes | X | X | X |  | HAI | Uganda Social Protection Platform
|  | A.2.2.3 Increase capacity of CSOs on grassroots/community-based social accountability |  |  |  |  | HAI | Uganda Social Protection Platform
| One programme document on urban social protection programme for adolescent girls; | A.2.2.4 Support to GoU (KCCA) in the development of programmatic documents for their urban social protection programme for adolescent girls; Support to GoU (KCCA) in establishing mechanisms to sustain and scale SP for children; | X |  |  |  | UNICEF | MoGLSD/KCCA
| At least one multi-stakeholder dialogue event to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | A.2.2.5 Organise multi-stakeholder dialogue events to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP |  |  |  | X | ILO | GOU, DPs, CSOs, UNICEF, HAI